## MSP Download (hidden)
New WBS | Task Name | Duration | Start | Finish | % Complete
| HM Probation Reform Programme | 1 day | Tue 14/04/20 | Tue 14/04/20 | 0%
SNP-MIL | Snapshot Milestones | 1567 days | Wed 01/01/20 | Thu 01/01/26 | 0%
SNP-MIL-10 | Start of 2019 Probation Reform Programme Scope | 0 days | Tue 01/01/19 | Tue 01/01/19 | 0%
SNP-MIL-20 | Snapshot 0 - January 2020 | 0 days | Wed 01/01/20 | Wed 01/01/20 | 100%
SNP-MIL-30 | Snapshot 1 - April 2020 | 0 days | Wed 01/04/20 | Wed 01/04/20 | 100%
SNP-MIL-40 | Snapshot 2 - July 2020 | 0 days | Wed 01/07/20 | Wed 01/07/20 | 0%
SNP-MIL-50 | Snapshot 3 - October 2020 | 0 days | Thu 01/10/20 | Thu 01/10/20 | 0%
SNP-MIL-60 | Snapshot 4 - January 2021 | 0 days | Fri 01/01/21 | Fri 01/01/21 | 0%
SNP-MIL-70 | Snapshot 5 - April 2021 | 0 days | Thu 01/04/21 | Thu 01/04/21 | 0%
SNP-MIL-80 | Day 1 Snapshot - June 2021 | 0 days | Mon 28/06/21 | Mon 28/06/21 | 0%
SNP-MIL-90 | 2022 Snapshot | 0 days | Mon 03/01/22 | Mon 03/01/22 | 0%
SNP-MIL-100 | 2026 Snapshot | 0 days | Thu 01/01/26 | Thu 01/01/26 | 0%
PRP-MIL | Programme Milestones | 255 days | Wed 20/11/19 | Wed 11/11/20 | 0%
PRP-MIL-10 | Outline Business Case (OBC) 1 Approved | 0 days | Thu 13/02/20 | Thu 13/02/20 | 100%
PRP-MIL-20 | Day One Defined | 0 days | Thu 21/11/19 | Thu 21/11/19 | 100%
PRP-MIL-30 | Programme Vision Finalised | 0 days | Mon 02/12/19 | Mon 02/12/19 | 100%
PRP-MIL-40 | Wales Transferred | 0 days | Fri 13/12/19 | Fri 13/12/19 | 100%
PRP-MIL-50 | Baseline Plan Version 1 | 0 days | Mon 23/12/19 | Mon 23/12/19 | 100%
PRP-MIL-60 | Regional Deep Dives Start | 0 days | Tue 14/01/20 | Tue 14/01/20 | 100%
PRP-MIL-70 | Detailed Design of Day 1 Um Approved | 0 days | Mon 02/03/20 | Mon 02/03/20 | 100%
PRP-MIL-80 | Change Strategy Approval | 0 days | Mon 02/03/20 | Mon 02/03/20 | 100%
PRP-MIL-90 | Business Readiness Framework & Regional Transition Plans Developed | 0 days | Tue 31/03/20 | Tue 31/03/20 | 100%
PRP-MIL-100 | Regional Director Induction | 0 days | Thu 02/04/20 | Thu 02/04/20 | 100%
PRP-MIL-110 | Q1 Planning Review | 0 days | Thu 02/04/20 | Thu 02/04/20 | 100%
PRP-MIL-120 | Outline Business Case (OBC) 2 Approved | 0 days | Fri 15/05/20 | Fri 15/05/20 | 0%
PRP-MIL-130 | Regional Change Impact Assessment Completed | 0 days | Wed 01/07/20 | Wed 01/07/20 | 0%
PRP-MIL-140 | Change Management and Communications Plan Fully Aligned | 0 days | Wed 01/07/20 | Wed 01/07/20 | 0%
PRP-MIL-150 | Q2 Planning Review | 0 days | Thu 02/07/20 | Thu 02/07/20 | 0%
PRP-MIL-160 | Q3 Planning Review | 0 days | Fri 02/10/20 | Fri 02/10/20 | 0%
PRP-MIL-170 | Full Business Case (FBC) Approval | 0 days | Thu 12/11/20 | Thu 12/11/20 | 0%
PRP-MIL-180 | Q4 Planning Review | 0 days | Tue 02/06/20 | Tue 02/06/20 | 0%
PRP-MIL-190 | Day One - Go Live | 0 days | Fri 26/06/20 | Fri 26/06/20 | 0%
PRP-B | BEBE | 1652 days | Mon 02/09/19 | Tue 30/12/25 | 7%
PRP-B-MIL | Milestones | 692 days | Wed 06/05/20 | Thu 29/12/22 | 0%
PRP-B-MIL-010 | Outline Business Case 2 | 0 days | Thu 07/05/20 | Thu 07/05/20 | 0%
PRP-B-MIL-020 | Full Business Case | 0 days | Mon 02/11/20 | Mon 02/11/20 | 0%
PRP-B-MIL-030 | Efficiencies Analysis | 0 days | Tue 19/05/20 | Tue 19/05/20 | 0%
PRP-B-MIL-040 | Benefits Realisation Plan | 0 days | Mon 28/09/20 | Mon 28/09/20 | 0%
PRP-B-MIL-050 | Evaluation | 0 days | Mon 02/01/23 | Mon 02/01/23 | 0%
PRP-B-BSC | Business Case | 200 days | Fri 31/01/20 | Thu 05/11/20 | 0%
PRP-B-BSC-010 | First 'should-cost' assumptions locked down | 0 days | Fri 31/01/20 | Fri 31/01/20 | 100%
PRP-B-BSC-020 | First outline Business Case draft submission | 0 days | Fri 07/02/20 | Fri 07/02/20 | 100%
PRP-B-BSC-030 | Outline Business Case version one | 0 days | Wed 12/02/20 | Wed 12/02/20 | 100%
PRP-B-BSC-040 | First version of 'should-cost' model available for QA | 0 days | Fri 14/02/20 | Fri 14/02/20 | 100%
PRP-B-BSC-050 | Second 'should-cost' assumptions locked down | 0 days | Fri 21/02/20 | Fri 21/02/20 | 100%
PRP-B-BSC-060 | Second Outline Business Case draft submission | 0 days | Fri 28/02/20 | Fri 28/02/20 | 100%
PRP-B-BSC-070 | Outline Business Case version two | 0 days | Wed 04/03/20 | Wed 04/03/20 | 100%
PRP-B-BSC-080 | Second version of 'should-cost' model available for QA | 0 days | Fri 06/03/20 | Fri 06/03/20 | 100%
PRP-B-BSC-090 | Third Outline Business Case draft submission | 0 days | Fri 20/03/20 | Fri 20/03/20 | 100%
PRP-B-BSC-100 | Outline Business Case version three | 0 days | Wed 25/03/20 | Wed 25/03/20 | 100%
PRP-B-BSC-110 | Fourth outline Business Case draft and annex submissions | 0 days | Fri 03/04/20 | Fri 03/04/20 | 100%
PRP-B-BSC-120 | Outline Business Case version four | 0 days | Wed 08/04/20 | Wed 08/04/20 | 100%
PRP-B-BSC-130 | Outline Business Case quality checking | 0 days | Mon 13/04/20 | Mon 13/04/20 | 100%
PRP-B-BSC-140 | Final 'should-cost' model locked down | 0 days | Thu 16/04/20 | Thu 16/04/20 | 100%
PRP-B-BSC-150 | Outline Business Case Programme Board Approval | 0 days | Wed 22/04/20 | Wed 22/04/20 | 0%
PRP-B-BSC-160 | Post-keyholder edits submitted | 0 days | Fri 01/05/20 | Fri 01/05/20 | 0%
PRP-B-BSC-170 | Outline Business Case Final Version | 0 days | Thu 07/05/20 | Thu 07/05/20 | 0%
PRP-B-BSC-180 | Against Go/No Go decision on OBC Validity | 0 days | Thu 07/05/20 | Thu 07/05/20 | 0%
PRP-B-BSC-190 | Investco approval - OBC | 0 days | Wed 13/05/20 | Wed 13/05/20 | 0%
PRP-B-BSC-200 | Review of OBC conducted by HMT & Cabinent Office | 0 days | Wed 13/05/20 | Wed 13/05/20 | 0%
PRP-B-BSC-210 | Start work on FBC | 0 days | Wed 13/05/20 | Wed 13/05/20 | 0%
PRP-B-BSC-220 | MPRG approval - OBC | 0 days | Mon 08/06/20 | Mon 08/06/20 | 0%
PRP-B-BSC-230 | Start of work on FBC | 11 days | Mon 08/06/20 | Mon 22/06/20 | 0%
PRP-B-BSC-240 | Contract Signing | 0 days | Mon 02/11/20 | Mon 02/11/20 | 0%
PRP-B-BSC-250 | Written FPRG Approval | 0 days | Mon 02/11/20 | Mon 02/11/20 | 0%
PRP-B-BSC-260 | MPRG Approval - FBC | 0 days | Mon 02/11/20 | Mon 02/11/20 | 0%
PRP-B-BSC-270 | Investco approval - FBC | 0 days | Mon 02/11/20 | Mon 02/11/20 | 0%
PRP-B-EFF | Efficiencies | 96 days | Mon 06/01/20 | Mon 18/05/20 | 86%
PRP-B-EFF-010 | Sign off of Project Plan | 0 days | Mon 06/01/20 | Mon 06/01/20 | 100%
PRP-B-EFF-020 | Schedule Interviews | 5 days | Tue 07/01/20 | Mon 13/01/20 | 100%
PRP-B-EFF-030 | Conduct Interviews | 15 days | Tue 14/01/20 | Mon 03/02/20 | 100%
PRP-B-EFF-040 | Analyse Interview Data | 15 days | Tue 04/02/20 | Mon 24/02/20 | 100%
PRP-B-EFF-090 | Interrogate assumptions | 6 days | Tue 25/02/20 | Tue 03/03/20 | 100%
PRP-B-EFF-100 | Arrange meetings with assumptions owners to discuss | 6 days | Wed 04/03/20 | Wed 11/03/20 | 100%
PRP-B-EFF-120 | Quality assurance of any analysis | 3 days | Thu 12/03/20 | Mon 16/03/20 | 100%
PRP-B-EFF-130 | Draft narrative written up | 4 days | Thu 12/03/20 | Tue 17/03/20 | 100%
PRP-B-EFF-140 | Comments taken | 4 days | Wed 18/03/20 | Mon 23/03/20 | 100%
PRP-B-EFF-150 | Final narrative produced | 4 days | Tue 24/03/20 | Fri 27/03/20 | 100%
PRP-B-EFF-160 | Efficiencies Analysis Report [PPB draft] | 8 days | Mon 30/03/20 | Wed 08/04/20 | 100%
PRP-B-EFF-170 | Scoping efficiencies analysis for full business case | 11 days | Mon 04/05/20 | Mon 18/05/20 | 0%
PRP-B-BEN | Benefits | 584 days | Mon 02/12/19 | Thu 24/02/22 | 7%
PRP-B-BEN-010 | Develop benefits map - OBC version 3 | 86 days | Mon 02/12/19 | Mon 30/03/20 | 100%
PRP-B-BEN-020 | Identify benefits measures - OBC version 3 | 86 days | Mon 02/12/19 | Mon 30/03/20 | 100%
PRP-B-BEN-030 | Develop benefit profile agreements - version 1 | 51 days | Mon 20/01/20 | Mon 30/03/20 | 100%
PRP-B-BEN-040 | Develop methodology/narrative - version 1 | 51 days | Mon 20/01/20 | Mon 30/03/20 | 100%
PRP-B-BEN-050 | Identify major realisation milestones - version 1 | 61 days | Mon 06/01/20 | Mon 30/03/20 | 100%
PRP-B-BEN-060 | Develop benefits map - OBC final version | 109 days | Tue 31/03/20 | Fri 28/08/20 | 0%
PRP-B-BEN-070 | Identify benefits measures - OBC final version | 109 days | Tue 31/03/20 | Fri 28/08/20 | 0%
PRP-B-BEN-080 | Detail measures and metrics - OBC final version | 74 days | Mon 20/01/20 | Thu 30/04/20 | 0%
PRP-B-BEN-090 | Identify benefit owners - OBC final version | 74 days | Mon 20/01/20 | Thu 30/04/20 | 0%
PRP-B-BEN-100 | Develop benefit profile agreements - OBC final version | 74 days | Tue 31/03/20 | Fri 10/07/20 | 0%
PRP-B-BEN-110 | Develop methodology/narrative - OBC final version | 74 days | Tue 31/03/20 | Fri 10/07/20 | 0%
PRP-B-BEN-120 | Develop plan template - OBC final version | 84 days | Mon 06/01/20 | Thu 30/04/20 | 0%
PRP-B-BEN-130 | Identify major realisation milestones - OBC final version | 84 days | Tue 31/03/20 | Fri 24/07/20 | 0%
PRP-B-BEN-140 | Develop benefits map - revision | 174 days | Mon 31/08/20 | Thu 29/04/21 | 0%
PRP-B-BEN-150 | Identify benefits measures - revision | 174 days | Mon 31/08/20 | Thu 29/04/21 | 0%
PRP-B-BEN-160 | Detail measures and metrics - revision | 139 days | Fri 01/05/20 | Wed 11/11/20 | 0%
PRP-B-BEN-170 | Identify benefit owners revision | 139 days | Fri 01/05/20 | Wed 11/11/20 | 0%
PRP-B-BEN-180 | Develop benefit profile agreements - Full Business Case Draft | 160 days | Mon 13/07/20 | Fri 19/02/21 | 0%
PRP-B-BEN-190 | Develop methodology/narrative - Full Business Case Draft | 160 days | Mon 13/07/20 | Fri 19/02/21 | 0%
PRP-B-BEN-200 | Develop plan template - Full Business Case Draft | 170 days | Fri 01/05/20 | Thu 24/12/20 | 0%
PRP-B-BEN-210 | Identify major realisation milestones - Full Business Case Draft | 169 days | Mon 27/07/20 | Thu 18/03/21 | 0%
PRP-B-BEN-220 | Develop detailed realisation trajectory - Full Business Case Draft | 108 days | Fri 10/04/20 | Tue 08/09/20 | 0%
PRP-B-BEN-230 | Develop benefits map - Full Business Case Final | 551 days | Fri 30/04/21 | Fri 09/06/23 | 0%
PRP-B-BEN-240 | Identify benefits measures - Full Business Case Final | 215 days | Fri 30/04/21 | Thu 24/02/22 | 0%
PRP-B-BEN-250 | Detail measures and metrics - Full Business Case Final | 215 days | Thu 12/11/20 | Wed 08/09/21 | 0%
PRP-B-BEN-260 | Identify benefit owners - Full Business Case Final | 215 days | Thu 12/11/20 | Wed 08/09/21 | 0%
PRP-B-BEN-270 | Develop benefit profile agreements - Full Business Case Final | 180 days | Mon 22/02/21 | Fri 29/10/21 | 0%
PRP-B-BEN-280 | Develop methodology/narrative - Full Business Case Final | 180 days | Mon 22/02/21 | Fri 29/10/21 | 0%
PRP-B-BEN-290 | Develop plan template - Full Business Case Final | 180 days | Fri 25/12/20 | Thu 02/09/21 | 0%
PRP-B-BEN-300 | Identify major realisation milestones - Full Business Case Final | 180 days | Fri 19/03/21 | Thu 25/11/21 | 0%
PRP-B-BEN-310 | Develop detailed realisation trajectory - Full Business Case Final | 190 days | Mon 31/08/20 | Fri 21/05/21 | 0%
PRP-B-BEN-320 | Benefits working group – ongoing | 192 days | Tue 07/01/20 | Wed 30/09/20 | 0%
PRP-B-BEN-330 | Engagement with business change – ongoing | 191 days | Wed 08/01/20 | Wed 30/09/20 | 0%
PRP-B-BEN-340 | Engagement with BAU / Operations – ongoing | 0 days | Thu 01/10/20 | Thu 01/10/20 | 0%
PRP-B-EVA | Evaluation | 1652 days | Mon 02/09/19 | Tue 30/12/25 | 5%
PRP-B-EVA-010 | Programme Evaluation Strategy [PPB draft] | 64 days | Wed 01/01/20 | Mon 30/03/20 | 100%
PRP-B-EVA-020 | Programme Evaluation Strategy Full Business Case | 133 days | Mon 30/03/20 | Wed 30/09/20 | 0%
PRP-B-EVA-030 | ETTG Phase One - Conduct Interviews | 107 days | Fri 01/11/19 | Mon 30/03/20 | 100%
PRP-B-EVA-040 | ETTG Phase One - Analysis and write up | 65 days | Wed 01/04/20 | Tue 30/06/20 | 0%
PRP-B-EVA-050 | ETTG Phase Two - Conduct Interviews | 66 days | Wed 01/07/20 | Wed 30/09/20 | 0%
PRP-B-EVA-060 | ETTG Phase Two - Analysis and write up | 65 days | Thu 01/10/20 | Wed 30/12/20 | 0%
PRP-B-EVA-070 | ETTG Process evaluation | 348 days | Thu 31/12/20 | Mon 02/05/22 | 0%
PRP-B-EVA-080 | ETTG Impact evaluation | 260 days | Tue 03/05/22 | Mon 01/05/23 | 0%
PRP-B-EVA-090 | Wales OM Model Transition - Survey | 42 days | Fri 01/11/19 | Mon 30/12/19 | 100%
PRP-B-EVA-100 | Wales OM Model Transition - Conduct Interviews | 42 days | Fri 01/11/19 | Mon 30/12/19 | 100%
PRP-B-EVA-110 | Wales OM Model Transition - Analysis and write up | 0 days | Tue 31/12/19 | Tue 31/12/19 | 100%
PRP-B-EVA-120 | Wales OM Model Process - Conduct Interviews | 131 days | Wed 01/07/20 | Wed 30/12/20 | 0%
PRP-B-EVA-130 | Wales OM Model Process - Analysis and write up | 63 days | Fri 01/01/21 | Tue 30/03/21 | 0%
PRP-B-EVA-140 | Wales OM Model Process Evaluation | 412 days | Mon 02/09/19 | Tue 30/03/21 | 0%
PRP-B-EVA-150 | Phased Transition England CRCs Transition - Conduct Interviews | 88 days | Mon 01/06/20 | Wed 30/09/20 | 0%
PRP-B-EVA-160 | Phased Transition England CRCs Transition - Analysis and write up | 65 days | Thu 01/10/20 | Wed 30/12/20 | 0%
PRP-B-EVA-170 | Phased Transition England CRCs Process - Conduct Interviews | 63 days | Fri 01/01/21 | Tue 30/03/21 | 0%
PRP-B-EVA-180 | Phased Transition England CRCs Process - Analysis and write up | 65 days | Thu 01/04/21 | Wed 30/06/21 | 0%
PRP-B-EVA-190 | Unified Model Transition - Conduct Interviews | 88 days | Tue 01/06/21 | Thu 30/09/21 | 0%
PRP-B-EVA-200 | Unified Model Transition - Analysis and write up | 65 days | Fri 01/10/21 | Thu 30/12/21 | 0%
PRP-B-EVA-210 | Unified Model Process - Conduct Interviews | 63 days | Mon 03/01/22 | Wed 30/03/22 | 0%
PRP-B-EVA-220 | Unified Model Process - Analysis and write up | 65 days | Fri 01/04/22 | Thu 30/06/22 | 0%
PRP-B-EVA-230 | Unified Model Impact Evaluation | 131 days | Fri 01/07/22 | Fri 30/12/22 | 0%
PRP-B-EVA-240 | Dynamic Framework Process Evaluation | 261 days | Thu 01/07/21 | Thu 30/06/22 | 0%
PRP-B-EVA-250 | Dynamic Framework Impact Evaluation | 391 days | Fri 01/07/22 | Fri 29/12/23 | 0%
PRP-B-EVA-260 | Transition/Operational Design Process Evaluation | 261 days | Thu 01/07/21 | Thu 30/06/22 | 0%
PRP-B-EVA-270 | Transition/Operational Design Impact Evaluation | 391 days | Fri 01/07/22 | Fri 29/12/23 | 0%
PRP-B-EVA-280 | Courts and Sentencing Process Evaluation | 260 days | Mon 03/07/23 | Fri 28/06/24 | 0%
PRP-B-EVA-290 | Courts and Sentencing Impact Evaluation | 392 days | Mon 01/07/24 | Tue 30/12/25 | 0%
PRP-B-EVA-300 | Resttlement and Rehabilitation Process Evaluation | 260 days | Mon 03/07/23 | Fri 28/06/24 | 0%
PRP-B-EVA-310 | Resttlement and Rehabilitation Impact Evaluation | 392 days | Mon 01/07/24 | Tue 30/12/25 | 0%
PRP-S | Service Design | 324 days | Mon 24/02/20 | Thu 20/05/21 | 0%
PRP-S-MIL | Milestones | 108 days | Tue 21/07/20 | Fri 18/12/20 | 0%
PRP-S-MIL-010 | Final TOM 1st draft complete | 0 days | Mon 17/08/20 | Mon 17/08/20 | 0%
PRP-S-MIL-020 | PPB signs off tiering timing assumptions | 0 days | Tue 01/12/20 | Tue 01/12/20 | 0%
PRP-S-MIL-030 | NPS design input into FBC complete | 0 days | Mon 03/08/20 | Mon 03/08/20 | 0%
PRP-S-MIL-040 | Final TOM sign off (AR/JB/Ministers) | 0 days | Mon 10/08/20 | Mon 10/08/20 | 0%
PRP-S-MIL-050 | Final TOM publication on gov.uk | 0 days | Mon 30/11/20 | Mon 30/11/20 | 0%
PRP-S-MIL-060 | ROIF framework agreed | 0 days | Mon 21/12/20 | Mon 21/12/20 | 0%
PRP-S-PAB | Policy and Briefing | 0 days | Mon 24/02/20 | Mon 24/02/20 | 0%
PRP-S-TOM | Final TOM | 195 days | Tue 03/03/20 | Mon 30/11/20 | 0%
PRP-S-TOM-010 | Interim TOM published | 0 days | Tue 03/03/20 | Tue 03/03/20 | 100%
PRP-S-TOM-020 | Review of TOM EIA | 0 days | Fri 26/06/20 | Fri 26/06/20 | 0%
PRP-S-TOM-030 | Final TOM 1st draft complete | 0 days | Tue 21/07/20 | Tue 21/07/20 | 0%
PRP-S-TOM-040 | Final TOM sign off by AR/JB | 0 days | Fri 07/08/20 | Fri 07/08/20 | 0%
PRP-S-TOM-050 | Share Final TOM with HMT, Cabinet Office | 0 days | Mon 26/10/20 | Mon 26/10/20 | 0%
PRP-S-TOM-060 | Final TOM publication on gov.uk | 0 days | Mon 30/11/20 | Mon 30/11/20 | 0%
PRP-S-TOM-070 | Sentence Management / OM | 59 days | Tue 14/04/20 | Fri 03/07/20 | 0%
PRP-S-TOM-080 | DSB review sentence mgt scope and ambition paper | 0 days | Tue 05/05/20 | Tue 05/05/20 | 0%
PRP-S-TOM-090 | DSB review of Admin Hubs paper | 0 days | Tue 05/05/20 | Tue 05/05/20 | 0%
PRP-S-TOM-100 | DAB sign off of Admin Hubs model proposal (tbc) | 0 days | Thu 21/05/20 | Thu 21/05/20 | 0%
PRP-S-TOM-110 | DAB sign off of RO role | 0 days | Thu 21/05/20 | Thu 21/05/20 | 0%
PRP-S-TOM-120 | DAB decision on sentence mgt scope and ambition | 0 days | Thu 21/05/20 | Thu 21/05/20 | 0%
PRP-S-TOM-130 | Sentence mgt design testing completed | 0 days | Fri 05/06/20 | Fri 05/06/20 | 0%
PRP-S-TOM-140 | Sentence Mgt Final TOM input completed | 0 days | Fri 26/06/20 | Fri 26/06/20 | 0%
PRP-S-TOM-150 | Sentence Mgt design input into FBC completed | 0 days | Fri 24/07/20 | Fri 24/07/20 | 0%
PRP-S-CDE | Court Design | 324 days | Mon 24/02/20 | Thu 20/05/21 | 0%
PRP-S-CDE-010 | DAB court ambition approval | 11 days | Tue 31/03/20 | Tue 14/04/20 | 100%
PRP-S-CDE-020 | Court ambition paper to DA Sub board | 0 days | Tue 14/04/20 | Tue 14/04/20 | 100%
PRP-S-CDE-030 | Court Ambition paper to DAB | 0 days | Thu 23/04/20 | Thu 23/04/20 | 100%
PRP-S-CDE-040 | Defining E3 plus model | 33 days | Fri 31/07/20 | Tue 15/09/20 | 0%
PRP-S-CDE-050 | DAB approval of E3 plus design | 0 days | Fri 26/06/20 | Fri 26/06/20 | 0%
PRP-S-CDE-060 | E3 plus model costings approved by PPB | 0 days | Fri 26/06/20 | Fri 26/06/20 | 0%
PRP-S-CDE-070 | Evaluate results of Wales PSI pilot | 0 days | Tue 15/09/20 | Tue 15/09/20 | 0%
PRP-S-CDE-080 | Court input to FBC complete | 0 days | Fri 26/06/20 | Fri 26/06/20 | 0%
PRP-S-CDE-090 | PSR pilot design | 0 days | Thu 23/04/20 | Thu 23/04/20 | 0%
PRP-S-CDE-100 | PSR pilot started | 0 days | Mon 01/06/20 | Mon 01/06/20 | 0%
PRP-S-CDE-110 | PSR pilot complete | 0 days | Mon 31/08/20 | Mon 31/08/20 | 0%
PRP-S-CDE-120 | PSR full scale up complete | 0 days | Tue 30/03/21 | Tue 30/03/21 | 0%
PRP-S-CDE-130 | PSR full scale pilot paper approved | 0 days | Fri 30/04/21 | Fri 30/04/21 | 0%
PRP-S-CDE-120 | Victim Services | 102 days | Thu 12/03/20 | Fri 31/07/20 | 0%
PRP-S-CDE-130 | OBC Victims cost input completed | 0 days | Thu 12/03/20 | Thu 12/03/20 | 100%
PRP-S-CDE-140 | DSB review of Victim contact scheme options paper | 0 days | Tue 05/05/20 | Tue 05/05/20 | 0%
PRP-S-CDE-150 | DAB decision of Victim contact scheme options | 0 days | Thu 04/06/20 | Thu 04/06/20 | 0%
PRP-S-CDE-160 | Victim Services Final TOM input completed | 0 days | Tue 23/06/20 | Tue 23/06/20 | 0%
PRP-S-CDE-170 | Agree FBC inputs | 0 days | Fri 31/07/20 | Fri 31/07/20 | 0%
PRP-S-CDE-180 | Tiering | 174 days | Tue 31/03/20 | Fri 27/11/20 | 0%
PRP-S-CDE-190 | Findings from Interim Tiering Model for Wales | 0 days | Tue 31/03/20 | Tue 31/03/20 | 100%
PRP-S-CDE-200 | Review OMIC tiering model in parallel to new tiering design. | 0 days | Fri 10/04/20 | Fri 10/04/20 | 100%
PRP-S-CDE-210 | Proposal on Unified Model Tiering to DAB | 21 days | Fri 31/07/20 | Mon 31/08/20 | 0%
PRP-S-CDE-220 | Results of Women's Strategy Pilot | 0 days | Fri 31/07/20 | Fri 31/07/20 | 0%
PRP-S-CDE-230 | Impact assessment for Unified Model Tiering with caseload volume forecasting | 0 days | Fri 31/07/20 | Fri 31/07/20 | 0%
PRP-S-CDE-240 | Assess impact of design change on workload | 0 days | Mon 31/08/20 | Mon 31/08/20 | 0%
PRP-S-CDE-250 | Resources assigned to Tiering Model Based on Design Changes for whole system | 0 days | Mon 02/11/20 | Mon 02/11/20 | 0%
PRP-S-CDE-260 | PPB signs off timing assumptions for each tier (links to the role boundaries for POs / PSOs) | 0 days | Mon 30/11/20 | Mon 30/11/20 | 0%
PRP-S-CDE-270 | National Standards and PIs | 175 days | Fri 18/09/20 | Fri 21/05/21 | 0%
PRP-S-CDE-280 | Update the OM role policies and procedures based on service design | 0 days | Mon 28/06/21 | Mon 28/06/21 | 0%
PRP-S-CDE-290 | Staff consultation on changes | 0 days | Mon 28/06/21 | Mon 28/06/21 | 0%
PRP-S-CDE-300 | Workshops on changes | 0 days | Mon 28/06/21 | Mon 28/06/21 | 0%
PRP-S-CDE-310 | Changes to Policies, procedures and guidance for new OM roles | 0 days | Mon 28/06/21 | Mon 28/06/21 | 0%
PRP-S-CDE-320 | ROIF / SOF | 274 days | Fri 13/03/20 | Thu 01/04/21 | 0%
PRP-S-CDE-330 | Funding for SOF agreed | 0 days | Fri 13/03/20 | Fri 13/03/20 | 100%
PRP-S-CDE-340 | SOF Pilots launched | 0 days | Fri 05/06/20 | Fri 05/06/20 | 0%
PRP-S-CDE-350 | ROIF TOM input completed | 0 days | Fri 26/06/20 | Fri 26/06/20 | 0%
PRP-S-CDE-360 | Develop outline ROIF operating model | 0 days | Fri 24/07/20 | Fri 24/07/20 | 0%
PRP-S-CDE-370 | ROIF FBC input completed | 0 days | Fri 24/07/20 | Fri 24/07/20 | 0%
PRP-S-CDE-380 | ROIF detailed framework model developed | 0 days | Mon 30/11/20 | Mon 30/11/20 | 0%
PRP-S-CDE-390 | ROIF framework agreed | 0 days | Fri 18/12/20 | Fri 18/12/20 | 0%
PRP-S-CDE-400 | ROIF go-live | 0 days | Thu 01/04/21 | Thu 01/04/21 | 0%
PRP-S-CDE-410 | Service User Involvement | 179 days | Mon 24/02/20 | Thu 29/10/20 | 0%
PRP-S-CDE-420 | SUI paper presented and agreed at NPS PDD Weekly Touch Base Board | 0 days | Mon 24/02/20 | Mon 24/02/20 | 100%
PRP-S-CDE-430 | Fuller SUI Options paper drafted | 0 days | Wed 20/05/20 | Wed 20/05/20 | 0%
PRP-S-CDE-440 | SUI Options paper presented to the Design Sub Board | 0 days | Mon 01/06/20 | Mon 01/06/20 | 0%
PRP-S-CDE-450 | SUI Options presented to the DAB | 0 days | Tue 30/06/20 | Tue 30/06/20 | 0%
PRP-S-CDE-460 | SUI Model fully developed | 0 days | Fri 30/10/20 | Fri 30/10/20 | 0%
PRP-R | Resettlement | 202 days | Fri 13/03/20 | Sun 20/12/20 | 6%
PRP-R-MIL | Milestones | 191 days | Fri 27/03/20 | Sun 20/12/20 | 0%
PRP-R-MIL-010 | Unified Model OMiC scoped | 0 days | Mon 30/03/20 | Mon 30/03/20 | 100%
PRP-R-MIL-020 | OMIC processes agreed for Day 1 | 0 days | Mon 21/12/20 | Mon 21/12/20 | 0%
PRP-R-MIL-030 | Short sentence pilot complete | 0 days | Fri 25/09/20 | Fri 25/09/20 | 0%
PRP-R-MIL-040 | Resettlement design input into FBC completed | 0 days | Fri 31/07/20 | Fri 31/07/20 | 0%
PRP-R-MIL-050 | Resettlement Final TOM input completed | 0 days | Fri 26/06/20 | Fri 26/06/20 | 0%
PRP-R-OMI | OMIC | 202 days | Fri 13/03/20 | Sun 20/12/20 | 8%
PRP-R-OMI-010 | Additional activities TBD post plan agreement | 0 days | Fri 17/04/20 | Fri 17/04/20 | 100%
PRP-R-OMI-020 | Articulate regional flex for resettlement processes | 0 days | Fri 29/05/20 | Fri 29/05/20 | 0%
PRP-R-OMI-030 | OMIC processes agreed for Day 1 | 0 days | Mon 21/12/20 | Mon 21/12/20 | 0%
PRP-R-OMI-040 | Unified Model OMiC scoped | 11 days | Fri 13/03/20 | Fri 27/03/20 | 100%
PRP-R-OMI-050 | High level action plan with OMiC team agreed | 4 days | Tue 14/04/20 | Fri 17/04/20 | 100%
PRP-R-OMI-060 | Information sharing protocols between prisons and probation defined | 32 days | Tue 14/04/20 | Wed 27/05/20 | 0%
PRP-R-OMI-070 | Resettlement pack definition | 108 days | Tue 14/04/20 | Thu 10/09/20 | 0%
PRP-R-OMI-080 | BCST1 Assessment scope of work agreed (w/Reducing Reoffending) | 45 days | Tue 14/04/20 | Mon 15/06/20 | 0%
PRP-R-SSM | Short Sentence Model | 111 days | Thu 23/04/20 | Fri 25/09/20 | 0%
PRP-R-SSM-010 | Short sentence pilot DAB decision | 0 days | Thu 23/04/20 | Thu 23/04/20 | 0%
PRP-R-SSM-020 | Short sentence pilot kick off | 0 days | Mon 01/06/20 | Mon 01/06/20 | 0%
PRP-R-SSM-030 | Short sentence pilot complete | 0 days | Fri 25/09/20 | Fri 25/09/20 | 0%
PRP-R-TOM | TOM/OC/FBC input | 89 days | Fri 27/03/20 | Thu 30/07/20 | 0%
PRP-R-TOM-010 | Resettlement Final TOM input completed | 0 days | Fri 26/06/20 | Fri 26/06/20 | 0%
PRP-R-TOM-020 | Resettlement design input into FBC completed | 0 days | Fri 31/07/20 | Fri 31/07/20 | 0%
PRP-R-TOM-030 | Refined cost options for OBC2 drafted | 0 days | Mon 30/03/20 | Mon 30/03/20 | 100%
PRP-R-TOM-040 | Cost options paper refined for PPB | 0 days | Mon 13/04/20 | Mon 13/04/20 | 100%
PRP-R-TOM-050 | Collate resettlement activity into final model | 44 days | Tue 14/04/20 | Fri 12/06/20 | 0%
PRP-R-TRA | Transition | 30 days | Fri 20/03/20 | Thu 30/04/20 | 0%
PRP-R-TRA-010 | DAB approval of Resettlement options for plugging the IMS gap | 0 days | Fri 27/03/20 | Fri 27/03/20 | 100%
PRP-R-TRA-020 | Resettlement options for plugging IMS gap to include within wider IMS gap analysis | 0 days | Fri 20/03/20 | Fri 20/03/20 | 100%
PRP-R-TRA-030 | Contribute to DF evaluation questions for resettlement | 13 days | Tue 14/04/20 | Thu 30/04/20 | 0%
PRP-C | Competed Services | 641 days | Mon 14/01/19 | Mon 28/06/21 | 15%
PRP-C-MIL | Milestones | 313 days | Wed 15/04/20 | Fri 25/06/21 | 0%
PRP-C-MIL-010 | PDP - ITT Evaluation and Moderation complete | 0 days | Mon 25/05/20 | Mon 25/05/20 | 0%
PRP-C-MIL-020 | BAFO Evaluation and Moderation Complete | 0 days | Mon 05/10/20 | Mon 05/10/20 | 0%
PRP-C-MIL-030 | PDP Contract Award | 0 days | Wed 25/11/20 | Wed 25/11/20 | 0%
PRP-C-MIL-040 | PDP - Go-Live | 0 days | Mon 28/06/21 | Mon 28/06/21 | 0%
PRP-C-MIL-050 | Finalise Day 1 national specifications | 0 days | Thu 16/04/20 | Thu 16/04/20 | 100%
PRP-C-MIL-060 | Framework Agreement Finalised (Develop documentation and schedules) | 0 days | Fri 01/05/20 | Fri 01/05/20 | 0%
PRP-C-MIL-070 | Procurement Documents Finalised | 0 days | Thu 30/04/20 | Thu 30/04/20 | 0%
PRP-C-MIL-080 | Legal review of Framework ITP pack for publication | 0 days | Fri 15/05/20 | Fri 15/05/20 | 0%
PRP-C-MIL-090 | DF Framework Launch | 0 days | Mon 18/05/20 | Mon 18/05/20 | 0%
PRP-C-MIL-100 | Call-Off Competitions Starts | 0 days | Mon 06/07/20 | Mon 06/07/20 | 0%
PRP-C-MIL-110 | DF Contract Awards complete | 0 days | Wed 23/12/20 | Wed 23/12/20 | 0%
PRP-C-MIL-120 | DF Go Live | 0 days | Fri 25/06/21 | Fri 25/06/21 | 0%
PRP-C-PDP | PDP | 372 days | Fri 24/01/20 | Mon 28/06/21 | 5%
PRP-C-PDP-010 | PDP - SQ Evaluation and moderation complete | 0 days | Fri 24/01/20 | Fri 24/01/20 | 100%
PRP-C-PDP-020 | PDP - Debrief letters issued to successful and unsuccessful SQ responders | 0 days | Mon 27/01/20 | Mon 27/01/20 | 100%
PRP-C-PDP-030 | PDP - ITT Issued to successful SQ respondents | 9 days | Tue 28/01/20 | Fri 07/02/20 | 100%
PRP-C-PDP-040 | PDP - ITT Evaluation team ready | 6 days | Tue 03/03/20 | Tue 10/03/20 | 100%
PRP-C-PDP-050 | Deadline for bidder clarifications questions for PDP ITT | 0 days | Fri 20/03/20 | Fri 20/03/20 | 100%
PRP-C-PDP-060 | Deadline for receipt of Bidders Initial Tenders for PDP | 0 days | Fri 27/03/20 | Fri 27/03/20 | 100%
PRP-C-PDP-070 | PDP - ITT Evaluation and Moderation | 40 days | Mon 30/03/20 | Fri 22/05/20 | 0%
PRP-C-PDP-080 | PDP - ITT Evaluation and Moderation complete | 0 days | Mon 25/05/20 | Mon 25/05/20 | 0%
PRP-C-PDP-090 | PDP - ITT Debrief letters issued to responders | 5 days | Tue 26/05/20 | Mon 01/06/20 | 0%
PRP-C-PDP-100 | PDP - Face to Face meetings with successful ITT responders | 25 days | Tue 02/06/20 | Mon 06/07/20 | 0%
PRP-C-PDP-110 | BAFO stage | 20 days | Mon 13/07/20 | Fri 07/08/20 | 0%
PRP-C-PDP-120 | The Authority issues invitation to submit BAFO | 0 days | Mon 13/07/20 | Mon 13/07/20 | 0%
PRP-C-PDP-130 | Deadline for Bidders to submit clarification questions on the BAFO | 0 days | Fri 07/08/20 | Fri 07/08/20 | 0%
PRP-C-PDP-140 | Deadline for receipt of Bidders BAFO's submission | 0 days | Fri 21/08/20 | Fri 21/08/20 | 0%
PRP-C-PDP-150 | BAFO Evaluation and Moderation | 30 days | Mon 24/08/20 | Fri 02/10/20 | 0%
PRP-C-PDP-160 | BAFO Evaluation and Moderation Complete | 0 days | Mon 05/10/20 | Mon 05/10/20 | 0%
PRP-C-PDP-170 | Successful BAFO bidders notified | 5 days | Tue 06/10/20 | Mon 12/10/20 | 0%
PRP-C-PDP-180 | Standstill period | 7 days | Tue 13/10/20 | Wed 21/10/20 | 0%
PRP-C-PDP-190 | PDP Contract Award | 0 days | Wed 25/11/20 | Wed 25/11/20 | 0%
PRP-C-PDP-200 | FBC/PDP Contingency period | 20 days | Thu 26/11/20 | Wed 23/12/20 | 0%
PRP-C-PDP-210 | Mobilisation period | 132 days | Thu 24/12/20 | Fri 25/06/21 | 0%
PRP-C-PDP-220 | PDP - Go-Live | 0 days | Mon 28/06/21 | Mon 28/06/21 | 0%
PRP-C-DNF | Dynamic Framework | 454 days | Tue 01/10/19 | Fri 25/06/21 | 30%
PRP-C-DNF-010 | Categories specifications complete | 0 days | Fri 31/01/20 | Fri 31/01/20 | 100%
PRP-C-DNF-020 | First draft of DF categories specifications complete | 33 days | Fri 31/01/20 | Tue 17/03/20 | 100%
PRP-C-DNF-030 | Gap analysis work complete | 21 days | Fri 07/02/20 | Fri 06/03/20 | 100%
PRP-C-DNF-040 | First draft Gap Analysis template and guidance shared with NPS PDDs | 25 days | Mon 06/01/20 | Fri 07/02/20 | 100%
PRP-C-DNF-050 | Gap analysis returns from PDDs | 0 days | Fri 06/03/20 | Fri 06/03/20 | 100%
PRP-C-DNF-060 | Finalise Day 1 national specifications | 19 days | Sun 22/03/20 | Wed 15/04/20 | 100%
PRP-C-DNF-070 | Design Authority Approval of Day 1 Services | 0 days | Mon 23/03/20 | Mon 23/03/20 | 100%
PRP-C-DNF-080 | Workforce staff and pensions obligations requirements confirmed | 70 days | Mon 06/01/20 | Fri 10/04/20 | 100%
PRP-C-DNF-090 | Finalise contract values | 79 days | Mon 13/01/20 | Thu 30/04/20 | 0%
PRP-C-DNF-100 | ICT position (IPR, Information Security Requirements) confirmed | 84 days | Mon 06/01/20 | Thu 30/04/20 | 0%
PRP-C-DNF-110 | DF Sourcing system SQ build | 53 days | Mon 03/02/20 | Wed 15/04/20 | 100%
PRP-C-DNF-120 | Write Boiler Plate Regional Specifications | 18 days | Mon 23/03/20 | Wed 15/04/20 | 100%
PRP-C-DNF-130 | Develop performance measure regime (KPIs/SLAs/Service credits) | 52 days | Mon 03/02/20 | Tue 14/04/20 | 100%
PRP-C-DNF-140 | Draft Performance Framework agreed | 0 days | Wed 15/04/20 | Wed 15/04/20 | 100%
PRP-C-DNF-150 | Market warming events | 23 days | Thu 16/04/20 | Mon 18/05/20 | 100%
PRP-C-DNF-160 | Framework Agreement Finalised (Develop documentation and schedules) | 131 days | Thu 31/10/19 | Thu 30/04/20 | 0%
PRP-C-DNF-170 | Develop Framework Agreement Evaluation Methodology | 28 days | Tue 24/03/20 | Thu 30/04/20 | 0%
PRP-C-DNF-180 | Develop Call-Off Contract Evaluation Methodology | 28 days | Tue 24/03/20 | Thu 30/04/20 | 0%
PRP-C-DNF-190 | Draft OJEU Contract notice | 0 days | Thu 30/04/20 | Thu 30/04/20 | 0%
PRP-C-DNF-200 | Write ITT form | 0 days | Thu 30/04/20 | Thu 30/04/20 | 0%
PRP-C-DNF-210 | Write Framework competition guidance | 0 days | Thu 30/04/20 | Thu 30/04/20 | 0%
PRP-C-DNF-220 | Procurement Documents Finalised | 0 days | Thu 16/04/20 | Thu 16/04/20 | 100%
PRP-C-DNF-230 | Develop payment mechanism | 65 days | Fri 31/01/20 | Thu 30/04/20 | 0%
PRP-C-DNF-250 | Programme Board approval of draft call-off procurement plan | 0 days | Fri 15/05/20 | Fri 15/05/20 | 0%
PRP-C-DNF-260 | Final Ministerial review | 0 days | Mon 18/05/20 | Mon 18/05/20 | 0%
PRP-C-DNF-270 | Legal review and clearance of Framework ITP pack for publication | 22 days | Thu 16/04/20 | Fri 15/05/20 | 0%
| Framework Evaluators appointed and Trained | 0 days | Tue 14/04/20 | Tue 14/04/20 | 100%
PRP-C-DNF-290 | Develop technical evaluation template | 33 days | Wed 01/01/20 | Fri 14/02/20 | 100%
PRP-C-DNF-320 | DF Launch Go/No Go Decision | 0 days | Fri 15/05/20 | Fri 15/05/20 | 0%
PRP-C-DNF-330 | DF Framework Launch | 0 days | Mon 18/05/20 | Mon 18/05/20 | 0%
PRP-C-DNF-340 | DF SQ Evaluation | 79 days | Wed 20/05/20 | Sat 05/09/20 | 0%
PRP-C-DNF-350 | DF SQ Evaluation - 1st wave | 30 days | Wed 20/05/20 | Tue 30/06/20 | 0%
PRP-C-DNF-360 | DF SQ Evaluation - 2nd wave | 22 days | Fri 03/07/20 | Mon 03/08/20 | 0%
PRP-C-DNF-370 | Appoint Call-Off Competition Evaluators | 32 days | Wed 20/05/20 | Thu 02/07/20 | 0%
PRP-C-DNF-380 | DF SQ Evaluation - 3rd wave | 23 days | Wed 05/08/20 | Fri 04/09/20 | 0%
PRP-C-DNF-390 | Data room ready and open | 0 days | Fri 03/07/20 | Fri 03/07/20 | 0%
PRP-C-DNF-400 | Call-Off Competitions Starts | 0 days | Mon 06/07/20 | Mon 06/07/20 | 0%
PRP-C-DNF-410 | Call-Off Competition Evaluators Training | 28 days | Wed 08/07/20 | Fri 14/08/20 | 0%
PRP-C-DNF-420 | Call-Off Competition Invitation to Tender - 1st, 2nd and 3rd waves | 104 days | Mon 06/07/20 | Thu 26/11/20 | 0%
PRP-C-DNF-430 | Call-Off Evaluation - 1st, 2nd and 3rd waves | 75 days | Mon 07/09/20 | Fri 18/12/20 | 0%
PRP-C-DNF-440 | DF Contract Awards complete | 0 days | Wed 23/12/20 | Wed 23/12/20 | 0%
PRP-C-DNF-450 | Mobisation period | 130 days | Mon 28/12/20 | Fri 25/06/21 | 0%
PRP-C-DNF-460 | DF Go Live | 0 days | Fri 25/06/21 | Fri 25/06/21 | 0%
PRP-C-ECM | Exit and Contract Mobilisation | 640 days | Mon 14/01/19 | Fri 25/06/21 | 3%
PRP-C-ECM-010 | Exit Plan 1st update | 30 days | Mon 14/01/19 | Fri 22/02/19 | 100%
PRP-C-ECM-020 | Transition meetings with regions | 440 days | Mon 21/10/19 | Fri 25/06/21 | 0%
PRP-C-ECM-030 | Regular Exit Plan updates | 260 days | Tue 14/01/20 | Mon 11/01/21 | 0%
PRP-C-ECM-040 | Interventions Services Transfer Activities | 150 days | Mon 30/11/20 | Fri 25/06/21 | 0%
PRP-C-ECM-050 | Data transfer/destroy | 119 days | Tue 12/01/21 | Fri 25/06/21 | 0%
PRP-C-ECM-060 | Contract expired period & exit date | 84 days | Tue 02/03/21 | Fri 25/06/21 | 0%
PRP-C-ECM-070 | Regional Structures in place for Contract Management and BAU | 0 days | Fri 25/06/21 | Fri 25/06/21 | 0%
PRP-E | Estates | 478 days | Mon 02/09/19 | Wed 30/06/21 | 48%
PRP-E-MIL | Milestones | 323 days | Tue 31/03/20 | Thu 24/06/21 | 0%
PRP-E-MIL-10 | Probation Reform Programme board signs off national strategy | 0 days | Fri 17/04/20 | Fri 17/04/20 | 99%
PRP-E-MIL-20 | Regional Plans - High Level Activities Confirmed | 0 days | Mon 04/05/20 | Mon 04/05/20 | 0%
PRP-E-MIL-30 | Fully scoped plans for all buildings | 0 days | Tue 30/06/20 | Tue 30/06/20 | 0%
PRP-E-MIL-40 | Site Surveys Completed | 0 days | Wed 30/09/20 | Wed 30/09/20 | 0%
PRP-E-MIL-50 | Regional Director Bases operational | 0 days | Tue 31/03/20 | Tue 31/03/20 | 100%
PRP-E-MIL-60 | Year 2 feasibility studies complete | 0 days | Thu 31/12/20 | Thu 31/12/20 | 0%
PRP-E-MIL-70 | Facilities Management plan for service for Day 1 in place | 0 days | Mon 29/03/21 | Mon 29/03/21 | 100%
PRP-E-MIL-80 | Day 1 - Properties Completed | 0 days | Fri 25/06/21 | Fri 25/06/21 | 0%
PRP-E-STR | Estates Strategy | 174 days | Mon 02/09/19 | Thu 30/04/20 | 98%
PRP-E-STR-10 | HMPPS Confirm NPS first Estates strategy reviewed | 16 days | Mon 02/09/19 | Mon 23/09/19 | 100%
PRP-E-STR-20 | Initial Site Analysis | 5 days | Tue 24/09/19 | Mon 30/09/19 | 100%
PRP-E-STR-30 | Initial Site Surveys | 0 days | Tue 01/10/19 | Tue 01/10/19 | 100%
PRP-E-STR-40 | 2nd phase condition surveys | 56 days | Wed 02/10/19 | Wed 18/12/19 | 100%
PRP-E-STR-50 | NPS Strategy 1st draft developed | 30 days | Mon 02/09/19 | Fri 11/10/19 | 100%
PRP-E-STR-60 | Design Guide 1st Draft developed | 73 days | Mon 02/09/19 | Wed 11/12/19 | 100%
PRP-E-STR-70 | Blueprint for the modern probation estate design guide completed | 160 days | Mon 02/09/19 | Fri 10/04/20 | 100%
PRP-E-STR-80 | DDAT, People and Estates Interface created | 45 days | Thu 12/12/19 | Wed 12/02/20 | 100%
PRP-E-STR-90 | Regional sub-group structure established | 10 days | Tue 01/10/19 | Mon 14/10/19 | 100%
PRP-E-STR-100 | Sign off strategy at regional boards | 121 days | Tue 15/10/19 | Tue 31/03/20 | 100%
PRP-E-STR-110 | National estates strategy approved by Estates Programme Board | 0 days | Wed 01/04/20 | Wed 01/04/20 | 100%
PRP-E-STR-120 | Probation Reform Programme board signs off national strategy | 0 days | Thu 16/04/20 | Thu 16/04/20 | 100%
PRP-E-STR-130 | Budget authority for proposed expenditure provided to MoJ Estates | 11 days | Thu 16/04/20 | Thu 30/04/20 | 0%
PRP-E-PLA | Planning | 344 days | Fri 06/03/20 | Wed 30/06/21 | 4%
PRP-E-PLA-10 | Landlord Engagement | 0 days | Wed 18/03/20 | Wed 18/03/20 | 100%
PRP-E-PLA-20 | Hold workshop to discuss approach to engaging landlords | 0 days | Wed 18/03/20 | Wed 18/03/20 | 100%
PRP-E-PLA-30 | Finalise and confirm strategy for landlord engagement | 284 days | Fri 29/05/20 | Wed 30/06/21 | 0%
PRP-E-PLA-40 | Write to CRCs to inform that we will be speaking to landloard re leases | 0 days | Fri 29/05/20 | Fri 29/05/20 | 0%
PRP-E-PLA-50 | Write to Treasury & Cabinet Office for PTS & LMER for approval | 0 days | Tue 30/06/20 | Tue 30/06/20 | 0%
PRP-E-PLA-60 | Transferring and Acquiring new buildings as required by the strategy | 0 days | Wed 30/06/21 | Wed 30/06/21 | 0%
PRP-E-PLA-70 | Regional Plans - High Level Activities Confirmed | 63 days | Fri 06/03/20 | Tue 02/06/20 | 35%
PRP-E-PLA-80 | Update regional strategies in light of national funding profile | 11 days | Fri 06/03/20 | Fri 20/03/20 | 100%
PRP-E-PLA-90 | Draw up plans for delivery of SW regional strategy as basis for planing discussions | 11 days | Mon 23/03/20 | Mon 06/04/20 | 100%
PRP-E-PLA-100 | Workshop to review SW delivery plan and agree wider application of planning assumptions within | 0 days | Tue 07/04/20 | Tue 07/04/20 | 100%
PRP-E-PLA-110 | Finalise SW high evel delivery plan as model for remaining regions | 19 days | Tue 07/04/20 | Fri 01/05/20 | 0%
PRP-E-PLA-120 | Draw up each region's high level Day 1 delivery plan | 22 days | Mon 04/05/20 | Tue 02/06/20 | 0%
PRP-E-PLA-130 | Confirm high level activities required for Day 1 of unified model | 0 days | Wed 03/06/20 | Wed 03/06/20 | 0%
PRP-E-PLA-140 | Fully scoped plans for all buildings | 21 days | Mon 01/06/20 | Mon 29/06/20 | 0%
PRP-E-PLA-150 | Draw up detailed Day 1 delivery plans for each region | 21 days | Mon 01/06/20 | Mon 29/06/20 | 0%
PRP-E-PLA-160 | Detailed Day 1 delivery plan approval in each region | 16 days | Mon 08/06/20 | Mon 29/06/20 | 0%
PRP-E-PLA-170 | Confirm detailed activities required for Day 1 of unified model | 0 days | Mon 29/06/20 | Mon 29/06/20 | 0%
PRP-E-PLA-180 | Final approval by Operational Readiness Board | 0 days | Tue 30/06/20 | Tue 30/06/20 | 0%
PRP-E-PLA-190 | Site Surveys Completed | 131 days | Wed 01/04/20 | Wed 30/09/20 | 0%
PRP-E-PLA-200 | IT surveys required for Day 1 properties complete | 88 days | Wed 01/04/20 | Fri 31/07/20 | 0%
PRP-E-PLA-210 | Security surveys required for Day 1 properties complete | 88 days | Wed 01/04/20 | Fri 31/07/20 | 0%
PRP-E-PLA-220 | Health & Safety surveys required for Day 1 properties complete | 131 days | Wed 01/04/20 | Wed 30/09/20 | 0%
PRP-E-PLA-230 | FM surveys required for Day 1 properties complete | 131 days | Wed 01/04/20 | Wed 30/09/20 | 0%
PRP-E-D1P | Day 1 Properties (June 2021) | 349 days | Mon 24/02/20 | Thu 24/06/21 | 13%
PRP-E-D1P-10 | Regional Director Bases operational | 349 days | Mon 24/02/20 | Thu 24/06/21 | 13%
PRP-E-D1P-20 | Establish minimum requirements for new RD bases to be operational | 7 days | Mon 24/02/20 | Tue 03/03/20 | 100%
PRP-E-D1P-30 | Secure funding to obtain and install furniture | 2 days | Wed 04/03/20 | Thu 05/03/20 | 100%
PRP-E-D1P-40 | Place furniture orders | 2 days | Tue 14/04/20 | Wed 15/04/20 | 100%
PRP-E-D1P-50 | Installation of furniture | 6 days | Wed 01/07/20 | Wed 08/07/20 | 0%
PRP-E-D1P-60 | Facilities Management plan for service for Day 1 in place | 0 days | Mon 29/03/21 | Mon 29/03/21 | 0%
PRP-E-D1P-70 | Day 1 - Property Refurbishments | 0 days | Fri 25/06/21 | Fri 25/06/21 | 0%
PRP-E-D1P-80 | Day 1 - Property Acquisitions | 0 days | Fri 25/06/21 | Fri 25/06/21 | 0%
PRP-E-D1P-90 | Day 1 - Property Transfers | 0 days | Fri 25/06/21 | Fri 25/06/21 | 0%
PRP-E-D1P-100 | Facilities Management contracts operational | 0 days | Fri 25/06/21 | Fri 25/06/21 | 0%
PRP-E-D1P-110 | Year 2 Properties | 0 days | Tue 14/04/20 | Tue 14/04/20 | 100%
PRP-E-D1P-120 | Year 2 feasibility studies complete | 65 days | Thu 31/12/20 | Wed 31/03/21 | 0%
PRP-E-D1P-130 | Day 1 Handover to RDDs and BSCs | 0 days | Tue 14/04/20 | Tue 14/04/20 | 100%
PRP-P | People | 585 days | Fri 03/01/20 | Thu 31/03/22 | 2%
PRP-P-MIL | Milestones | 320 days | Tue 14/04/20 | Mon 05/07/21 | 0%
PRP-P-MIL-010 | Role assignment ends | 0 days | Wed 01/07/20 | Wed 01/07/20 | 0%
PRP-P-MIL-020 | Placemnet: Confirmation of final matching outcome | 0 days | Tue 18/08/20 | Tue 18/08/20 | 0%
PRP-P-MIL-030 | Mobilisation: Outcome of staff ballot | 0 days | Wed 01/07/20 | Wed 01/07/20 | 0%
PRP-P-MIL-040 | TU Consultation: Secretary of state to sign staff transfer agreement | 0 days | Mon 05/07/21 | Mon 05/07/21 | 0%
PRP-P-MIL-050 | Mobilisation: Formal letters sent to staff re. transfer | 0 days | Mon 31/05/21 | Mon 31/05/21 | 0%
PRP-P-MIL-060 | Workforce data: CRC complete role assignment template | 0 days | Mon 21/06/21 | Mon 21/06/21 | 0%
PRP-P-MIL-070 | Payroll: testing begins | 0 days | Mon 01/03/21 | Mon 01/03/21 | 0%
PRP-P-MIL-080 | Outcome of NPS staff ballot | 0 days | Thu 30/04/20 | Thu 30/04/20 | 0%
PRP-P-MIL-090 | Assignment process data requested | 0 days | Thu 30/04/20 | Thu 30/04/20 | 0%
PRP-P-MIL-100 | Data migration: File transfer | 0 days | Sat 01/05/21 | Sat 01/05/21 | 0%
PRP-P-MIL-110 | Commence Role Assignment with CRCs | 0 days | Fri 01/05/20 | Fri 01/05/20 | 0%
PRP-P-MIL-120 | Assignment process data received | 0 days | Mon 01/06/20 | Mon 01/06/20 | 0%
PRP-P-MIL-130 | Recruitment of all SMT Roles Complete | 0 days | Mon 08/06/20 | Mon 08/06/20 | 0%
PRP-P-MIL-140 | Complete Role Assignment with CRCs | 0 days | Fri 17/07/20 | Fri 17/07/20 | 0%
PRP-P-MIL-150 | RFCs: Submit RFCs | 0 days | Tue 14/07/20 | Tue 14/07/20 | 0%
PRP-P-MIL-160 | Recruitment: HO roles filled | 0 days | Tue 29/09/20 | Tue 29/09/20 | 0%
PRP-P-MIL-170 | Vetting: commission SSCL to start basic vetting | 0 days | Fri 02/10/20 | Fri 02/10/20 | 0%
PRP-P-MIL-180 | Vetting Process | 0 days | Mon 31/05/21 | Mon 31/05/21 | 0%
PRP-P-MIL-190 | Vetting: Completed | 0 days | Tue 03/08/21 | Tue 03/08/21 | 0%
PRP-P-MIL-200 | Divisions to Regions: PDUs become fully active / Go-Live | 0 days | Fri 02/04/21 | Fri 02/04/21 | 0%
PRP-P-MIL-210 | Divisions to Regions: Letters to staff confirming location changes | 0 days | Tue 06/10/20 | Tue 06/10/20 | 0%
PRP-P-MIL-220 | Inductions: SLT Induction sessions completed | 0 days | Tue 08/12/20 | Tue 08/12/20 | 0%
PRP-P-MIL-230 | Inductions: CRC Staff inductions (Delivery Complete) | 0 days | Tue 01/06/21 | Tue 01/06/21 | 0%
PRP-P-MIL-240 | LND: Comission development of course content and convert into eLearning modules | 0 days | Wed 02/09/20 | Wed 02/09/20 | 0%
PRP-P-MIL-250 | LND: Finalise modules of mandatory training for all staff groups | 0 days | Mon 31/05/21 | Mon 31/05/21 | 0%
PRP-P-MIL-260 | Induction events completed | 0 days | Tue 15/06/21 | Tue 15/06/21 | 0%
PRP-P-MIL-270 | SOP transition complete and payroll live | 0 days | Fri 25/06/21 | Fri 25/06/21 | 0%
PRP-P-DTA | Design & Transfer Approach | 385 days | Mon 10/02/20 | Fri 30/07/21 | 5%
PRP-P-DTA-010 | Role Assignment | 132 days | Mon 10/02/20 | Tue 11/08/20 | 40%
PRP-P-DTA-020 | CRCs decide whether to agree to activity | 20 days | Mon 10/02/20 | Fri 06/03/20 | 100%
PRP-P-DTA-030 | Go/no go following Jim's comms #1 | 0 days | Mon 09/03/20 | Mon 09/03/20 | 100%
PRP-P-DTA-040 | CRCs commence Role Assignment | 0 days | Fri 01/05/20 | Fri 01/05/20 | 0%
PRP-P-DTA-050 | Role assignment ends | 0 days | Tue 30/06/20 | Tue 30/06/20 | 0%
PRP-P-DTA-060 | Formal challenges to be sent in writing with deadline | 10 days | Wed 01/07/20 | Tue 14/07/20 | 0%
PRP-P-DTA-070 | Face to face challenge meetings, if required | 20 days | Wed 15/07/20 | Tue 11/08/20 | 0%
PRP-P-DTA-080 | Placement | 221 days | Mon 30/03/20 | Sun 31/01/21 | 0%
PRP-P-DTA-090 | Complete products for placement | 0 days | Mon 30/03/20 | Mon 30/03/20 | 100%
PRP-P-DTA-100 | Complete mapping and matching desktop exercise using JDs (national) for ACO grades | 5 days | Mon 15/06/20 | Fri 19/06/20 | 0%
PRP-P-DTA-110 | CRC 1:1s for matching and mapping (gather role info) and share with NPS | 5 days | Mon 22/06/20 | Fri 26/06/20 | 0%
PRP-P-DTA-120 | Confirmation of outcome and right to appeal letter | 5 days | Mon 06/07/20 | Fri 10/07/20 | 0%
PRP-P-DTA-130 | Appeal panels held and outcomes sent | 0 days | Fri 14/08/20 | Fri 14/08/20 | 0%
PRP-P-DTA-140 | Confirmation comms - final matching outcome letter and data report by division for CRC to use for preference exercise 1:1s | 0 days | Mon 17/08/20 | Mon 17/08/20 | 0%
PRP-P-DTA-150 | Undersupply/Exact Fit: Letter preference confirmation via CRCs | 5 days | Mon 14/09/20 | Fri 18/09/20 | 0%
PRP-P-DTA-160 | Undersupply/Exact Fit: final placement letters | 0 days | Mon 26/10/20 | Mon 26/10/20 | 0%
PRP-P-DTA-170 | Oversupply: Unsuccesful - outcome (placement or surplus) letters | 3 days | Mon 21/12/20 | Wed 23/12/20 | 0%
PRP-P-DTA-180 | Pre-transfer placement consultation | 22 days | Fri 01/01/21 | Sun 31/01/21 | 0%
PRP-P-DTA-190 | Voluntary redundancy | 106 days | Fri 27/03/20 | Fri 21/08/20 | 0%
PRP-P-DTA-200 | Finalise Business Case for EVR to go to HMT | 0 days | Fri 27/03/20 | Fri 27/03/20 | 100%
PRP-P-DTA-210 | Send response from HMT to Trade Unions | 0 days | Mon 27/04/20 | Mon 27/04/20 | 0%
PRP-P-DTA-220 | Review potential demand for VR following Role Assignment | 0 days | Tue 30/06/20 | Tue 30/06/20 | 0%
PRP-P-DTA-230 | Review potential demand for VR following placement | 0 days | Fri 21/08/20 | Fri 21/08/20 | 0%
PRP-P-DTA-240 | National Agreement | 0 days | Tue 14/04/20 | Tue 14/04/20 | 100%
PRP-P-DTA-250 | Review and update ballot material | 11 days | Wed 15/04/20 | Wed 29/04/20 | 0%
PRP-P-DTA-260 | Hold ballot | 22 days | Mon 01/06/20 | Tue 30/06/20 | 0%
PRP-P-DTA-270 | Joint comms | 6 days | Wed 01/07/20 | Wed 08/07/20 | 0%
PRP-P-DTA-280 | Mobilisation: TU consultation over measures | 295 days | Mon 18/05/20 | Fri 02/07/21 | 0%
PRP-P-DTA-290 | Draft measures circulated with key internal stakeholders | 10 days | Mon 18/05/20 | Fri 29/05/20 | 0%
PRP-P-DTA-300 | Draft measures for harmonised and non-harmonised | 0 days | Mon 01/06/20 | Mon 01/06/20 | 0%
PRP-P-DTA-310 | TU consultation on final measures | 23 days | Thu 01/10/20 | Sat 31/10/20 | 0%
PRP-P-DTA-320 | Measures agreed and finalised post consultation | 0 days | Sat 31/10/20 | Sat 31/10/20 | 0%
PRP-P-DTA-330 | Secretary of state to sign staff transfer agreement | 0 days | Fri 02/07/21 | Fri 02/07/21 | 0%
PRP-P-DTA-340 | Mobilisation | 345 days | Thu 30/04/20 | Wed 25/08/21 | 0%
PRP-P-DTA-350 | Mobilisation: Staff data for OM transfer | 120 days | Mon 04/01/21 | Fri 18/06/21 | 0%
PRP-P-DTA-360 | Confirm estates requirements with NPS and send list to SSCL | 25 days | Mon 04/01/21 | Fri 05/02/21 | 0%
PRP-P-DTA-370 | Final data sets received from CRCs (online and hard copies) | 0 days | Mon 31/05/21 | Mon 31/05/21 | 0%
PRP-P-DTA-380 | Payroll data finalised | 0 days | Fri 18/06/21 | Fri 18/06/21 | 0%
PRP-P-DTA-390 | Mobilisation: Transfer of casework | 284 days | Thu 30/04/20 | Tue 01/06/21 | 0%
PRP-P-DTA-400 | RFC submitted | 0 days | Thu 30/04/20 | Thu 30/04/20 | 0%
PRP-P-DTA-410 | Outcome of staff ballot | 0 days | Tue 30/06/20 | Tue 30/06/20 | 0%
PRP-P-DTA-420 | MoJ Case Managers allocated | 0 days | Tue 01/06/21 | Tue 01/06/21 | 0%
PRP-P-DTA-430 | Mobilisation: Comms | 8 days | Mon 01/02/21 | Wed 10/02/21 | 0%
PRP-P-DTA-440 | PDU head briefings | 8 days | Mon 01/02/21 | Wed 10/02/21 | 0%
PRP-P-DTA-450 | Mobilisation: Staff engagement and business change | 182 days | Tue 15/12/20 | Wed 25/08/21 | 0%
PRP-P-DTA-460 | Liase with business change and contribute to change activitis produced for OM staff | 135 days | Tue 15/12/20 | Sun 20/06/21 | 0%
PRP-P-DTA-470 | Senior leaders to hold townhalls to ensure awareness over measure | 23 days | Mon 21/06/21 | Wed 21/07/21 | 0%
PRP-P-DTA-480 | Formal letters sent to staff re. transfer/no transfer | 0 days | Mon 31/05/21 | Mon 31/05/21 | 0%
PRP-P-DTA-490 | All Staff roadshows(inc info on benefits, policies, pensions, unions) | 25 days | Thu 22/07/21 | Wed 25/08/21 | 0%
PRP-P-WFD | Workforce Data | 267 days | Fri 03/01/20 | Sun 10/01/21 | 1%
PRP-P-WFD-010 | PDP Competition | 23 days | Mon 06/04/20 | Wed 06/05/20 | 99%
PRP-P-WFD-020 | Refreshed data set for ITT PDP presented to the virtual data room - monthly based on Feb data | 5 days | Mon 06/04/20 | Fri 10/04/20 | 100%
PRP-P-WFD-030 | Refreshed data set for ITT PDP presented to the virtual data room - monthly (granular level ahead of BAFO) | 0 days | Wed 06/05/20 | Wed 06/05/20 | 0%
PRP-P-WFD-040 | Publish DF data set for data room | 0 days | Tue 14/04/20 | Tue 14/04/20 | 100%
PRP-P-WFD-050 | Consolidate the data for DF BAFO | 0 days | Wed 15/04/20 | Wed 15/04/20 | 100%
PRP-P-WFD-060 | Reporting | 238 days | Fri 03/01/20 | Tue 01/12/20 | 0%
PRP-P-WFD-070 | Ad hoc - Programme reports for various workstreams - Transition, Design, HR, legal, Commercial, Pensions, Resettlement, Target Staffing, OBC etc. | 238 days | Fri 03/01/20 | Tue 01/12/20 | 0%
PRP-P-WFD-080 | Launch and teach ins of "workforce data insights" across the programme | 0 days | Fri 10/04/20 | Fri 10/04/20 | 100%
PRP-P-WFD-090 | CRC engagement | 0 days | Tue 30/06/20 | Tue 30/06/20 | 0%
PRP-P-WFD-100 | CRC complete role assignment template | 0 days | Tue 30/06/20 | Tue 30/06/20 | 0%
PRP-P-WFD-110 | Competition Support | 204 days | Wed 01/04/20 | Sun 10/01/21 | 0%
PRP-P-WFD-120 | PDP | 204 days | Wed 01/04/20 | Sun 10/01/21 | 0%
PRP-P-WFD-130 | DF | 180 days | Fri 24/04/20 | Thu 31/12/20 | 0%
PRP-P-WFD-140 | Pensions | 187 days | Fri 24/04/20 | Sun 10/01/21 | 0%
PRP-P-WFD-150 | Assignment process data Compiled | 23 days? | Thu 30/04/20 | Mon 01/06/20 | 0%
PRP-P-SSC | SSCL | 381 days | Sat 01/02/20 | Fri 16/07/21 | 0%
PRP-P-SSC-010 | Payroll - SOP migration & system builds | 280 days | Mon 01/06/20 | Fri 25/06/21 | 0%
PRP-P-SSC-020 | Payroll - SOP migration & system builds | 0 days | Mon 01/06/20 | Mon 01/06/20 | 0%
PRP-P-SSC-030 | Agree data sharing cycle and process including transfer data – logistics * | 44 days | Tue 01/09/20 | Fri 30/10/20 | 0%
PRP-P-SSC-040 | Commercialise RFC and system build begins* | 0 days | Fri 30/10/20 | Fri 30/10/20 | 0%
PRP-P-SSC-050 | Payroll testing begins - full migration details in place, replicate Feb payroll* | 0 days | Mon 01/03/21 | Mon 01/03/21 | 0%
PRP-P-SSC-060 | Final HR Data Set Received* | 0 days | Fri 28/05/21 | Fri 28/05/21 | 0%
PRP-P-SSC-070 | Staff transfer* | 0 days | Fri 25/06/21 | Fri 25/06/21 | 0%
PRP-P-SSC-080 | Harmonisation | 85 days | Mon 01/06/20 | Fri 25/09/20 | 0%
PRP-P-SSC-090 | Obtain CRC policy/T&Cs data/info used for payroll specification | 20 days | Mon 01/06/20 | Fri 26/06/20 | 0%
PRP-P-SSC-100 | Outcome of Staff Ballot | 0 days | Tue 30/06/20 | Tue 30/06/20 | 0%
PRP-P-SSC-110 | Impact Analysis of Pay and Reward for harmonisation of staff transferring into NPS | 63 days | Wed 01/07/20 | Fri 25/09/20 | 0%
PRP-P-SSC-120 | Instruct additional SSCL system build to allow for multiple T&Cs/policies* | 0 days | Fri 25/09/20 | Fri 25/09/20 | 0%
PRP-P-SSC-130 | Data Migration | 222 days | Fri 26/06/20 | Sat 01/05/21 | 0%
PRP-P-SSC-140 | Identify SPOCs | 0 days | Fri 26/06/20 | Fri 26/06/20 | 0%
PRP-P-SSC-150 | Scope DDAT support re data migration | 8 days | Mon 29/06/20 | Wed 08/07/20 | 0%
PRP-P-SSC-160 | Identify volume of hard and soft files | 132 days | Thu 09/07/20 | Fri 08/01/21 | 0%
PRP-P-SSC-170 | File transfer | 0 days | Sat 01/05/21 | Sat 01/05/21 | 0%
PRP-P-SSC-180 | RFCs | 28 days | Mon 29/06/20 | Wed 05/08/20 | 0%
PRP-P-SSC-190 | High level staff transfer RFC1 | 26 days | Wed 01/07/20 | Wed 05/08/20 | 0%
PRP-P-SSC-200 | Review RFC1 | 15 days | Wed 01/07/20 | Tue 21/07/20 | 0%
PRP-P-SSC-210 | Amend and submit RFC1 to CCT Change | 11 days | Wed 22/07/20 | Wed 05/08/20 | 0%
PRP-P-SSC-220 | Draft RFC 2 (Harmonisation) | 10 days | Mon 29/06/20 | Fri 10/07/20 | 0%
PRP-P-SSC-230 | Submit RFCs * | 0 days | Fri 10/07/20 | Fri 10/07/20 | 0%
PRP-P-SSC-240 | Comms & engagement | 185 days | Mon 02/11/20 | Fri 16/07/21 | 0%
PRP-P-SSC-250 | Identify comms requirements for SSCL info. | 20 days | Mon 02/11/20 | Fri 27/11/20 | 0%
PRP-P-SSC-260 | Review and confirm comms plan with SSCL | 8 days | Mon 30/11/20 | Wed 09/12/20 | 0%
PRP-P-SSC-270 | Issue comms to all staff | 77 days | Thu 01/04/21 | Fri 16/07/21 | 0%
PRP-P-REC | Recruitment | 100 days | Mon 16/03/20 | Fri 31/07/20 | 12%
PRP-P-REC-010 | All Regional Directors appointed | 0 days | Wed 01/04/20 | Wed 01/04/20 | 0%
PRP-P-REC-020 | Head of Ops | 141 days | Mon 16/03/20 | Mon 28/09/20 | 17%
PRP-P-REC-030 | Candidates to select interview dates | 7 days | Mon 16/03/20 | Tue 24/03/20 | 100%
PRP-P-REC-040 | Hold interviews | 16 days | Mon 30/03/20 | Mon 20/04/20 | 100%
PRP-P-REC-050 | Interview results uploaded | 17 days | Tue 21/04/20 | Wed 13/05/20 | 0%
PRP-P-REC-060 | SSCL to process results | 18 days | Thu 14/05/20 | Mon 08/06/20 | 0%
PRP-P-REC-070 | Successful candidates informed* | 17 days | Tue 09/06/20 | Wed 01/07/20 | 0%
PRP-P-REC-080 | Successful candidates to accept conditional offer | 9 days | Thu 02/07/20 | Tue 14/07/20 | 0%
PRP-P-REC-090 | Successful candidates to give notice | 9 days | Wed 15/07/20 | Mon 27/07/20 | 0%
PRP-P-REC-100 | Pre-employment and vetting checks | 44 days | Tue 28/07/20 | Fri 25/09/20 | 0%
PRP-P-REC-110 | Candidate in post* | 0 days | Fri 25/09/20 | Fri 25/09/20 | 0%
PRP-P-REC-120 | BM/DM - EOI | 62 days | Wed 18/03/20 | Thu 11/06/20 | 43%
PRP-P-REC-130 | Interviews | 17 days | Wed 18/03/20 | Thu 09/04/20 | 100%
PRP-P-REC-140 | Candidate in post* | 0 days | Thu 09/04/20 | Thu 09/04/20 | 100%
PRP-P-REC-150 | Head of Corporate Services | 0 days | Mon 13/04/20 | Mon 13/04/20 | 100%
PRP-P-REC-160 | Annex A presented to TUs (review period) | 0 days | Tue 14/04/20 | Tue 14/04/20 | 100%
PRP-P-REC-170 | Engagement/consultation with current incumbents | 23 days | Mon 11/05/20 | Wed 10/06/20 | 0%
PRP-P-REC-180 | Recruitment process (dependent on Annex A outcome) | 0 days | Wed 10/06/20 | Wed 10/06/20 | 0%
PRP-P-REC-190 | Head of Community Integration, Commissioning and Contract Management | 101 days | Thu 30/04/20 | Thu 17/09/20 | 0%
PRP-P-REC-200 | JD submitted to JES team (dependency on JD for remaining team) | 0 days | Thu 30/04/20 | Thu 30/04/20 | 0%
PRP-P-REC-210 | Annex A drafted | 3 days | Fri 01/05/20 | Tue 05/05/20 | 0%
PRP-P-REC-220 | Annex A presented to TUs (review period) | 28 days | Wed 06/05/20 | Fri 12/06/20 | 0%
PRP-P-REC-230 | Engagement/consultation with current Senior Contract Managers | 24 days | Mon 15/06/20 | Thu 16/07/20 | 0%
PRP-P-REC-240 | Recruitment process (dependent on Annex A outcome) | 45 days | Fri 17/07/20 | Thu 17/09/20 | 0%
PRP-P-REC-250 | Head of P&Q | 77 days | Mon 20/04/20 | Tue 04/08/20 | 0%
PRP-P-REC-260 | Preference exercise held for current incumbents to identify regions for the vacancies | 10 days | Mon 20/04/20 | Fri 01/05/20 | 0%
PRP-P-REC-270 | Recruitment process for remaining vacancies | 45 days | Mon 01/06/20 | Fri 31/07/20 | 0%
PRP-P-REC-280 | Additional P&Q roles | 0 days | Mon 03/08/20 | Mon 03/08/20 | 0%
PRP-P-REC-290 | Decision on JDs and roles confirmed | 0 days | Mon 03/08/20 | Mon 03/08/20 | 0%
PRP-P-REC-300 | Additional Commissioning and Contract Management roles | 58 days | Mon 23/03/20 | Wed 10/06/20 | 0%
PRP-P-REC-310 | JDs and roles confirmed | 29 days | Mon 23/03/20 | Thu 30/04/20 | 0%
PRP-P-REC-320 | JDs to be designed and developed | 28 days | Fri 01/05/20 | Tue 09/06/20 | 0%
PRP-P-REC-330 | JD submitted to JES team | 0 days | Tue 09/06/20 | Tue 09/06/20 | 0%
PRP-P-REC-340 | Executive Assistant to Probation Regional Director (full SLT) | 28 days | Tue 24/03/20 | Thu 30/04/20 | 99%
PRP-P-REC-350 | JD design to be developed | 9 days | Tue 24/03/20 | Fri 03/04/20 | 100%
PRP-P-REC-360 | JD submitted to JES team | 0 days | Thu 30/04/20 | Thu 30/04/20 | 0%
PRP-P-REC-370 | Head of Public Protection | 2 days | Tue 14/04/20 | Wed 15/04/20 | 100%
PRP-P-REC-380 | Decision on whether the existing JD needs to be amended | 0 days | Tue 14/04/20 | Tue 14/04/20 | 100%
PRP-P-REC-390 | Decision on the recruitment process - timescales and scope | 0 days | Wed 15/04/20 | Wed 15/04/20 | 100%
PRP-P-VET | Vetting | 297 days | Mon 13/04/20 | Tue 01/06/21 | 0%
PRP-P-VET-010 | Discovery | 29 days | Mon 13/04/20 | Thu 21/05/20 | 0%
PRP-P-VET-020 | Confirmation of all vetting points of contact by May 2020 | 15 days | Mon 13/04/20 | Fri 01/05/20 | 0%
PRP-P-VET-030 | Decide if further training of VPCs are needed to increase capacity | 13 days | Mon 04/05/20 | Wed 20/05/20 | 0%
PRP-P-VET-040 | Confirmation of current level of vetting for all CRC staff | 0 days | Thu 21/05/20 | Thu 21/05/20 | 0%
PRP-P-VET-050 | Delivery approach | 27 days | Tue 05/05/20 | Wed 10/06/20 | 0%
PRP-P-VET-060 | Engage with TUs on the approach and outcomes | 0 days | Mon 04/05/20 | Mon 04/05/20 | 0%
PRP-P-VET-070 | Inform CRCs of the process of vetting and outcomes | 0 days | Wed 06/05/20 | Wed 06/05/20 | 0%
PRP-P-VET-080 | Present Final approach to Programme Board? | 0 days | Wed 10/06/20 | Wed 10/06/20 | 0%
PRP-P-VET-090 | Preparation | 89 days | Wed 01/07/20 | Sun 01/11/20 | 0%
PRP-P-VET-100 | Arrange for VPCs to be released to support Vetting of CRC staff from Nov-20 | 0 days | Wed 01/07/20 | Wed 01/07/20 | 0%
PRP-P-VET-110 | Identify and Train up additional Vetting Support Staff | 66 days | Mon 03/08/20 | Sun 01/11/20 | 0%
PRP-P-VET-120 | Send commission to SSCL to start basic vetting from information returned by the placement | 0 days | Thu 01/10/20 | Thu 01/10/20 | 0%
PRP-P-VET-130 | Delivery | 196 days | Mon 02/11/20 | Mon 02/08/21 | 0%
PRP-P-VET-140 | Validated docs uploaded by CRC staff | 86 days | Mon 02/11/20 | Mon 01/03/21 | 0%
PRP-P-VET-150 | Submit lists of people to be vetted by SSCL | 65 days | Tue 02/03/21 | Mon 31/05/21 | 0%
PRP-P-VET-160 | Implement adverse plan interventions | 44 days | Tue 01/06/21 | Fri 30/07/21 | 0%
PRP-P-VET-170 | Phase complete | 0 days | Fri 30/07/21 | Fri 30/07/21 | 0%
PRP-P-VET-180 | ViSoR Delivery | 87 days | Mon 01/02/21 | Tue 01/06/21 | 0%
PRP-P-DTR | Divisions to Regions | 274 days | Mon 16/03/20 | Thu 01/04/21 | 14%
PRP-P-DTR-010 | HR System Changes | 28 days | Mon 23/03/20 | Wed 29/04/20 | 40%
PRP-P-DTR-020 | Define/Scope all SOP changes needed to support Division to Region Changes | 10 days | Mon 23/03/20 | Fri 03/04/20 | 100%
PRP-P-DTR-030 | SSCL Make changes, test and release | 15 days | Mon 06/04/20 | Fri 24/04/20 | 0%
PRP-P-DTR-040 | Comms to regions | 0 days | Fri 24/04/20 | Fri 24/04/20 | 0%
PRP-P-DTR-050 | Oleeo changes confirmed | 0 days | Fri 24/04/20 | Fri 24/04/20 | 0%
PRP-P-DTR-060 | Comms to regions | 0 days | Fri 24/04/20 | Fri 24/04/20 | 0%
PRP-P-DTR-070 | All HR System changes to Initial setting up of regions complete | 0 days | Fri 24/04/20 | Fri 24/04/20 | 0%
PRP-P-DTR-080 | Transfer Cross-Regional Staff between Regions | 91 days | Mon 01/06/20 | Mon 05/10/20 | 0%
PRP-P-DTR-090 | Agree the NPS Cross Regional Split Approach and align with Staff Transfer | 0 days | Mon 01/06/20 | Mon 01/06/20 | 0%
PRP-P-DTR-100 | Engage with the Unions on physical location/support changes to cross regional staff to support Region and future PDUs | 0 days | Mon 01/06/20 | Mon 01/06/20 | 0%
PRP-P-DTR-110 | Raise request to SSCL to perform Bulk transfer staff between cost centres | 0 days | Thu 01/10/20 | Thu 01/10/20 | 0%
PRP-P-DTR-120 | Raise RfC to SSCL to update staff records/contracts with new work locations where applicable | 0 days | Thu 01/10/20 | Thu 01/10/20 | 0%
PRP-P-DTR-130 | Letters to staff confirming location changes | 0 days | Mon 05/10/20 | Mon 05/10/20 | 0%
PRP-P-DTR-140 | Creation of the Probation Delivery Unit Cost Centres and Bulk Transfer | 219 days | Mon 01/06/20 | Thu 01/04/21 | 0%
PRP-P-DTR-150 | Design all the PDU Cost Centres | 0 days | Mon 01/06/20 | Mon 01/06/20 | 0%
PRP-P-DTR-160 | Map all the existing LDU cost centres to the new PDU Cost centres | 0 days | Wed 01/07/20 | Wed 01/07/20 | 0%
PRP-P-DTR-170 | Map all the PEOPLE in existing LDU cost centres into the PDU Cost centres | 0 days | Sat 01/08/20 | Sat 01/08/20 | 0%
PRP-P-DTR-180 | Raise RfC to SSCL to deliver the changes by drafting and submitting an RfC | 0 days | Tue 01/12/20 | Tue 01/12/20 | 0%
PRP-P-DTR-190 | Raise request to SSCL to perform Bulk transfer staff between cost centres | 0 days | Tue 01/12/20 | Tue 01/12/20 | 0%
PRP-P-DTR-200 | SSCL to complete creation of all cost centres | 22 days | Fri 01/01/21 | Sun 31/01/21 | 0%
PRP-P-DTR-210 | SSCL to complete creation of all bulk transfer | 23 days | Mon 01/03/21 | Wed 31/03/21 | 0%
PRP-P-DTR-220 | PDUs become fully active / Go-Live | 0 days | Thu 01/04/21 | Thu 01/04/21 | 0%
PRP-P-IND | Inductions | 313 days | Thu 19/03/20 | Mon 31/05/21 | 0%
PRP-P-IND-010 | Comms announcing the new Regions and Regions Direvtors + Programme update | 5 days | Tue 28/04/20 | Mon 04/05/20 | 0%
PRP-P-IND-020 | Confirm BAU process for SLT inductions | 12 days | Tue 05/05/20 | Wed 20/05/20 | 0%
PRP-P-IND-030 | Agree other training needed | 12 days | Thu 21/05/20 | Fri 05/06/20 | 0%
PRP-P-IND-040 | Pull relevent materials together | 21 days | Mon 08/06/20 | Mon 06/07/20 | 0%
PRP-P-IND-050 | Regional Teams to deliver induction sessions for SLT staff | 109 days | Tue 07/07/20 | Fri 04/12/20 | 0%
PRP-P-IND-060 | Confirm SLT Induction sessions completed | 0 days | Fri 04/12/20 | Fri 04/12/20 | 0%
PRP-P-IND-070 | National comms when all SLT roles in post | 0 days | Tue 08/12/20 | Tue 08/12/20 | 0%
PRP-P-IND-080 | CRC Induction: Develop Approach | 46 days | Wed 01/04/20 | Wed 03/06/20 | 0%
PRP-P-IND-090 | Scope out induction requirements, stakeholders, content owners, existing processes etc | 0 days | Wed 01/04/20 | Wed 01/04/20 | 100%
PRP-P-IND-100 | Develop Approach for how to deliver induction for ~4500 CRC staff | 0 days | Thu 02/04/20 | Thu 02/04/20 | 100%
PRP-P-IND-110 | Propose approach to People Board | 0 days | Wed 03/06/20 | Wed 03/06/20 | 0%
PRP-P-IND-120 | Comms to CRC staff to outline the induction plan, process etc | 0 days | Thu 04/06/20 | Thu 04/06/20 | 0%
PRP-P-IND-130 | CRC Induction: LCC | 304 days | Tue 14/04/20 | Fri 11/06/21 | 0%
PRP-P-IND-140 | Agree process for identifying CRC Local Change Champions (LCC) | 282 days | Tue 14/04/20 | Wed 12/05/21 | 0%
PRP-P-IND-150 | Deliver Workshops | 22 days | Thu 13/05/21 | Fri 11/06/21 | 0%
PRP-P-IND-160 | Add new CRC LCCs to LCC HMPPS Network | 0 days | Wed 12/05/21 | Wed 12/05/21 | 0%
PRP-P-IND-170 | CRC Staff Induction: Venue/Delivery | 282 days | Fri 01/05/20 | Mon 31/05/21 | 0%
PRP-P-IND-180 | Procure eLearning solution | 32 days | Fri 01/05/20 | Mon 15/06/20 | 0%
PRP-P-IND-190 | Review and test induction content | 166 days | Mon 13/07/20 | Sun 28/02/21 | 0%
PRP-P-IND-200 | Face-to-Face Line Manager / staff Sessions | 21 days | Mon 03/05/21 | Mon 31/05/21 | 0%
PRP-P-LND | Learning & Development | 500 days | Fri 01/05/20 | Thu 31/03/22 | 0%
PRP-P-LND-010 | Develop approach | 177 days | Fri 01/05/20 | Mon 04/01/21 | 0%
PRP-P-LND-020 | Develop approach for in scope training delivery | 0 days | Fri 01/05/20 | Fri 01/05/20 | 0%
PRP-P-LND-030 | Comission development of course content and convert into eLearning modules | 67 days | Mon 01/06/20 | Tue 01/09/20 | 0%
PRP-P-LND-040 | Arrange logistic, rooms etc | 89 days | Wed 02/09/20 | Mon 04/01/21 | 0%
PRP-P-LND-050 | Preparation | 85 days | Mon 01/02/21 | Fri 28/05/21 | 0%
PRP-P-LND-060 | Receive results from CRCs of skills audit and training needs at OM staff | 0 days | Mon 01/02/21 | Mon 01/02/21 | 0%
PRP-P-LND-070 | Identify skills gap | 22 days | Thu 01/04/21 | Fri 30/04/21 | 0%
PRP-P-LND-080 | Finalise modules of mandatory training for all staff groups | 20 days | Mon 03/05/21 | Fri 28/05/21 | 0%
PRP-P-LND-090 | Delivery | 195 days | Fri 02/07/21 | Thu 31/03/22 | 0%
PRP-P-LND-100 | Essential training phase 1 (high risk of harm, Sex Offenders, MAPPA, oral hearings, child safeguarding & CS essentials) | 65 days | Fri 02/07/21 | Thu 30/09/21 | 0%
PRP-P-LND-110 | Essentail training phase 2(remaining mandatory training, other core learning & role specific training, mop up from phase 1) | 130 days | Fri 01/10/21 | Thu 31/03/22 | 0%
PRP-D | DDaT | 365 days | Mon 03/02/20 | Fri 25/06/21 | 4%
PRP-D-MIL | Milestones | 296 days | Tue 14/04/20 | Tue 01/06/21 | 0%
PRP-D-MIL-010 | Technology delivery: Estates requirements confirmed | 0 days | Wed 01/07/20 | Wed 01/07/20 | 0%
PRP-D-MIL-020 | Delius/Oasys Roll Out (East and West Lincolnshire) | 0 days | Mon 04/05/20 | Mon 04/05/20 | 0%
PRP-D-MIL-030 | Delius/Oasys Roll Out (North West) | 0 days | Mon 01/06/20 | Mon 01/06/20 | 0%
PRP-D-MIL-040 | Delius/Oasys Roll Out (North East) | 0 days | Mon 29/06/20 | Mon 29/06/20 | 0%
PRP-D-MIL-050 | Delius/Oasys Roll Out (Remaining Regions) | 0 days | Mon 19/10/20 | Mon 19/10/20 | 0%
PRP-D-MIL-060 | Interventions catalogue live | 0 days | Mon 01/03/21 | Mon 01/03/21 | 0%
PRP-D-MIL-070 | Interventions booking live | 0 days | Sat 01/05/21 | Sat 01/05/21 | 0%
PRP-D-MIL-080 | Provider services live | 0 days | Sat 01/05/21 | Sat 01/05/21 | 0%
PRP-D-MIL-090 | Provider updates live | 0 days | Sat 01/05/21 | Sat 01/05/21 | 0%
PRP-D-MIL-100 | Interventions service | 0 days | Fri 25/06/21 | Fri 25/06/21 | 0%
PRP-D-MIL-110 | NPS Structures - England | 132 days | Mon 01/06/20 | Tue 01/12/20 | 0%
PRP-D-MIL-120 | OMIC sentence plan live | 0 days | Thu 01/10/20 | Thu 01/10/20 | 0%
PRP-D-MIL-130 | Probation in Court live | 0 days | Fri 01/01/21 | Fri 01/01/21 | 0%
PRP-D-MIL-140 | IT site surveys completed | 0 days | Fri 01/01/21 | Fri 01/01/21 | 0%
PRP-D-MIL-150 | User Matrix Frozen | 0 days | Wed 31/03/21 | Wed 31/03/21 | 0%
PRP-D-DIG | Digital Delivery | 1 day | Tue 14/04/20 | Tue 14/04/20 | 9%
PRP-D-DIG-010 | Catalogue and Booking | 372 days | Sun 01/12/19 | Sat 01/05/21 | 13%
PRP-D-DIG-020 | Interventions catalogue | 327 days | Sun 01/12/19 | Mon 01/03/21 | 13%
PRP-D-DIG-030 | Discovery | 47 days | Sun 01/12/19 | Sat 01/02/20 | 0%
PRP-D-DIG-040 | Alpha | 44 days | Sat 01/02/20 | Wed 01/04/20 | 100%
PRP-D-DIG-050 | Private Beta | 110 days | Wed 01/04/20 | Tue 01/09/20 | 0%
PRP-D-DIG-060 | Public beta | 130 days | Tue 01/09/20 | Mon 01/03/21 | 0%
PRP-D-DIG-070 | Live | 0 days | Mon 01/03/21 | Mon 01/03/21 | 0%
PRP-D-DIG-080 | Interventions Booking Discovery | 327 days | Sat 01/02/20 | Sat 01/05/21 | 13%
PRP-D-DIG-090 | Discovery | 44 days | Sat 01/02/20 | Wed 01/04/20 | 100%
PRP-D-DIG-100 | Alpha | 66 days | Wed 01/04/20 | Wed 01/07/20 | 0%
PRP-D-DIG-110 | Private Beta | 89 days | Wed 01/07/20 | Sun 01/11/20 | 0%
PRP-D-DIG-120 | Public beta | 132 days | Sun 01/11/20 | Sat 01/05/21 | 0%
PRP-D-DIG-130 | Live | 0 days | Sat 01/05/21 | Sat 01/05/21 | 0%
PRP-D-DIG-140 | Provider Services and Updates | 457 days | Sat 01/02/20 | Mon 01/11/21 | 6%
PRP-D-DIG-150 | Provider services | 327 days | Sat 01/02/20 | Sat 01/05/21 | 13%
PRP-D-DIG-160 | Discovery | 44 days | Sat 01/02/20 | Wed 01/04/20 | 100%
PRP-D-DIG-170 | Alpha | 66 days | Wed 01/04/20 | Wed 01/07/20 | 0%
PRP-D-DIG-180 | Private Beta | 89 days | Wed 01/07/20 | Sun 01/11/20 | 0%
PRP-D-DIG-190 | Public beta | 132 days | Sun 01/11/20 | Mon 03/05/21 | 0%
PRP-D-DIG-200 | Live | 0 days | Sat 01/05/21 | Sat 01/05/21 | 0%
PRP-D-DIG-210 | Provider updates | 414 days | Wed 01/04/20 | Mon 01/11/21 | 0%
PRP-D-DIG-220 | Discovery | 44 days | Wed 01/04/20 | Mon 01/06/20 | 0%
PRP-D-DIG-230 | Alpha | 67 days | Mon 01/06/20 | Tue 01/09/20 | 0%
PRP-D-DIG-240 | Private Beta | 305 days | Tue 01/09/20 | Mon 01/11/21 | 0%
PRP-D-DIG-250 | Public beta | 0 days | Sat 01/05/21 | Sat 01/05/21 | 0%
PRP-D-DIG-260 | Live | 0 days | Sat 01/05/21 | Sat 01/05/21 | 0%
PRP-D-DIG-270 | Interventions Service | 263 days | Sun 01/12/19 | Tue 01/12/20 | 16%
PRP-D-DIG-280 | Deployment pipeline set up | 67 days | Sun 01/12/19 | Sun 01/03/20 | 100%
PRP-D-DIG-290 | Interventions Service access discovery | 46 days | Sun 01/03/20 | Fri 01/05/20 | 0%
PRP-D-DIG-300 | Alpha | 44 days | Fri 01/05/20 | Wed 01/07/20 | 0%
PRP-D-DIG-310 | Private beta | 110 days | Wed 01/07/20 | Tue 01/12/20 | 0%
PRP-D-DIG-320 | Public beta | 149 days | Tue 01/12/20 | Fri 25/06/21 | 0%
PRP-D-DIG-330 | Live | 0 days | Fri 25/06/21 | Fri 25/06/21 | 0%
PRP-D-DIG-340 | NPS Structures | 240 days | Wed 01/01/20 | Tue 01/12/20 | 0%
PRP-D-DIG-350 | Tiering | 0 days | Wed 01/01/20 | Wed 01/01/20 | 100%
PRP-D-DIG-360 | Wales | 0 days | Wed 01/01/20 | Wed 01/01/20 | 100%
PRP-D-DIG-370 | NPS structure changes | 109 days | Wed 01/01/20 | Mon 01/06/20 | 0%
PRP-D-DIG-380 | England | 132 days | Mon 01/06/20 | Tue 01/12/20 | 0%
PRP-D-DIG-390 | Sentence and Assessments | 524 days | Sun 01/12/19 | Wed 01/12/21 | 11%
PRP-D-DIG-400 | OMIC sentence plan | 220 days | Sun 01/12/19 | Thu 01/10/20 | 41%
PRP-D-DIG-410 | Alpha | 47 days | Sun 01/12/19 | Sat 01/02/20 | 100%
PRP-D-DIG-420 | Private Beta | 44 days | Sat 01/02/20 | Wed 01/04/20 | 100%
PRP-D-DIG-430 | Public beta | 132 days | Wed 01/04/20 | Thu 01/10/20 | 0%
PRP-D-DIG-440 | Live | 0 days | Thu 01/10/20 | Thu 01/10/20 | 0%
PRP-D-DIG-450 | Assessment | 366 days | Sat 01/02/20 | Fri 25/06/21 | 12%
PRP-D-DIG-460 | Discovery | 44 days | Sat 01/02/20 | Wed 01/04/20 | 100%
PRP-D-DIG-470 | Alpha | 66 days | Wed 01/04/20 | Wed 01/07/20 | 0%
PRP-D-DIG-480 | Private Beta | 110 days | Wed 01/07/20 | Tue 01/12/20 | 0%
PRP-D-DIG-490 | Public beta | 149 days | Tue 01/12/20 | Fri 25/06/21 | 0%
PRP-D-DIG-500 | Live | 0 days | Fri 25/06/21 | Fri 25/06/21 | 0%
PRP-D-DIG-510 | Sentence plan | 479 days | Sat 01/02/20 | Wed 01/12/21 | 0%
PRP-D-DIG-520 | Discovery | 44 days | Wed 01/04/20 | Mon 01/06/20 | 0%
PRP-D-DIG-530 | Alpha | 67 days | Mon 01/06/20 | Tue 01/09/20 | 0%
PRP-D-DIG-540 | Private Beta | 0 days | Sat 01/02/20 | Sat 01/02/20 | 100%
PRP-D-DIG-550 | Public beta | 479 days | Sat 01/02/20 | Wed 01/12/21 | 0%
PRP-D-DIG-560 | Case and court | 415 days | Sun 01/12/19 | Thu 01/07/21 | 0%
PRP-D-DIG-570 | Probation in court | 286 days | Sun 01/12/19 | Fri 01/01/21 | 0%
PRP-D-DIG-580 | Private Beta | 154 days | Sun 01/12/19 | Wed 01/07/20 | 0%
PRP-D-DIG-590 | Public beta | 133 days | Wed 01/07/20 | Fri 01/01/21 | 0%
PRP-D-DIG-600 | Live | 0 days | Fri 01/01/21 | Fri 01/01/21 | 0%
PRP-D-DIG-610 | Workforce case management | 175 days | Wed 01/04/20 | Tue 01/12/20 | 0%
PRP-D-DIG-620 | Discovery | 45 days | Wed 01/07/20 | Tue 01/09/20 | 0%
PRP-D-DIG-630 | Alpha | 66 days | Tue 01/09/20 | Tue 01/12/20 | 0%
PRP-D-DIG-640 | Private Beta | 88 days | Tue 01/12/20 | Thu 01/04/21 | 0%
PRP-D-DIG-650 | Public beta | 45 days | Sat 01/05/21 | Thu 01/07/21 | 0%
PRP-D-DAT | Data | 0 days | Tue 14/04/20 | Tue 14/04/20 | 0%
PRP-D-DAT-010 | Day 1 Digital Services: Digital services contain data requirements & Appropriate data modelling / management exists in Digital | 0 days | Sun 21/06/20 | Sun 21/06/20 | 0%
PRP-D-DAT-020 | Data Pipelines to/from Analytical Platform: Oasys, Delius, and day-one critical services data are regularly and automatically copied to the Analytical Platform for analysts and data scientists to use | 0 days | Sun 21/06/20 | Sun 21/06/20 | 0%
PRP-D-TEC | Technology Transition Delivery | 0 days | Tue 14/04/20 | Tue 14/04/20 | 0%
PRP-D-TEC-010 | WAN/LAN/WiFi | 323 days | Wed 01/04/20 | Fri 25/06/21 | 0%
PRP-D-TEC-020 | Discovery - Site Surveys | 198 days | Wed 01/04/20 | Fri 01/01/21 | 0%
PRP-D-TEC-030 | Supplier engagement - ordering, solution, governance | 155 days | Mon 01/06/20 | Fri 01/01/21 | 0%
PRP-D-TEC-040 | Delivery - Circuits, infrastructure | 196 days | Tue 01/09/20 | Tue 01/06/21 | 0%
PRP-D-TEC-050 | EUD/Users/Print/Telephony | 392 days | Wed 01/01/20 | Thu 01/07/21 | 0%
PRP-D-TEC-060 | User requirements - matrix | 176 days | Mon 01/06/20 | Mon 01/02/21 | 0%
PRP-D-TEC-060 | Agree matrix template | 32 days | Wed 01/04/20 | Thu 14/05/20 | 0%
PRP-D-TEC-060 | Issue matrix template | 0 days | Thu 14/05/20 | Thu 14/05/20 | 0%
PRP-D-TEC-060 | Initiate compilation | 87 days | Sun 01/11/20 | Sun 28/02/21 | 0%
PRP-D-TEC-060 | Matrix received back | 87 days | Tue 01/12/20 | Wed 31/03/21 | 0%
PRP-D-TEC-060 | Freeze matrix (week-by-week) | 87 days | Tue 01/12/20 | Wed 31/03/21 | 0%
PRP-D-TEC-060 | Supplier engagement - ordering, solution, governance | 174 days | Wed 01/07/20 | Mon 01/03/21 | 0%
PRP-D-TEC-060 | Delivery - logistics, account creation, handover training | 130 days | Fri 01/01/21 | Thu 01/07/21 | 0%
PRP-D-TEC-060 | Data | 388 days | Wed 01/01/20 | Fri 25/06/21 | 0%
PRP-D-TEC-060 | Discovery - Analysis, migration, solution | 242 days | Sun 01/03/20 | Mon 01/02/21 | 0%
PRP-D-TEC-060 | Data Migration | 392 days | Wed 01/01/20 | Thu 01/07/21 | 0%
PRP-D-TEC-060 | Applications | 196 days | Thu 01/10/20 | Thu 01/07/21 | 0%
PRP-D-TEC-060 | Account creation, team creation, testing, UAT | 196 days | Thu 01/10/20 | Thu 01/07/21 | 0%
PRP-D-TEC-060 | Video | 262 days | Wed 01/07/20 | Thu 01/07/21 | 0%
PRP-D-TEC-060 | Supplier engagement - ordering, solution, governance | 174 days | Wed 01/07/20 | Mon 01/03/21 | 0%
PRP-D-TEC-060 | Delivery - logistics, installation, training | 130 days | Fri 01/01/21 | Thu 01/07/21 | 0%
PRP-D-TD | NPS 7-12 Technology Delivery | 1 day | Wed 01/07/20 | Wed 01/07/20 | 0%
PRP-D-TD-010 | Divisions to regions | 89 days | Sun 01/03/20 | Wed 01/07/20 | 0%
PRP-D | Transition TBC | 0 days | Tue 14/04/20 | Tue 14/04/20 | 0%

## Sandbox (hidden)
Day1 Requirements & Inter/Dependencies (Customer & Digital)
Dependency: Reliance on just one other area to address requirement
Interdependency: Reliance across multiple areas to address requirement
Sub Theme | Service / Work Package | Cluster | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency | Interdependency | With | With | With | Date needed by | Approved?
e.g. Environment | e.g. Place Theme - Housing |  | e.g. AUDIT-REQ1 | e.g. Out Of Hours Service | e.g. Must have/Should have | e.g. is reliant upon decisions being made by | e.g. requires support from | e.g. Workstream - Organisational Development & Human Resources | e.g. ICT - Service Continuity | e.g. Customer & Digital - Service Functions | e.g. 01/08/2022 | (Yes/No)

## Front Page (hidden)
Cumbria Local Government Reorganisation (LGR)
Engagement Lead: |  | Andrew Lea
Engagement Manager: |  | Will Hamilton
Definitions of Key Terms used within this document
Key Term | Definition
Actions | Key actions are what needs to be done to progress activity and mitigate against arising risks.
Assumptions | Project assumptions are events or circumstances that are expected to occur during the project life-cycle.
Change | Change control is the process through which all requests to change the baseline scope of a project, programme or portfolio are captured, evaluated and then approved, rejected or deferred. A change register is a record of all proposed changes to scope.
Decisions | Key decisions are formal agreement on the actions to be taken, often coming from Boards and Delivery Groups.
Dependencies | A project dependency is where a task, milestone or activity is dependent on another milestone or activity being completed before it can start or be completed
Issues | A formal issue occurs when the tolerances of delegated work are predicted to be exceeded or have been exceeded. This triggers the escalation of the issue from one level of management to the next in order to seek a solution.
Plan | The plan is the statement of how and when the programme's objectives are to be achieved, by showing the major milestones and activities required on the project.
Plan On A Page (POAP) | A Plan on a Page is a concise, one page synthesis of the key milestones and activity from the programme plan, to be used to communicate strategy and priorities to key senior stakeholders.
Requirements | Requirements are capabilities to help the project team understand exactly what is to be provided and forms the basis of the project scope. Requirements must be clearly defined, consistent (with other requirements), complete, traceable and verifiable.
Risks | A risk is the potential of an action or event to impact on the achievement of objectives.

## Guidance
Cumbria Local Government Reorganisation (LGR)
Guidance on how to complete the workbook
Day 1 Requirements & Dependencies Tab Theme Tab: Use drop down function to mark theme to the appropriate theme as per programme reset. Cluster Tab: Use drop down to map the cluster as appropriate. Service / Work Package Tab: Use the drop down to categorise the correct Service / work package to the appropriate cluster and theme. Requirement ID: Please input the requirement ID using format: 'Abbreviation of work package' '-REQ' '1,2,3,etc...' (e.g. Health and Safety Requirement Number 1 = H&S-REQ1) Day 1 Requirement: Provide a description for the necessary requirement for go-live on day 1. Priority/MoSCoW: Please choose between drop down options "Must Have", "Should Have", "Could Have", "Won't Have" based on the correct classification of requirement. Dependency: Please provide detail of the dependency (the reliance on one other area to address requirement) of the item. Interdependency: Please provide detail of the reliance across multiple areas to address requirement. If it is not dependent on any other workstream - choose 'none' within the with column With: Using the drop down, choose the corresponding services/work package(s) needed to fulfill requirements (Note: if it requires multiple - please insert new below copying columns A-H and add additional workpackage in Column I) Comment: Include any supplementary details about dependencies and interdependencies (if required). Date Needed By: Infill the requirement date. Agreed?: Provide detail on whether the corresponding workpackages have agreed the requirements unanimously. |  | Assumptions Tab ID: If the assumption is linked to a Day 1 Requirement, the ID will correspond to the relevant Day 1 Requirement (e.g. Health and Safety Requirement Number 1 = H&S-REQ1) If the assumption is not linked to a Day 1 Requirement, it will have its own unique assumption ID using the format: 'Abbreviation of work package' '-ASSUM' '1,2,3,etc (e.g. Business Admin Assumption 1 = ADMIN-ASSUM1) Theme Tab: Use drop down function to mark theme to the appropriate theme as per programme rest. Cluster Tab: Use drop down to map the cluster as appropriate. Service / Work Package Tab: Use the drop down to categorise the correct Service / Work Package to the appropriate cluster and theme. Assumption: Please provide detail of the assumption correlated to the requirement. Work Package Responsible: Using the drop down, map the assumption to the relevant and responsible work package. Agreed: Provide detail on whether the corresponding workpackages have agreed the requirements unanimously. Priority: Using drop down, choose the priority based on the below criteria. High Priority: Fundamental in shaping the blueprint design Medium Priority: Impacts detail of the blueprint but not overall shape Low Priority: Does not significantly impact the blueprint or shape

## Overview (hidden)
Cumbria LGR Overview
Data Definitions
Purpose | Provide detailed information on each data field used, the source of this data and the format to be used.
Guidance | To provide guidance to the user, this sheet is locked and should only be edited by the PMO.
Delivery Summary
Purpose | This provides a high-level summary of the content in the other sheets, providing a 1-page overview of the key risks and issues, decisions, dependencies and assumptions.
Guidance | To be regularly updated in accordance with the reporting schedule to reflect changes within the workstream and escalate as appropriate.
Day 1 Requirements
Purpose | All of the Day 1 Requirements for the programme collated in a single document. Requirements relevant to the workstream are highlighted using orange text. EDIT this to context
Guidance | This sheet is for reference and should not be amended by the workstream once the applicable requirements are agreed.
Requirements Tracker
Purpose | Provide a reporting and tracking mechanism for the workstream against their Day 1 Requirements, linking these to the relevant milestones, risks, dependencies and decisions, in order to identify potential changes and challenges to meeting requirements.
Guidance | SPM/WL to review and update whenever another worksheet is amended.
Plan On A Page (POAP)
Purpose | Provide a high-level overview of the activities and milestones from the workstream plan, to communicate strategy and priorities to stakeholders.
Guidance | To be updated by the SPM/WL once a change to a milestone or activity included in the POAP has been through formal change control.
Milestone and Activity Summary Sheet (MASS)
Purpose | Summarise all of the milestones and activity that is set out in the plan, to provide an understanding of the baseline and forecast dates and any deltas.
Guidance | To be updated by the SPM/WL once a change to a milestone or activity has been through formal change control. The baseline dates are locked down and will not change.
Plan
Purpose | Workstream milestones from the MSP plan, set out as an automated Gantt chart depicting the forecast start and finish dates. Each month can be expanded/collapsed as required for ease of use.
Guidance | Changes to the planned milestones and their forecast start and finish dates are to be captured in here after they have been through the Change Control process and approved by the PMO.
Dependencies
Purpose | Record and monitor key 'Give' or 'Get' Dependency Milestones, prioritise and use RAG rating to track potential impact.
Guidance | To be regularly updated in accordance with the reporting schedule to reflect changes within the workstream and escalate as appropriate.
Risks, Issues and Assumptions
Purpose | Risk profile for the workstream of Programme level risks, issues and assumptions, including mitigations and tipping points.
Guidance | To be regularly reviewed and maintained to ensure consistency with risk.
Key Decisions and Actions
Purpose | A log of all key decisions and actions to be taken, identifying owners and setting out required timescales.
Guidance | To be regularly updated in accordance with the reporting schedule to reflect changes within the workstream and escalate as appropriate.
Change Register
Purpose | Provide a log of all changes proposed and the progress of each change request through the approvals process.
Guidance | To be updated every time a change is proposed through the formal change control process.
The template for this document has been created and is owned by the XXX to be used by each workstream to measure and report on performance and progress.
The workstream Senior Project Manager alongside the Workstream Lead will manage the document and submit it to the Programme PMO in alignment with the reporting structure - TBC, via an upload to XXX.
If you have any queries around this template please contact the XXX mailbox - xxx
This page provides an overview of each worksheet within this pack and how it is to be used. The title of each worksheet provides a hyperlink directly to the relevant sheet.

## Data Definitions (hidden)
| Data Definitions for the Workstream Performance Measurement Update Pack |  |  | Updated: 18/03/2022
| Field Type | Description | Source | Format
Delivery Summary
Jun-21 Go Live RAG | RAG | This is a shape with accompanying text demonstrating the feasibility of achieving Jun-21 as a Go-Live date. The formatting of this is to be amended manually by the user as appropriate. | New - Workstream Lead | Red / Red/Amber / Amber / Amber/Green / Green
Jun-21 Go Live Narrative | Narrative | Summary narrative text to support RAG status, clearly setting out reasoning behind decision | New - Workstream Lead | Free text
Dec-21 Go Live RAG | RAG | This is a shape with accompanying text demonstrating the feasibility of achieving Dec-21 as a Go-Live date. The formatting of this is to be amended manually by the user as appropriate. | New - Workstream Lead | Red / Red/Amber / Amber / Amber/Green / Green
Dec-21 Go Live Narrative | Narrative | Summary narrative text to support RAG status, clearly setting out reasoning behind decision | New - Workstream Lead | Free text
Decision: ID | Unique ID | ID assigned to the decision in the 'Decisions + Actions' worksheet | Decisions + Actions worksheet | DDaT-DEC-000
Decision: Title | Short text | Title assigned to the decision in the 'Decisions + Actions' worksheet | Decisions + Actions worksheet | Free text
Decision: Description | Narrative | Brief summary of decision that is recorded in more detail in the 'Decisions + Actions' worksheet | Decisions + Actions worksheet | Free text
Decision: Required by | Date | Date Decision Required assigned to the decision in the 'Decisions + Actions' worksheet | Decisions + Actions worksheet | dd-mmm-yy
Risks/Issues: Risk ID | Unique ID | Risk ID assigned to the risk/issue in the 'Risks + Assumptions' worksheet | Risks + Assumptions worksheet | 0000
Risks/Issues: Title | Short text | Title assigned to the risk/issue in the 'Risks + Assumptions' worksheet | Risks + Assumptions worksheet | Free text
Risks/Issues: Description | Narrative | Brief summary of decision that is recorded in more detail in the 'Risks + Assumptions' worksheet | Risks + Assumptions worksheet | Free text
Risks/Issues: Required by | Date | Date Decision Required assigned to the risk/issue in the 'Risks + Assumptions' worksheet | Risks + Assumptions worksheet | dd-mmm-yy
Dependencies: ID | Unique ID | ID assigned to the dependency in the 'Dependencies' worksheet | Dependencies worksheet | DDaT-DEP-000
Dependencies: Title | Short text | Title assigned to the dependency in the 'Dependencies' worksheet | Dependencies worksheet | Free text
Dependencies: Description | Narrative | Brief summary of dependency that is recorded in more detail in the 'Dependencies' worksheet | Dependencies worksheet | Free text
Dependencies: Required by | Date | Date Decision Required assigned to the dependency in the 'Dependencies' worksheet | Dependencies worksheet | dd-mmm-yy
Assumptions: ID | Unique ID | ID assigned to the assumption in the 'Risks + Assumptions' worksheet | Risks + Assumptions worksheet | DDaT-ASS-000
Assumptions: Title | Short text | Title assigned to the assumption in the 'Risks + Assumptions' worksheet | Risks + Assumptions worksheet | Free text
Assumptions: Description | Narrative | Brief summary of assumption that is recorded in more detail in the 'Risks + Assumptions' worksheet | Risks + Assumptions worksheet | Free text
Assumptions: Required by | Date | Date Decision Required assigned to the assumption in the 'Risks + Assumptions' worksheet | Risks + Assumptions worksheet | dd-mmm-yy
Requirements Tracker
Business Area | Short text | Relevant Business Area title input from Day1 Requirements worksheet - pre-populated | Day1 Requirements worksheet | Free text
Operational Architecture Lever | Short text | Relevant title input from Day1 Requirements worksheet - pre-populated | Day1 Requirements worksheet | Free text
Requirement ID | Unique ID | Unique ID assigned to requirement | New - Workstream Lead | DDaT-REQ-000
Day 1 Requirement | Narrative | Requirement description from Day1 Requirements worksheet | Day1 Requirements worksheet | Free text
Milestone ID | Unique ID | Unique ID assigned to milestone(s) relevant to requirement | Plan worksheet | PRP-D-xxx-000
Risk ID | Unique ID | Unique ID assigned to risk/issue(s) relevant to requirement | Risks + Assumptions worksheet | 0000
Decision ID | Unique ID | Unique ID assigned to decision(s) relevant to requirement | Decisions + Actions worksheet | DDaT-DEC-000
Dependency ID | Unique ID | Unique ID assigned to dependency(s) relevant to requirement | Dependencies worksheet | DDaT-DEP-000
POAP
Any changes to the key milestones/activity should be updated here in each reporting peRiskd by adding/removing/updating the shapes as required
Milestone and Activity Summary Sheet
Level | Dropdown | Dropdown menu to select the defined WBS level that the milestone/activity sits at within the Programme WBS in MSP | MSP WBS | L2 / L3 / L4
Milestone Code | Unique ID | Unique ID assigned to milestone/activity in the WBS in MSP | MSP WBS | PRP-D-xxx-000
WBS | Short text | Task name assigned to the milestone/activity in the WBS in MSP | MSP WBS | Free text
Baseline Start Date | Date | Locked down start date of milestone/activity agreed in WBS in MSP | MSP WBS | dd-mmm-yy
Baseline Finish Date | Date | Locked down finish date of milestone/activity agreed in WBS in MSP | MSP WBS | dd-mmm-yy
Previous Reporting PeRiskd Forecast: Start Date | Date | User to update with the start date forecast in previous reporting peRiskd in the 'Current Reporting PeRiskd Forecast' | MASS: Current Reporting PeRiskd Forecast: Start Date | dd-mmm-yy
Previous Reporting PeRiskd Forecast: Finish Date | Date | User to update with the finish date forecast in previous reporting peRiskd in the 'Current Reporting PeRiskd Forecast' | MASS: Current Reporting PeRiskd Forecast: Finish Date | dd-mmm-yy
Current Reporting PeRiskd Forecast: Start Date | Date | Update with any changes to the forecast start date for the current reporting peRiskd from the Plan worksheet | Plan worksheet | dd-mmm-yy
Current Reporting PeRiskd Forecast: Finish Date | Date | Update with any changes to the forecast finish date for the current reporting peRiskd from the Plan worksheet | Plan worksheet | dd-mmm-yy
End Date Delta1 - Current forecast vs Baseline | Formula | No action needed - formula calculates delta automatically | Automatically populated | Formula output
End Date Delta2 - Current forecast vs Previous forecast | Formula | No action needed - formula calculates delta automatically | Automatically populated | Formula output
Plan
ID | Unique ID | Unique ID assigned to milestone/activity in the WBS in MSP | MSP WBS | PRP-D-xxx-000
B / N | Dropdown | Baseline or New dropdown menu. Select 'N' for any new milestones or activity that are added into the plan. | New - Workstream Lead | B / N
Status | Percentage | Percentage activity is complete in the WBS in MSP | MSP WBS | x%
Milestone / Activity | Short text | Task name assigned to the milestone/activity in the WBS in MSP | MSP WBS | Free text
Critical | Dropdown | Dropdown menu to select 'C' if the milestone/activity is critical | New - Workstream Lead | C / blank
Baseline Start Date | Date | Do not edit - locked down start date of milestone/activity agreed in WBS in MSP | MSP WBS | dd-mmm-yy
Baseline Finish Date | Date | Do not edit - locked down finish date of milestone/activity agreed in WBS in MSP | MSP WBS | dd-mmm-yy
Forecast Start Date | Date | User to update with any changes to the forecast start date for the current reporting peRiskd | New - Workstream Lead | dd-mmm-yy
Forecast Finish Date | Date | User to update with any changes to the forecast finish date for the current reporting peRiskd | New - Workstream Lead | dd-mmm-yy
Owner | Short text | Name of the owner assigned to the milestone/activity, this should remain the same in each reporting peRiskd |  | Free text
Dependencies
ID | Unique ID | Unique ID assigned to dependency | New - Workstream Lead | DDaT-DEP-000
Status | Percentage | Percentage activity is complete - take data from Plan worksheet | Plan worksheet | x%
Give Milestone / Activity | Short text | Task name assigned to the milestone/activity in the WBS in MSP | Plan worksheet | Free text
Critical | Dropdown | Dropdown menu to select 'C' if the milestone/activity is critical | Plan worksheet | C / blank
Forecast Start Date | Date | Updated forecast start date from Plan worksheet | Plan worksheet | dd-mmm-yy
Forecast Finish Date | Date | Updated forecast finish date from Plan worksheet | Plan worksheet | dd-mmm-yy
Baseline Finish v Forecast Finish Delta | Number | Take calculated delta from MASS worksheet - take the cell value, rather than copying and pasting the formula as this will cause an error | MASS worksheet - End Date Delta1 - Current forecast vs Baseline | +/- xx
RAG | RAG | Move diamond shape to correct cell to reflect the current impact of dependency | New - Workstream Lead | Red / Red/Amber / Amber / Amber/Green / Green
ID | Unique ID | Unique ID assigned to dependency | New - Workstream Lead | DDaT-DEP-000
Status | Percentage | Percentage activity is complete - take data from Plan worksheet | Plan worksheet | x%
Get Milestone / Activity | Short text | Task name assigned to the milestone/activity in the WBS in MSP | Plan worksheet | Free text
Critical | Dropdown | Dropdown menu to select 'C' if the milestone/activity is critical | Plan worksheet | C / blank
Forecast Start Date | Date | Updated forecast start date from Plan worksheet | Plan worksheet | dd-mmm-yy
Forecast Finish Date | Date | Updated forecast finish date from Plan worksheet | Plan worksheet | dd-mmm-yy
Baseline Finish v Forecast Finish Delta | Number | Take calculated delta from MASS worksheet - take the cell value, rather than copying and pasting the formula as this will cause an error | MASS worksheet - End Date Delta1 - Current forecast vs Baseline | +/- xx
Risks, Issues and Assumptions
WBS ID | Unique ID | Unique ID assigned to milestone/activity related to the risk/issue | Plan worksheet | PRP-D-xxx-000
Risk ID | Unique ID | Unique ID assigned to the risk/issue in Risk | Risk | 0000
Risk Title | Short text | Title of risk, as recorded in Risk | Risk | Free text
Date Raised | Date | Date on which the risk/issue was raised, as recorded in Risk | Risk | dd-mmm-yy
Risk Score | Number | Overall score taken from Risk assessing the Impact and Likelihood of the risk/issue | Risk | 0-25
Mitigation / Action | Narrative | Narrative from Risk describing the mitigations (controls) to be implemented | Risk | Free text
Key Threshold / Tipping Point | Narrative | Narrative setting out the threshold/tipping point at which the risk will become an issue | New - Workstream Lead | Free text
Risk Owner | Short text | Name of the owner assigned to the risk/issue in Risk | Risk | Free text
Dependencies | Narrative | Narrative setting out the other areas which will be directly impacted if the risk materialises and areas which will influence the risk materialising. This text should also include the dependency ID. | Dependencies worksheet | Free text
Decisions | Narrative | A record of the decisions made and actions to be taken relating to this risk/issue as recorded in the Decisions + Actions worksheet | Decisions + Actions worksheet | Free text
Status | Dropdown | Select the current status of the risk/issue from the dropdown menu | New - Workstream Lead | Open / Ongoing / Closed
Completion Date | Date | When the Status is changed to 'Closed', record the date of this in this field | Risk | dd-mmm-yy
Update / Comments | Narrative | Narrative giving latest updates on the proximity and any changes | New - Workstream Lead | Free text
Decisions and Actions
Decision ID | Unique ID | Unique ID assigned to the decision/action | New - Workstream Lead | DDaT-DEC-000
Decision Origin | Short text | Title of where the decision/action originated - board, workshop, delivery group etc. | New - Workstream Lead | Free text
Decision Raised By | Short text | Title of Programme Area/Workstream that raised the decision/action | New - Workstream Lead | Free text
Type of Decision | Dropdown | Dropdown menu to select if the decision is at Programme or Workstream level | New - Workstream Lead | Programme / Workstream
Decision Title | Short text | Text with the title of the decision | New - Workstream Lead | Free text
Owner | Short text | Name of the decision owner | New - Workstream Lead | Free text
Status | Dropdown | Select the current status of the decision/action from the dropdown menu | New - Workstream Lead | Open / Pending / Closed
Impact | Dropdown | Select the current impact of the decision/action from the dropdown menu | New - Workstream Lead | High / Medium / Low
PRiskrity | Dropdown | Select the current pRiskrity of the decsion/action from the dropdown menu | New - Workstream Lead | Critical / Required / Monitor / Complete
Required Sign-off Board | Short text | Name of the Board at which sign-off on the decsion will be required | New - Workstream Lead | Free text
Date Raised | Date | Date on which the decision/action was raised | New - Workstream Lead | dd-mmm-yy
Date Required | Date | Date by which sign-off of the decision/action is required | New - Workstream Lead | dd-mmm-yy
Date Closed | Date | When the Status is changed to 'Closed', record the date of this in this field | New - Workstream Lead | dd-mmm-yy
Impacted Workstreams / Enabling Capabilities | Short text | Name of the other workstream(s) and Enabling Capability(s) that will be impacted by this decision/action | New - Workstream Lead | Free text
First Key Approval | Short text | Brief detail of the First Key Approval - name, date and result | New - Workstream Lead | Free text
Second Key Approval | Short text | Brief detail of the Second Key Approval - name, date and result | New - Workstream Lead | Free text
Third Key Approval | Short text | Brief detail of the Third Key Approval - name, date and result | New - Workstream Lead | Free text
Change Register
Change ID | Unique ID | Unique ID assigned to the change on the submitted Change Control Form | Change Control Form | DDaT-CHG-000
Status | Dropdown | Select the current status of the change from the dropdown menu | New - Workstream Lead | Open / Pending / Closed
Change Title | Short text | Title assigned to the change on the submitted Change Control Form | Change Control Form | Free text
Change Description | Narrative | Description of the change as used on the Change Control Form | Change Control Form | Free text
Change Author | Short text | Name of the owner of the change, as submitted on the Change Control Form | Change Control Form | Free text
Date Raised | Date | Date on which the change was raised through the submission of the Change Control Form | Change Control Form | dd-mmm-yy
Change Raised By | Short text | Workstream(s) or Business Area(s) that raised the change, as set out on the Change Control Form | Change Control Form | Free text
Required Sign-off Board | Short text | Name of the Board at which sign-off on the change will be required | Change Control Form | Free text
Impacted Areas | Short text | Other Workstream(s) or Business Area(s) that will be impacted by the changed being implemented, as set out on the Change Control Form | Change Control Form | Free text
Date Required | Date | Date by which sign-off of the change is required, as set out on the Change Control Form | Change Control Form | dd-mmm-yy
First Key Approval | Short text | Brief detail of the First Key Approval - name, date and result | Change Control Form | Free text
Second Key Approval | Short text | Brief detail of the Second Key Approval - name, date and result | Change Control Form | Free text
This worksheet provides detailed information on each data field contained in each worksheet and how they are to be completed.

## RAIDS (hidden)
|  | Delivery Summary |  |  |  |  | Workstream Lead |  | Senior Project Manager
Is 25-Jun-21 Go-Live Delivery Date still feasible? |  |  |  |  | Is Dec-21 Go-Live Delivery Date still feasible?
|  | Summary narrative text….. |  |  |  |  | Summary narrative text…..
Green |  |  |  |  | Green
Key Decisions / Actions |  |  |  |  | Key Risks / Issues
ID | Title |  | Description | Required by | Risk ID | Title |  | Description |  | Required by
Key Dependencies |  |  |  |  | Key Assumptions
ID | Title |  | Description | Required by | ID | Title |  | Description |  | Required by

## Day1 Statutory Requirements (hidden)
|  | Day 1 Statutory Requirements - Tech Workstream | [6 empty] | Updated: 18/03/2022
| PLACE | PEOPLE | XXX | XXX | XXX | XXX | XXX | XXX | XXX
Services | e.g. 1. what are the statutory services you will deliver 2. what are the discretionary services you will deliver
Service Delivery | e.g. where does the work get done and who delivers it
Organisational Capabilities | e.g. 1. how will the work get done on day 1? 2. The new approach will be defined and implemented… 3. Where is the line drawn between services/themes (hand-offs?)?
People / Organisation | e.g. 1. Required Regional structures in place 2. There will be vacancies across the model with a plan for filling these? 3. What is the accepted risk level for vetting?
Processes | e.g. 1. Payroll and finance processes updated 2. Inductions to be undertaken for new staff 3. Payment systems in place
Tech | e.g. 1. MVP Digital tools aligned to new regions (M) 2. MVP tools developed, tested and deployed (M) 3. Data migration is ready
Estates / Location | e.g. 1. Transfer from x to y in place 2. Security of buildings meets security specifications 3. Physical layout of buildings meet security specifications
Governance | e.g. 1. Required level of Performance reporting implemented 2. Performance management framework defined and approved 3.Government framework in line with RACI
Users and Stakeholders | e.g. All users and staff will be aware of changes and some will relocate on Day 1

## Day1 Blue Print Requirements (hidden)
|  | Day 1 Blueprint Requirements - Tech Workstream | [6 empty] | Updated: 18/03/2022
| PLACE | PEOPLE | XXX | XXX | XXX | XXX | XXX | XXX | XXX
Services | e.g. 1. what are the statutory services you will deliver 2. what are the discretionary services you will deliver
Service Delivery | e.g. where does the work get done and who delivers it
Organisational Capabilities | e.g. 1. how will the work get done on day 1? 2. The new approach will be defined and implemented… 3. Where is the line drawn between services/themes (hand-offs?)?
People / Organisation | e.g. 1. Required Regional structures in place 2. There will be vacancies across the model with a plan for filling these? 3. What is the accepted risk level for vetting?
Processes | e.g. 1. Payroll and finance processes updated 2. Inductions to be undertaken for new staff 3. Payment systems in place
Tech | e.g. 1. MVP Digital tools aligned to new regions (M) 2. MVP tools developed, tested and deployed (M) 3. Data migration is ready
Estates / Location | e.g. 1. Transfer from x to y in place 2. Security of buildings meets security specifications 3. Physical layout of buildings meet security specifications
Governance | e.g. 1. Required level of Performance reporting implemented 2. Performance management framework defined and approved 3.Government framework in line with RACI
Users and Stakeholders | e.g. All users and staff will be aware of changes and some will relocate on Day 1

## Day1 Blue Print Requirement (2) (hidden)
|  | Day 1 Blueprint Requirements | [7 empty] | Updated: 18/03/2022
|  | Services | Service Delivery | Organisational Capabilities | People / Organisation | Processes | Tech | Estates / Location | Governance | Users and Stakeholders
PROGRAMME THEMES |  | e.g. 1. what are the statutory services you will deliver 2. what are the discretionary services you will deliver | e.g. where does the work get done and who delivers it | e.g. 1. how will the work get done on day 1? 2. The new approach will be defined and implemented… 3. Where is the line drawn between services/themes (hand-offs?)? | e.g. 1. Required Regional structures in place 2. There will be vacancies across the model with a plan for filling these? 3. What is the accepted risk level for vetting? | e.g. 1. Payroll and finance processes updated 2. Inductions to be undertaken for new staff 3. Payment systems in place | e.g. 1. MVP Digital tools aligned to new regions (M) 2. MVP tools developed, tested and deployed (M) 3. Data migration is ready | e.g. 1. Transfer from x to y in place 2. Security of buildings meets security specifications 3. Physical layout of buildings meet security specifications | e.g. 1. Required level of Performance reporting implemented 2. Performance management framework defined and approved 3.Government framework in line with RACI | e.g. All users and staff will be aware of changes and some will relocate on Day 1
PLACE | Workstream 1
Worktream 2
Workstream 3
PEOPLE | Workstream 1
Workstream 2
Workstream 3
ICT | Workstream 1
Workstream 2
Workstream 3
ENABLING / CORPORATE SERVICES | Workstream 1
Workstream 2
Workstream 3
FINANCE | Workstream 1
Workstream 2
Workstream 3

## Day1 Corporate Enablers (hidden)
Day 1 Corporate Enablers
|  | Service offer | Key metrics | IT systems | Customer and channels | Key partners/suppliers | Day 1 service delivery model | Budget/Staffing/Assets Dis/aggregation | Transition following Day 1 | Transformation ambitions | Exceptions | Other notes | Service Delivery | Organisational Capabilities | People / Organisation | Processes | Tech | Estates / Location | Governance | Users and Stakeholders
|  | e.g. 1. what are the statutory services you will deliver 2. what are the discretionary services you will deliver | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. where does the work get done and who delivers it | e.g. 1. how will the work get done on day 1? 2. The new approach will be defined and implemented… 3. Where is the line drawn between services/themes (hand-offs?)? | e.g. 1. Required Regional structures in place 2. There will be vacancies across the model with a plan for filling these? 3. What is the accepted risk level for vetting? | e.g. 1. Payroll and finance processes updated 2. Inductions to be undertaken for new staff 3. Payment systems in place | e.g. 1. MVP Digital tools aligned to new regions (M) 2. MVP tools developed, tested and deployed (M) 3. Data migration is ready | e.g. 1. Transfer from x to y in place 2. Security of buildings meets security specifications 3. Physical layout of buildings meet security specifications | e.g. 1. Required level of Performance reporting implemented 2. Performance management framework defined and approved 3.Government framework in line with RACI | e.g. All users and staff will be aware of changes and some will relocate on Day 1
ENABLING / CORPORATE SERVICES | Workstream 1
Workstream 2
Workstream 3

## Old tab (hidden)
waste requirements (old tab data)
Dependency: Reliance on just one other area to address requirement
Interdependency: Reliance across multiple areas to address requirement
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency (what is required from elsewhere in the programme?) | With | With | With | Interdependency | With | With | With | Comment | Date needed by | Agreed?
e.g. Environment |  |  | e.g. AUDIT-REQ1 | e.g. Out Of Hours Service | e.g. Must have/Should have | xxx | xxx | xxx | xxx | xxx | e.g. Workstream - Organisational Development & Human Resources
Place |  | Waste |  | Staff able to do the job, these will need contracts | Must have | requires support from | Workstream - Organisational Development & Human Resources
Place |  | Waste |  | Be able to dispose of waste | Must have
Place |  | Waste |  | Have appropriate vehicles that are under an O’Licence, insured | Must have | developed together with | Place Theme - Fleet |  |  | has a connection with | Place Theme - Transport
Place |  | Waste |  | Have access to fuel | Must have | has a connection with | Finance - Financial & Commercial Stability
Place |  | Waste |  | Be able to access routes and in cab data exchange | Must have | requires support from | ICT - Service Continuity |  |  | developed together with | ICT - Infrastructure
Place |  | Waste |  | Customer interface in the way residents are used to contacting us now, this may require access to each-others’ systems | Must have | requires support from | Customer & Digital - Website |  |  | developed together with | Customer & Digital - Service Functions | ICT - Service Continuity | ICT - Applications
Place |  | Waste |  | Essential outputs for householders (i.e. Collection calendars) | Must have | requires support from | Workstream - Communications & Engagement
Place |  | Waste |  | Clear lines of management / accountability and ability to redirect resources to support priority services eg from other operational services | Must have | requires support from | Workstream - Organisational Development & Human Resources
Place |  | Waste |  | Priority access to fleet maintenance and support | Must have | requires support from | Place Theme - Fleet |  |  | developed together with | Place Theme - Transport
Place |  | Waste |  | Officers authorised to place orders etc | Must have | developed together with | Finance - Financial & Commercial Stability
Place |  | Waste |  | Team of staff empowered and confident to make decisions | Must have | developed together with | Workstream - Organisational Development & Human Resources
Place |  | Waste |  | Hosted arrangement - Clear transfer of the services which would sit within Host Authority. Staffing, communication routes, Officer/Member governance confirmed. | Must have | requires support from | All Services
Place |  | Waste |  | Waste data collection and submission resourcing and arrangements confirmed (ie. WasteDataFlow). | Must have | developed together with | ICT - Service Continuity |  |  | requires support from | ICT - Applications | ICT - Infrastructure
Place |  | Waste |  | Governance Model | Must have | developed together with | All Services
Place |  | Waste |  | Duly appointed Shareholder Group for AWSL (Governance) and Partnering Board – a contractual requirement | Must have | developed together with | Workstream - Legal & Democratic
Place |  | Waste |  | Methodology for valuing fuel stock for example as at 31/3/23 | Must have | requires support from | Finance - Financial & Commercial Stability
Place |  | Waste |  | IT must work e.g. VPN, in-cab devices, | Must have | requires support from | ICT - Service Continuity |  |  | developed together with | ICT - Technical | ICT - Applications | ICT - Infrastructure
Place |  | Waste |  | DVLA to be advised of vehicle responsibility – Road Fund licence V5 – who will be responsible for taxing the vehicles 1/4/23 | Must have | requires support from | Workstream - Legal & Democratic
Place |  | Waste |  | LOLER – bin lifts/tail lifts - are we using one supplier for Cumberland | Must have | requires further discussion with | Workstream - Strategic Commissioning, Procurement and Contract Management
Place |  | Waste |  | Ability to check licences - internal or external | Must have | requires support from | ICT - Service Continuity
Place |  | Waste |  | Tachograph analysis – RHA/FTA | Must have | requires support from | ICT - Service Continuity
Place |  | Waste |  | Trade Waste Contracts assigned to Cumberland | Must have | developed together with | Workstream - Strategic Commissioning, Procurement and Contract Management
Place |  | Waste |  | Contingency offtakers in Cumberland e.g. bulky waste to Barrow in the past | Must have
Place |  | Waste |  | Decision on AWSL new name if any | Must have
Place |  | Waste |  | Waste Carriers Licence currently in the name of AWSL | Must have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | An understanding about the ownership of CWM | Must have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | Scheme of financial delegation for officers | Must have | requires support from | Finance - Financial & Commercial Stability
Place |  | Waste |  | AWSL, CWM and Tivoli (waste element) contracts assigned to Cumberland | Must have | requires further discussion with | Workstream - Strategic Commissioning, Procurement and Contract Management
Place |  | Waste |  | Portfolio Holder in place | Must have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | Alignment on fees and charges | Must have | requires further discussion with | Finance - Financial & Commercial Stability
Place |  | Waste |  | Staffing and therefore reporting structure to be in place | Must have | requires further discussion with | Workstream - Organisational Development & Human Resources
Place |  | Waste |  | Cumberland branding on RCVs | Must have | requires support from | Workstream - Communications & Engagement
Place |  | Waste |  | Standardisation of Customer Service roles across Cumberland | Must have | requires support from | Workstream - Organisational Development & Human Resources |  |  | developed together with | Customer & Digital - Service Functions
Place |  | Waste |  | Will Cumberland provide H&S advice to AWSL? | Must have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | Will Cumberland provide current SLA services to AWSL? | Must have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | Access to data – ICT systems/Sharepoint | Must have | requires support from | ICT - Service Continuity |  |  | developed together with | ICT - Applications | ICT - Architecture
Place |  | Waste |  | Waste, Green Waste & Recycling collections - Front-line services must happen on day one as they did in March 2022 | Must have | requires support from | All Services
Place |  | Waste |  | Vehicles must be legal & safe. Must be insured, serviced & MoT’d. | Must have | requires support from | Workstream - Legal & Democratic
Place |  | Waste |  | Fuel - Fuel cards or supplies must be available for vehicles | Must have | requires support from | Finance - Financial & Commercial Stability
Place |  | Waste |  | Insurance - Vehicles must be insured | Must have | requires support from | Workstream - Legal & Democratic
Place |  | Waste |  | Vehicle Accident Packs - Must be up-dated with new insurance details etc | Must have | requires support from | Workstream - Legal & Democratic
Place |  | Waste |  | Bring site emptying - Recycling banks must be emptied. | Must have
Place |  | Waste |  | Waste disposal - Transfer Stations must be open and accepting materials | Must have | developed together with | Workstream - Organisational Development & Human Resources
Place |  | Waste |  | Environmental Permits for Ecclerigg & Ulverston Waste Transfer Stations - Must be transferred to WandF. May be covered by the Change Order. Possible joint meeting with CCC, EDC, BBC & EA to resolve. | Must have | requires support from | Workstream - Legal & Democratic
Place |  | Waste |  | Staff - We must have staff in place, paid, covered by insurance, qualified to do their jobs. | Must have | requires support from | Workstream - Organisational Development & Human Resources
Place |  | Waste |  | Sickness & Holidays - Must be in place for non-desk-based staff. | Must have | requires support from | Workstream - Organisational Development & Human Resources |  |  | requires further discussion with | Finance - Financial & Commercial Stability
Place |  | Waste |  | Credit cards - As required, for emergency use. Possibly retain pre-WaF cards. | Must have | requires support from | Finance - Financial & Commercial Stability
Place |  | Waste |  | IT systems - Laptops and phone must work. | Must have | requires support from | ICT - Service Continuity |  |  | developed together with | ICT - Technical | ICT - Infrastructure | ICT - Applications
Place |  | Waste |  | Software - Core MS Office systems must work. Content must have transferred. Any specific systems must work. | Must have | requires support from | ICT - Service Continuity |  |  | developed together with | ICT - Technical | ICT - Infrastructure | ICT - Applications
Place |  | Waste |  | Utilities - All depots & buildings must have gas, electric, water etc. | Must have | developed together with | Workstream - Strategic Commissioning, Procurement and Contract Management |  |  | requires support from | Finance - Financial & Commercial Stability
Place |  | Waste |  | Payroll - Processes in place to pay staff and process overtime or other claims. | Must have | requires support from | Workstream - Organisational Development & Human Resources |  |  | developed together with | Finance - Financial & Commercial Stability | Finance - Dissaggregation of Budgets | Finance - Creation of Balance Sheets
Place |  | Waste |  | Communications - Staff and the public must know what is going on. May require access to each other's systems | Must have | requires support from | Customer & Digital - Service Functions |  |  | developed together with | ICT - Service Continuity | ICT - Infrastructure
Place |  | Waste |  | Website - Website content must be transferred & checked. Collection information (calendars) must be available. | Must have | requires support from | Customer & Digital - Website |  |  | developed together with | ICT - Service Continuity
Place |  | Waste |  | Processes - Systems must be in place to log missed collections, bin requests and queries; and allocate to the correct operational area. | Must have | requires support from | ICT - Service Continuity |  |  | developed together with | ICT - Infrastructure | ICT - Architecture | ICT - Applications
Place |  | Waste |  | Bulky waste - Requests must be received and forwarded to the correct contractor. | Must have | requires support from | Customer & Digital - Service Functions |  |  | developed together with | ICT - Service Continuity
Place |  | Waste |  | Clinical waste - Requests must be received and forwarded to the correct contractor. | Must have | requires support from | Customer & Digital - Service Functions |  |  | developed together with | ICT - Service Continuity
Place |  | Waste |  | Hosted arrangement - Clear transfer of the services which would sit within Host Authority. Staffing, communication routes, Officer/Member governance confirmed. | Must have | requires support from | Workstream - Legal & Democratic
Place |  | Waste |  | Waste data collection and submission resourcing and arrangements confirmed (ie. WasteDataFlow). | Must have | developed together with | ICT - Service Continuity
Place |  | Waste |  | Branded Calendars are essential from day one | Must have | requires support from | Workstream - Communications & Engagement
Place |  | Waste |  | Clear lines of Management and accountability – to be able to redirect resources if needed | Must have | requires support from | Workstream - Organisational Development & Human Resources
Place |  | Waste |  | Waste Carrier License's | Must have | requires support from | Workstream - Legal & Democratic
Place |  | Waste |  | Understanding ownership of CWM | Must have | requires support from | Workstream - Legal & Democratic
Place |  | Waste |  | Contract assigned to a correct legal entity – mechanism to be agreed (legal advice required) | Must have | requires support from | Workstream - Strategic Commissioning, Procurement and Contract Management |  |  | developed together with | Workstream - Legal & Democratic
Place |  | Waste |  | Authority representative to be agreed and Governance between Contractor and Authorities | Must have | requires support from | Workstream - Legal & Democratic |  |  | developed together with | Workstream - Strategic Commissioning, Procurement and Contract Management
Place |  | Waste |  | Up to date Authorised Vehicle List for new authorities – AVL to ensure no end dates of 31 March/April 2023 | Must have | requires support from | Place Theme - Fleet |  |  | developed together with | Place Theme - Transport | Workstream - Legal & Democratic
Place |  | Waste |  | New authorities to understand AVL procedure | Must have | requires support from | Workstream - Legal & Democratic
Place |  | Waste |  | Agreed process for updating and issuing AVL (currently CCC Service Centre) | Must have | requires support from | Workstream - Legal & Democratic
Place |  | Waste |  | Waste transfer notes for the 2 authorities | Must have | developed together with | Workstream - Strategic Commissioning, Procurement and Contract Management
Place |  | Waste |  | Agreement on HWRC permit system – is it run by one authority or 2? | Must have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | Agreement on use of HWRCs – can all residents use all sites in Cumberland and Westmorland and Furness? | Must have | requires support from | Workstream - Assets |  |  | developed together with | Workstream - Strategic Commissioning, Procurement and Contract Management
Place |  | Waste |  | Agree scope of Helpline and contact arrangements – confirm telephone number, training for helpline team. | Must have | requires support from | Workstream - Strategic Commissioning, Procurement and Contract Management |  |  | developed together with | Customer & Digital - Service Functions | Customer & Digital - Strategy
Place |  | Waste |  | Reporting lines to be communicated to RCL | Must have
Place |  | Waste |  | Agreement to pay CCC invoices for the period to 31 March 2023 and new authorities from 01 April 2023 | Must have | requires further discussion with | Finance - Financial & Commercial Stability |  |  | developed together with | Finance - Creation of Balance Sheets
Place |  | Waste |  | Inter Authority Agreement in place to process payments | Must have | requires support from | Finance - Financial & Commercial Stability |  |  | requires support from | Workstream - Strategic Commissioning, Procurement and Contract Management
Place |  | Waste |  | How to deal with CCC legacy issues: Accrual/provision | Must have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | Responsibilities for Waste Data Flow to be agreed between new authorities (currently districts for recycling/bring sites and CCC for residua) | Must have | requires support from | ICT - Service Continuity |  |  | developed together with | ICT - Applications | All Services
Place |  | Waste |  | Budgets to be set | Must have | requires support from | Finance - Dissaggregation of Budgets |  |  | developed together with | Finance - Financial & Commercial Stability
Place |  | Waste |  | Access to data – ICT systems/Sharepoint | Must have | requires support from | ICT - Service Continuity |  |  | requires support from | ICT - Infrastructure | ICT - Applications | ICT - Infrastructure
Place |  | Waste |  | Bulky waste collection | Should have
Place |  | Waste |  | Charges for replacement receptacles | Should have | requires support from | Finance - Financial & Commercial Stability |  |  | requires support from | Workstream - Communications & Engagement
Place |  | Waste |  | Consistency in uniform / PPE / badging etc | Should have | requires support from | Workstream - Communications & Engagement
Place |  | Waste |  | Vehicle livery | Should have | requires support from | Place Theme - Fleet
Place |  | Waste |  | Single approach to recruitment, selection and training of new staff starting from 01 April 2023 on common T+Cs, salaries etc | Should have | requires support from | Workstream - Organisational Development & Human Resources
Place |  | Waste |  | Consistency in policies and procedures i.e. assisted collections, collection of side waste, missed collections | Should have | requires support from | Workstream - Legal & Democratic |  |  | developed together with | Workstream - Strategic Commissioning, Procurement and Contract Management
Place |  | Waste |  | Combined service budgets – clear lines of responsibility | Should have | requires support from | Finance - Dissaggregation of Budgets |  |  | has a connection with | Finance - Financial & Commercial Stability
Place |  | Waste |  | Office locations agreed | Should have | requires support from | Workstream - Assets |  |  | developed together with | Finance - Financial & Commercial Stability
Place |  | Waste |  | Agreed trade tipping rates | Should have | developed together with | Finance - Financial & Commercial Stability
Place |  | Waste |  | Better understanding of Renewi policies that effect the waste collection element of Cumberland | Should have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | Agreement on how to handle complaints and FOIs | Should have | requires further discussion with | Customer & Digital - Strategy |  |  | developed together with | Customer & Digital - Service Functions
Place |  | Waste |  | Data - Systems should be in place to record data for the new authority. Must happen by end 1st month. | Should have | developed together with | ICT - Service Continuity |  |  | requires support from | ICT - Infrastructure | ICT - Applications | ICT - Architecture
Place |  | Waste |  | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have | requires support from | Workstream - Legal & Democratic |  |  | developed together with | Workstream - Organisational Development & Human Resources | Workstream - Strategic Commissioning, Procurement and Contract Management | Workstream - Communications & Engagement
Place |  | Waste |  | A better understanding of the contract for the Disposal element of the work | Should have | requires further discussion with | Workstream - Strategic Commissioning, Procurement and Contract Management
Place |  | Waste |  | Consistency in salaries for operational staff – supervisors / loaders / drivers etc | Could have | requires support from | Workstream - Organisational Development & Human Resources
Place |  | Waste |  | Potential to share resources eg at management / supervisory level | Could have | requires further discussion with | Workstream - Organisational Development & Human Resources
Place |  | Waste |  | Potential to share vehicles and other resources | Could have | requires further discussion with | Place Theme - Fleet |  |  | has a connection with | Place Theme - Transport
Place |  | Waste |  | Agreed position towards membership of national sector organisations and agreement on first point of contact (ie. LARAC, NAWDO, etc) | Could have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | A move towards consistency of IT use | Could have | requires further discussion with | ICT - Service Continuity |  |  | developed together with | ICT - Infrastructure
Place |  | Waste |  | An understanding about how current trade waste contracts could possibly be transferred to CWM | Could have | requires further discussion with | Workstream - Strategic Commissioning, Procurement and Contract Management |  |  | requires support from | Workstream - Legal & Democratic
Place |  | Waste |  | Standardised H&S procedures e.g. near misses, gate checks, seat belt checks, crew engagement, safety reps | Could have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | ICT – access to Scada system for closed landfill | Could have | requires support from | ICT - Service Continuity |  |  | developed together with | ICT - Infrastructure | ICT - Applications
Place |  | Waste |  | What will permit scheme look like? Pedestrian and Annual Permits? | Could have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | Policies - Existing policies transfer by area. Some policies could have been aligned (closed lid, side waste, lane end). | Could have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | Processes - Some processes could be aligned (assisted collections, requests for larger bins). | Could have
Place |  | Waste |  | National Waste Strategy - Depends on timing of announcement and required actions. | Could have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | Re-branding of PPE - Some could have been done. Potential for hybrid clothing (SLDC fleece, WaF coat etc). | Could have | requires further discussion with | Workstream - Communications & Engagement
Place |  | Waste |  | Agreed position towards membership of national sector organisations and agreement on first point of contact (ie. LARAC, NAWDO, etc) | Could have
Place |  | Waste |  | H&S and Performance, how that is monitored within Westmorland and Furness | Could have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | Awareness training for all waste service employees | Could have | requires support from | Workstream - Organisational Development & Human Resources
Place |  | Waste |  | Environment Agency Permit transfer/UU discharge consents to legal entity (is there a requirement to apply or is this covered by the SCO?) | Could have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | Ability to pay EA subsistence fees for closed landfill from 01 April 2023 | Could have | requires support from | Finance - Financial & Commercial Stability |  |  | requires further discussion with | Workstream - Strategic Commissioning, Procurement and Contract Management
Place |  | Waste |  | DCF registration – currently CWM | Could have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | Approach to branding strategy to be agreed and position on Performance Framework to be set out (eg how long CCC branding can remain in place before deductions apply) signs and PPE for site operatives | Could have | requires further discussion with | Workstream - Legal & Democratic |  |  | developed together with | Workstream - Communications & Engagement
Place |  | Waste |  | Agreement on paying royalty/rents – currently sitting with waste team | Could have | requires further discussion with | Finance - Financial & Commercial Stability |  |  | developed together with | Finance - Creation of Balance Sheets | Finance - Dissaggregation of Budgets
Place |  | Waste |  | New authorities to brief CWM site operatives – clear and unambiguous message about what the changes mean for the HWRC sites and customers | Could have | requires further discussion with | Workstream - Organisational Development & Human Resources |  |  | developed together with | Workstream - Legal & Democratic
Place |  | Waste |  | Commercial gate fees to be agreed with new authorities (currently only Copeland and Allerdale) | Could have | requires further discussion with | Finance - Financial & Commercial Stability |  |  | has a connection with | Finance - Dissaggregation of Budgets
Place |  | Waste |  | Agreement on policies eg charities, side waste | Could have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | Schedule of assets for the new authorities (MBT, HWRC, closed landfill) | Could have | requires support from | Workstream - Assets
Place |  | Waste |  | ICT – access to Scada system for closed landfill | Could have | requires support from | ICT - Service Continuity |  |  | has a connection with | ICT - Applications
Place |  | Waste |  | What will permit scheme look like? Pedestrian and Annual Permits? | Could have | requires further discussion with | Workstream - Legal & Democratic |  |  | has a connection with | Customer & Digital - Strategy
Place |  | Waste |  | Consistency in service standards | Won't have | requires further discussion with | Place Theme - Waste
Place |  | Waste |  | Consistency in service design | Won't have | requires further discussion with | Place Theme - Waste
Place |  | Waste |  | Consistency towards commercial waste collections | Won't have | requires further discussion with | Place Theme - Waste
Place |  | Waste |  | Waste and Recycling policy alignment | Won't have | requires further discussion with | Place Theme - Waste
Place |  | Waste |  | Consistency in collection frequency | Won't have | requires further discussion with | Place Theme - Waste
Place |  | Waste |  | Consistency in container type and size | Won't have | requires further discussion with | Place Theme - Waste
Place |  | Waste |  | Depot rationalisation/location | Won't have | requires support from | Workstream - Assets |  |  | developed together with | Place Theme - Waste
Place |  | Waste |  | Re-routing and re-rounding following removal of boundaries | Won't have | requires further discussion with | Place Theme - Waste
Place |  | Waste |  | Efficient direct delivery from the North of Allerdale to Hespin Wood but could have! | Won't have | requires further discussion with | Place Theme - Waste
Place |  | Waste |  | Decision on in-house v LATCo model | Won't have | requires further discussion with | Place Theme - Waste
Place |  | Waste |  | Opportunity to rationalise/standardise Bring Banks | Won't have | requires support from | Workstream - Assets
Place |  | Waste |  | Consistency in service standards | Won't have | requires further discussion with | Place Theme - Waste
Place |  | Waste |  | Consistency in service design | Won't have | requires further discussion with | Place Theme - Waste
Place |  | Waste |  | Consistency towards commercial waste collections | Won't have | requires further discussion with | Place Theme - Waste
Place |  | Waste |  | Re-branding of bins & boxes - Not urgent, can be done as new items, bins etc are ordered. | Won't have | requires support from | Workstream - Communications & Engagement
Place |  | Waste |  | Re-branding of vehicles - Not urgent, can be done as new vehicles are ordered or as prioritised. | Won't have | requires support from | Workstream - Communications & Engagement
Place |  | Waste |  | In-cab systems - Too complex to introduce by day 1. | Won't have | requires further discussion with | ICT - Service Continuity |  |  | has a connection with | ICT - Applications | ICT - Technical | ICT - Infrastructure
Place |  | Waste |  | Round changes - Any round or route changes must be embedded by December 2022. | Won't have | requires further discussion with | Place Theme - Waste
Place |  | Waste |  | Waste and Recycling Policy alignment and Consistency in collection frequency and containers | Won't have | requires further discussion with | Place Theme - Waste
Place |  | Waste |  | Reviewed Bring Sites within Westmorland and Furness | Won't have | requires further discussion with | Workstream - Assets
Place |  | Waste |  | Agreement on enforcement powers, eg suspected trade waste abuse at HWRCs | Won't have | requires further discussion with | Workstream - Legal & Democratic
Place |  | Waste |  | New HWRC permit scheme | Won't have | requires further discussion with | Workstream - Strategic Commissioning, Procurement and Contract Management

## Day1 Reqs&Depends (CE)
Day1 Requirements & Inter/Dependencies (Corporate and Enabling Services)
|  |  |  | DEFINITIONS: |  |  |  | KEY FOR COMMENTS SECTION:
|  |  |  | Dependency: Reliance on just one other area to address requirement |  |  |  | Needs double checking with department
|  |  |  | Interdependency: Reliance across multiple areas to address requirement |  |  |  | Gaps within the data
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency (what is required from elsewhere in the programme?) | Interdependency (numerous interdependencies from elsewhere in the programme) | With | Comment | Date needed by | Approved?
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ1 | Statutory compliance with: FOIA 2000/ EIR 2004/ DPA 2018/ UK GDPR - Data Protection Reform/ Public Records Act 58/67. INSPIRE Regulations / the Re-use of Public Sector Information Regulations 2015 (RPSI). NHS & Local Authority 2009 Care Act. Mental Capacity Consent '3ps' | Must have |  | needs to agree with approach and be able to apply | Information Governance
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ1 | Statutory compliance with: FOIA 2000/ EIR 2004/ DPA 2018/ UK GDPR - Data Protection Reform/ Public Records Act 58/67. INSPIRE Regulations / the Re-use of Public Sector Information Regulations 2015 (RPSI). NHS & Local Authority 2009 Care Act. Mental Capacity Consent '3ps' | Must have |  | needs to agree with approach and be able to apply | Records Management work package
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ1 | Statutory compliance with: FOIA 2000/ EIR 2004/ DPA 2018/ UK GDPR - Data Protection Reform/ Public Records Act 58/67. INSPIRE Regulations / the Re-use of Public Sector Information Regulations 2015 (RPSI). NHS & Local Authority 2009 Care Act. Mental Capacity Consent '3ps' | Must have |  | support the compliance through online means and wider communication | Customer & Digital
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ1 | Statutory compliance with: FOIA 2000/ EIR 2004/ DPA 2018/ UK GDPR - Data Protection Reform/ Public Records Act 58/67. INSPIRE Regulations / the Re-use of Public Sector Information Regulations 2015 (RPSI). NHS & Local Authority 2009 Care Act. Mental Capacity Consent '3ps' | Must have |  | needs to agree with the requirements of the community | Community/Localism
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ1 | Statutory compliance with: FOIA 2000/ EIR 2004/ DPA 2018/ UK GDPR - Data Protection Reform/ Public Records Act 58/67. INSPIRE Regulations / the Re-use of Public Sector Information Regulations 2015 (RPSI). NHS & Local Authority 2009 Care Act. Mental Capacity Consent '3ps' | Must have |  | the policy needs communicating with | All services - all employees
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ2 | Data Protection Officer as SPOC for Information Commissioner Office | Must have |  | how the information is managed/ communicated to the officer | Information Governance
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ2 | Data Protection Officer as SPOC for Information Commissioner Office | Must have |  | how the information is managed/ communicated to the officer | Records Management work package
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ2 | Data Protection Officer as SPOC for Information Commissioner Office | Must have |  | support the officer through online means and wider communication | Customer & Digital
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ2 | Data Protection Officer as SPOC for Information Commissioner Office | Must have |  | needs to agree with the requirements of the community | Community/Localism
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ2 | Data Protection Officer as SPOC for Information Commissioner Office | Must have |  | need to communicate who the SPOC is | All services - all employees
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ3 | Ensuring registration with Information Commissioner | Must have | requires registration |  | FOI/SAR, Comments, Compliments & Complaints
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ4 | Dealing directly with the Local Government and Social Care Ombudsman | Must have | works with |  | Social Care Brokerage
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ5 | Publishing information and data sets under a Publication Scheme/INSPIRE/RPS | Must have | publish information |  | FOI/SAR, Comments, Compliments & Complaints
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ6 | Ensuring the Complaints Policies and Information Governance Framework are complied with | Must have | to ensure policies and frameworks are adhered to |  | Information Governance
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ7 | Advising on Data Protection | Must have | to ensure policies and frameworks are adhered to |  | Information Governance
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ8 | Responding to complaints and requests | Must have | to communicate with the relevent people |  | Customer & Digital
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ9 | Ability to make a request for rectification, erasure, restriction, portability of your data under the General Data Protection Regulations (GDPR) Ability to make requests for CCTV footage Ability to report data breaches | Must have | needs to agree with approach and be able to apply |  | Information Governance
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ10 | FOI request form | Must have
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ11 | Disclosure Log | Must have
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ12 | Access to digital and hard records | Must have | requires collaboration to access records |  | Records Management work package
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ13 | SAR Process | Must have |  | requires collaboration to access records | Records Management work package
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ13 | SAR Process | Must have |  | requires collaboration to communicate with relevant stakeholders the process | Customer & Digital
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ14 | Agree a complaints process. Define scope, stages, escalation, timescales and limitations. | Must have |  | requires collaboration to access records for definition of scope, etc | Records Management work package
Corporate and Enabling Services |  | FOI/SAR, Comments, Compliments & Complaints | FOI-REQ14 | Agree a complaints process. Define scope, stages, escalation, timescales and limitations. | Must have |  | requires collaboration to communicate with relevant stakeholders the scope, etc | Customer & Digital
Total Day 1 Requirements for: FOI/SAR, Comments, Compliments, Complaints = 14 Total inter/dependencies for: FOI/SAR, Comments, Compliments, Complaints = 24
Corporate and Enabling Services |  | Health & Safety | H&S-REQ1 | Policy - Corporate H&S Policy. Need to be brought to the attention of all the employees as per the H&S at work act | Must have |  | is interdependent as the policy needs communicating to | All services - all employees
Corporate and Enabling Services |  | Health & Safety | H&S-REQ1 | Policy - Corporate H&S Policy. Need to be brought to the attention of all the employees as per the H&S at work act | Must have |  | needs approval from | LGR Leadership/Board | Reliance on Senior Management Team of new Council e.g. DMT/ CMT/ Leader / Portfolio Holder H&S CEO/ Executive Cabinet/ H&S Service
Corporate and Enabling Services |  | Health & Safety | H&S-REQ2 | The team - Access to sufficient resources for competent health and safety advice both general and “industry specific competence” depending on service or service areas | Must have |  | is interdependent as the training needs communicating to | All services - all employees
Corporate and Enabling Services |  | Health & Safety | H&S-REQ2 | The team - Access to sufficient resources for competent health and safety advice both general and “industry specific competence” depending on service or service areas | Must have |  | needs access to resources | HR & OD
Corporate and Enabling Services |  | Health & Safety | H&S-REQ2 | The team - Access to sufficient resources for competent health and safety advice both general and “industry specific competence” depending on service or service areas | Must have |  | needs help delivering the advice and training | Learning & Development
Corporate and Enabling Services |  | Health & Safety | H&S-REQ2 | The team - Access to sufficient resources for competent health and safety advice both general and “industry specific competence” depending on service or service areas | Must have |  | needs help communicating the resources to employees |  | Remaining interdependencies to map to a workstream: Employee Engagement Group / Specific Service
Corporate and Enabling Services |  | Health & Safety | H&S-REQ3 | The team - Review of health and safety resources (in terms of current workforce) | Must have |  | is interdependent as the resources need communicating to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ3 | The team - Review of health and safety resources (in terms of current workforce) | Must have |  | ensure the resources are relevant and can be used to train staff | Learning & Development
Corporate and Enabling Services |  | Health & Safety | H&S-REQ3 | The team - Review of health and safety resources (in terms of current workforce) | Must have |  | need to assist the review of the resources | HR & OD
Corporate and Enabling Services |  | Health & Safety | H&S-REQ3 | The team - Review of health and safety resources (in terms of current workforce) | Must have |  | needs approval from | LGR Leadership/Board
Corporate and Enabling Services |  | Health & Safety | H&S-REQ4 | Reporting/Recording - Agreed mechanisms for accident and incident reporting, recording and investigation | Must have |  | is interdependent as the agreed mechanisms for reporting/recording need communicating to | All services - all employees
Corporate and Enabling Services |  | Health & Safety | H&S-REQ4 | Reporting/Recording - Agreed mechanisms for accident and incident reporting, recording and investigation | Must have |  | help facilitate the IT systems needed for reporting/recording | ICT
Corporate and Enabling Services |  | Health & Safety | H&S-REQ4 | Reporting/Recording - Agreed mechanisms for accident and incident reporting, recording and investigation | Must have |  | requires support from | Trade Union | Remaining interdependencies to map to a workstream: H&S Executive
Corporate and Enabling Services |  | Health & Safety | H&S-REQ5 | Assessing Hazards – Controlling Risk - Agreed arrangements for the provisions of suitable and sufficient risk assessment, risk controls and PPE | Must have |  | risk assessment needs communicating to | All services - all employees
Corporate and Enabling Services |  | Health & Safety | H&S-REQ5 | Assessing Hazards – Controlling Risk - Agreed arrangements for the provisions of suitable and sufficient risk assessment, risk controls and PPE | Must have |  | needs help developing the risk and hazard assessment and regulation | Legal & Democratic Services | It just said L&D - assuming it's learning and development rather than legal and democratic?
Corporate and Enabling Services |  | Health & Safety | H&S-REQ5 | Assessing Hazards – Controlling Risk - Agreed arrangements for the provisions of suitable and sufficient risk assessment, risk controls and PPE | Must have |  | requires tech support | ICT
Corporate and Enabling Services |  | Health & Safety | H&S-REQ5 | Assessing Hazards – Controlling Risk - Agreed arrangements for the provisions of suitable and sufficient risk assessment, risk controls and PPE | Must have |  | communications on the engagement on safe systems of work | Communications and Engagement | Include H&S responsibilities in Job / Role Descriptions
Corporate and Enabling Services |  | Health & Safety | H&S-REQ6 | Training and Development - Ensuring the provisions of suitable and sufficient information, Instruction, training and supervision for employees specific to their area of work / working environment | Must have |  | training needs communicating to | All services - all employees
Corporate and Enabling Services |  | Health & Safety | H&S-REQ6 | Training and Development - Ensuring the provisions of suitable and sufficient information, Instruction, training and supervision for employees specific to their area of work / working environment | Must have |  | training needs development with | Learning & Development
Corporate and Enabling Services |  | Health & Safety | H&S-REQ6 | Training and Development - Ensuring the provisions of suitable and sufficient information, Instruction, training and supervision for employees specific to their area of work / working environment | Must have |  | requires support from | HR & OD
Corporate and Enabling Services |  | Health & Safety | H&S-REQ6 | Training and Development - Ensuring the provisions of suitable and sufficient information, Instruction, training and supervision for employees specific to their area of work / working environment | Must have |  | deployment of the training via tech infrastructure | ICT
Corporate and Enabling Services |  | Health & Safety | H&S-REQ6 | Training and Development - Ensuring the provisions of suitable and sufficient information, Instruction, training and supervision for employees specific to their area of work / working environment | Must have |  | training information and instructions need communicating to employees | Communications and Engagement
Corporate and Enabling Services |  | Health & Safety | H&S-REQ6 | Training and Development - Ensuring the provisions of suitable and sufficient information, Instruction, training and supervision for employees specific to their area of work / working environment | Must have |  | requires support from | Trade Unions
Corporate and Enabling Services |  | Health & Safety | H&S-REQ7 | The team - First Aid / Fire Safety Provisions – Equipment, training, appointed First Aid Persons | Must have |  | requires training collaboration with | Learning & Development | It just said L&D - assuming it's learning and development rather than legal and democratic?
Corporate and Enabling Services |  | Health & Safety | H&S-REQ7 | The team - First Aid / Fire Safety Provisions – Equipment, training, appointed First Aid Persons | Must have |  | requires approval from | HR & OD
Corporate and Enabling Services |  | Health & Safety | H&S-REQ7 | The team - First Aid / Fire Safety Provisions – Equipment, training, appointed First Aid Persons | Must have |  | equipment and training needs budgeting | Finance
Corporate and Enabling Services |  | Health & Safety | H&S-REQ7 | The team - First Aid / Fire Safety Provisions – Equipment, training, appointed First Aid Persons | Must have |  | appointed first aiders/training needs communicating to | All services - all employees | Is there a Competent assessor to ensure employees are Swepd? Could this be Outsourced?
Corporate and Enabling Services |  | Health & Safety | H&S-REQ7 | The team - First Aid / Fire Safety Provisions – Equipment, training, appointed First Aid Persons | Must have |  | needs to adhere to fire safety policies | Policy Framework | Remaining interdependencies to map to a workstream: Facilities
Corporate and Enabling Services |  | Health & Safety | H&S-REQ8 | Governance - Compliant workplace and welfare facilities | Must have |  | facilities need communicating to | All services - all employees
Corporate and Enabling Services |  | Health & Safety | H&S-REQ8 | Governance - Compliant workplace and welfare facilities | Must have |  | requires collaboration to arrange the facilities | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Health & Safety | H&S-REQ8 | Governance - Compliant workplace and welfare facilities | Must have |  | needs to adhere to workplace and welfare regulations | Legal & Democratic Services
Corporate and Enabling Services |  | Health & Safety | H&S-REQ8 | Governance - Compliant workplace and welfare facilities | Must have |  | requires support from | Contract Management/Monitoring | Contractors - is 'contract management/monitoring' the right workstream?
Corporate and Enabling Services |  | Health & Safety | H&S-REQ8 | Governance - Compliant workplace and welfare facilities | Must have |  |  |  | Remaining interdependencies to map to a workstream: Facilities
Corporate and Enabling Services |  | Health & Safety | H&S-REQ9 | The team - Agreed consultation mechanisms in place (workers and their TU H&S representatives) | Must have |  | needs to agree consultation mechanisms within the department | Health & Safety
Corporate and Enabling Services |  | Health & Safety | H&S-REQ9 | The team - Agreed consultation mechanisms in place (workers and their TU H&S representatives) | Must have |  | mechanisms need communicating to | All services - all employees
Corporate and Enabling Services |  | Health & Safety | H&S-REQ9 | The team - Agreed consultation mechanisms in place (workers and their TU H&S representatives) | Must have |  | requires development with | Trade Unions | Trade Unions Portfolio Holder H&S / Trade Union members
|  | Health & Safety | H&S-REQ9 | The team - Agreed consultation mechanisms in place (workers and their TU H&S representatives) | Must have |  | needs approval from | LGR Leadership/Board
Corporate and Enabling Services |  | Health & Safety | H&S-REQ10 | Delivery model - Statutory Health Surveillance for employees – Requirement specific to nature of work | Must have |  | health surveillance for employees | All services - all employees
Corporate and Enabling Services |  | Health & Safety | H&S-REQ10 | Delivery model - Statutory Health Surveillance for employees – Requirement specific to nature of work | Must have |  |  |  | Remaining interdependencies to map to a workstream: OCH / Podiatry, Physio (third parties)
Corporate and Enabling Services |  | Health & Safety | H&S-REQ11 | Delivery model - Robust contractor procurement and safety management systems | Must have |  | safety management systems need communicating to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ11 | Delivery model - Robust contractor procurement and safety management systems | Must have |  | needs collaboration with | Strategic Procurement / Strategy​ | Check this workstream
Corporate and Enabling Services |  | Health & Safety | H&S-REQ11 | Delivery model - Robust contractor procurement and safety management systems | Must have |  | requires approval from | LGR PMO | Project managers / CDM managers / facilities / Locality Services ie Customer Connect. Could be specific Case Manager?
Corporate and Enabling Services |  | Health & Safety | H&S-REQ12 | Assessing risk - Arrangements for Statutory Inspections / Compliance | Must have |  | inspections/compliance information needs communicating to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ12 | Assessing risk - Arrangements for Statutory Inspections / Compliance | Must have |  | needs to adhere to regulation | Legal & Democratic Services
Corporate and Enabling Services |  | Health & Safety | H&S-REQ12 | Assessing risk - Arrangements for Statutory Inspections / Compliance | Must have |  | requires collaboration with | Contract Management/Monitoring | Contractors - is 'contract management/monitoring' the right workstream?
Corporate and Enabling Services |  | Health & Safety | H&S-REQ12 | Assessing risk - Arrangements for Statutory Inspections / Compliance | Must have |  | need support organising the inspections | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Health & Safety | H&S-REQ12 | Assessing risk - Arrangements for Statutory Inspections / Compliance | Must have |  |  |  | Remaining interdependencies to map to a workstream: Insurance / Facilities ie Managers and Services and who arrange maintenance schedules
Corporate and Enabling Services |  | Health & Safety | H&S-REQ13 | The team - Provision of specifically assigned “Competent Persons” | Must have |  | identity of 'competent persons' needs communicating to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ13 | The team - Provision of specifically assigned “Competent Persons” | Must have |  | requires support from | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Health & Safety | H&S-REQ13 | The team - Provision of specifically assigned “Competent Persons” | Must have |  |  |  | Remaining interdependencies to map to a workstream: Dock board / CCC Resilience unit / LR forum
Corporate and Enabling Services |  | Health & Safety | H&S-REQ14 | Assessing risks - Approval and notification service for Educational Visits | Must have |  | educational visit dates need communicating to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ14 | Assessing risks - Approval and notification service for Educational Visits | Must have |  | the organisation of the visits requires tech infrastructure | ICT
Corporate and Enabling Services |  | Health & Safety | H&S-REQ14 | Assessing risks - Approval and notification service for Educational Visits | Must have |  | requires help arranging the location approval | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Health & Safety | H&S-REQ14 | Assessing risks - Approval and notification service for Educational Visits | Must have |  | needs organising with schools | Children's | Schools
Corporate and Enabling Services |  | Health & Safety | H&S-REQ15 | Assessing risks - Basic statutory compliance | Must have |  | statutory compliance needs communicating to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ15 | Assessing risks - Basic statutory compliance | Must have |  | requires support from | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Health & Safety | H&S-REQ15 | Assessing risks - Basic statutory compliance | Must have |  | H&S carrying out audits on buildings | Audit | Is audit correct? Was listed as an interdependency on: 'H&S carrying out audits on buildings'
Corporate and Enabling Services |  | Health & Safety | H&S-REQ16 | Governance - Corporate Insurance | Must have |  | corporate insurance information needs communicating to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ16 | Governance - Corporate Insurance | Must have |  | corporate insurance needs to adhere to regulation | Legal & Democratic Services
Corporate and Enabling Services |  | Health & Safety | H&S-REQ16 | Governance - Corporate Insurance | Must have |  | insurance needs budgeting | Finance
Corporate and Enabling Services |  | Health & Safety | H&S-REQ16 | Governance - Corporate Insurance | Must have |  | requires collaboration with | HR & OD
Corporate and Enabling Services |  | Health & Safety | H&S-REQ17 | Governance - Outline plan for accountability and lead for H&S Governance for the new authorities and establishment of management structures (e.g. H&S Management Board/Group) | Should have |  | accountability plan and H&S lead for the new authorities needs communicating to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ17 | Governance - Outline plan for accountability and lead for H&S Governance for the new authorities and establishment of management structures (e.g. H&S Management Board/Group) | Should have |  | requires approval from | LGR Leadership/Board | Senior manager / portfolio holder / senior leadership team / cabinet members / service managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ18 | The team - Portfolio holder for H & S - Council Members H & S understanding of their roles with regards to H&S | Should have |  | identity of portfolio holder needs communicating to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ18 | The team - Portfolio holder for H & S - Council Members H & S understanding of their roles with regards to H&S | Should have |  | training required to understand roles with regards to H&S | Learning & Development | It just said L&D - assuming it's learning and development rather than legal and democratic?
Corporate and Enabling Services |  | Health & Safety | H&S-REQ18 | The team - Portfolio holder for H & S - Council Members H & S understanding of their roles with regards to H&S | Should have |  | requires approval and communication support with | LGR Leadership/Board | Democratic service / senior officer to support them / senior management lead
Corporate and Enabling Services |  | Health & Safety | H&S-REQ19 | The team - Structural knowledge by Senior Team, Council Members, Manage | Should have |  | needs communicating to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ19 | The team - Structural knowledge by Senior Team, Council Members, Manage | Should have |  | requires collaboration with | HR & OD
Corporate and Enabling Services |  | Health & Safety | H&S-REQ19 | The team - Structural knowledge by Senior Team, Council Members, Manage | Should have |  | knowledge requires communicating across the team, specifically to line managers | Communications and Engagement
Corporate and Enabling Services |  | Health & Safety | H&S-REQ19 | The team - Structural knowledge by Senior Team, Council Members, Manage | Should have |  | needs communicating to | Trade Unions
Corporate and Enabling Services |  | Health & Safety | H&S-REQ20 | Governance - Clear longer term understanding of “who” in terms of H&S provisions and monitoring compliance is doing what in new authority | Should have |  | needs communicating after May election and when CEO is in place | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ20 | Governance - Clear longer term understanding of “who” in terms of H&S provisions and monitoring compliance is doing what in new authority | Should have |  | needs support with communicating this info after May election and when CEO is in place | Communications and Engagement
Corporate and Enabling Services |  | Health & Safety | H&S-REQ20 | Governance - Clear longer term understanding of “who” in terms of H&S provisions and monitoring compliance is doing what in new authority | Should have |  | needs communicating after May election and when CEO is in place | HR & OD
Corporate and Enabling Services |  | Health & Safety | H&S-REQ21 | The team - Dedicated H & S Administrative support | Should have |  | is interdependent as it needs communicating to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ21 | The team - Dedicated H & S Administrative support | Should have |  | requires collaboration with | HR & OD
Corporate and Enabling Services |  | Health & Safety | H&S-REQ21 | The team - Dedicated H & S Administrative support | Should have |  | needs support with budgeting | Finance
Corporate and Enabling Services |  | Health & Safety | H&S-REQ21 | The team - Dedicated H & S Administrative support | Should have |  | needs support recruiting admin support |  | Remaining interdependencies to map to a workstream: Recruitment
Corporate and Enabling Services |  | Health & Safety | H&S-REQ22 | Finance - Health and Safety budgets for team and for the wider H & S requirements | Should have |  | the budget needs communicating to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ22 | Finance - Health and Safety budgets for team and for the wider H & S requirements | Should have |  | needs collaboration with | Legal & Democratic Services | It just said L&D - assuming it's legal and democratic rather than learning and development?
Corporate and Enabling Services |  | Health & Safety | H&S-REQ22 | Finance - Health and Safety budgets for team and for the wider H & S requirements | Should have |  | requires support to establish the budget | Finance | Is this the correct workstream based on: 'Finance (for team and wider health agenda). Held in services for equipment and assets etc' ?
Corporate and Enabling Services |  | Health & Safety | H&S-REQ23 | Assessing Risk - Corporate Risk Register and H&S Action plans to identify “higher risk” areas and priority H&S Objectives | Should have |  | line managers of the risks and SMT need to be aware of the risk profile | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ23 | Assessing Risk - Corporate Risk Register and H&S Action plans to identify “higher risk” areas and priority H&S Objectives | Should have |  | requires support from | HR & OD
Corporate and Enabling Services |  | Health & Safety | H&S-REQ23 | Assessing Risk - Corporate Risk Register and H&S Action plans to identify “higher risk” areas and priority H&S Objectives | Should have |  |  |  | Remaining interdependencies to map to a workstream: Structures/ H&S committees
Corporate and Enabling Services |  | Health & Safety | H&S-REQ24 | Assessing risk - Agreed procedures for ongoing H&S audits, inspection and proactive monitoring | Should have |  | procedures need communicating to | All services - all employees | Including senior mangers of service
Corporate and Enabling Services |  | Health & Safety | H&S-REQ24 | Assessing risk - Agreed procedures for ongoing H&S audits, inspection and proactive monitoring | Should have |  | requires support from | HR & OD | (written in contract of employment)
Corporate and Enabling Services |  | Health & Safety | H&S-REQ24 | Assessing risk - Agreed procedures for ongoing H&S audits, inspection and proactive monitoring | Should have |  | procedures to be supported by IT infrastructure | ICT
Corporate and Enabling Services |  | Health & Safety | H&S-REQ25 | Communications - ICT infrastructure to support H&S systems and relevant communications | Should have |  | procedures to be supported by IT infrastructure | ICT
Corporate and Enabling Services |  | Health & Safety | H&S-REQ25 | Communications - ICT infrastructure to support H&S systems and relevant communications | Should have |  | needs support with communicating via the ICT infrastructure | Communications and Engagement
Corporate and Enabling Services |  | Health & Safety | H&S-REQ25 | Communications - ICT infrastructure to support H&S systems and relevant communications | Should have |  | H&S systems to be communicated to | All services - all employees
Corporate and Enabling Services |  | Health & Safety | H&S-REQ25 | Communications - ICT infrastructure to support H&S systems and relevant communications | Should have |  | requires collaboration with | Contract Management/Monitoring | External contractors' - is the correct workstream mapped?
Corporate and Enabling Services |  | Health & Safety | H&S-REQ26 | Governance - Mechanisms in place for production of annual H&S report | Should have |  | annual H&S report needs communicating to | All services - all employees
Corporate and Enabling Services |  | Health & Safety | H&S-REQ26 | Governance - Mechanisms in place for production of annual H&S report | Should have |  | requires collaboration with | HR & OD
|  | Health & Safety | H&S-REQ26 | Governance - Mechanisms in place for production of annual H&S report | Should have |  | the report must adhere to the correct regulations | Legal & Democratic Services | It just said L&D - assuming it's legal and democratic rather than learning and development?
|  | Health & Safety | H&S-REQ26 | Governance - Mechanisms in place for production of annual H&S report | Should have |  | requires approval from | LGR Leadership/Board | Remaining interdependencies to map to a workstream: Service areas ie High ways, specialist areas etc. Portfolio Holder, Lead H&S SMT, H&S Committees / Democratic
Corporate and Enabling Services |  | Health & Safety | H&S-REQ27 | Communications - Appropriate branding | Should have |  | requires support to develop brand voice | Communications and Engagement
Corporate and Enabling Services |  | Health & Safety | H&S-REQ27 | Communications - Appropriate branding | Should have |  | reliant on ICT infrastructure to develop the branding and communicate it | ICT
Corporate and Enabling Services |  | Health & Safety | H&S-REQ28 | Training and development - Clear H&S champions as part of working groups | Could have |  | the identity of the H&S champions needs communicating to | All services - all employees
Corporate and Enabling Services |  | Health & Safety | H&S-REQ28 | Training and development - Clear H&S champions as part of working groups | Could have |  | require support from | HR & OD
Corporate and Enabling Services |  | Health & Safety | H&S-REQ28 | Training and development - Clear H&S champions as part of working groups | Could have |  | requires development and facilitation with |  | Remaining interdependencies to map to a workstream: External Contractors, Partner organisation ie.GLL and Tivoli
Corporate and Enabling Services |  | Health & Safety | H&S-REQ29 | Governance - Unified H&S Unions working parties | Could have |  | H&S working parties need communicating to | All services - all employees
Corporate and Enabling Services |  | Health & Safety | H&S-REQ29 | Governance - Unified H&S Unions working parties | Could have |  | requires support with communicating the working parties across all services | Communications and Engagement
Corporate and Enabling Services |  | Health & Safety | H&S-REQ29 | Governance - Unified H&S Unions working parties | Could have |  | reliant on trade unions to unify the working parties | Trade Unions | H&S committees / unions
Corporate and Enabling Services |  | Health & Safety | H&S-REQ30 | The team - Agreed and recognised competence of H&S specialist list | Could have |  | specialist list needs communicating to | All services - all employees
Corporate and Enabling Services |  | Health & Safety | H&S-REQ30 | The team - Agreed and recognised competence of H&S specialist list | Could have |  | requires support to develop the competence of H&S specialist list | Trade Unions | Joint work with Trade union H&S (Unite, Unison and GMB etc one working party)
Corporate and Enabling Services |  | Health & Safety | H&S-REQ31 | Governance - Audits undertaken by those currently within different authorities | Could have |  | requires support from | HR & OD
Corporate and Enabling Services |  | Health & Safety | H&S-REQ31 | Governance - Audits undertaken by those currently within different authorities | Could have |  | information regarding the audit outputs needs communicating to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ31 | Governance - Audits undertaken by those currently within different authorities | Could have |  | requires support to carry out the audits across different authorities | Learning & Development | Internal training provider - is this mapped to the correct workstream?
Corporate and Enabling Services |  | Health & Safety | H&S-REQ32 | Finance - Shared Budgets for better purchasing power | Could have |  | requires support from | Audit | Audit Teams (Peer to Peer audits)
Corporate and Enabling Services |  | Health & Safety | H&S-REQ32 | Finance - Shared Budgets for better purchasing power | Could have |  |  |  | Remaining interdependencies to map to a workstream: External Organisations that provide H&S resources
Corporate and Enabling Services |  | Health & Safety | H&S-REQ33 | Finance - Agreed protocols between merging authorities | Could have |  | needs support with budgeting | Finance
Corporate and Enabling Services |  | Health & Safety | H&S-REQ33 | Finance - Agreed protocols between merging authorities | Could have |  | need to help agree the protocol between merging authorities | Strategic Procurement / Strategy​ | Procurement and contracts
Corporate and Enabling Services |  | Health & Safety | H&S-REQ33 | Finance - Agreed protocols between merging authorities | Could have |  | requires communication and collaboration with |  | Remaining interdependencies to map to a workstream: LGR Shadow Authority for setting of budgets
Corporate and Enabling Services |  | Health & Safety | H&S-REQ34 | The team - Action plan to review current H & S team structures and corporate OH&S arrangements | Could have | requires collaboration to develop the H&S arrangements and structures |  |  | Dependency to map to a workstream: Shadow Authorities and working groups and wider workstream
Corporate and Enabling Services |  | Health & Safety | H&S-REQ35 | Delivery model - Review of tasks currently undertaken by H & S Services | Could have |  | needs support from | HR & OD
Corporate and Enabling Services |  | Health & Safety | H&S-REQ35 | Delivery model - Review of tasks currently undertaken by H & S Services | Could have |  | tasks undertaken by H&S services needs communicating to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ35 | Delivery model - Review of tasks currently undertaken by H & S Services | Could have |  | requires collaboration with | Trade Unions
|  | Health & Safety | H&S-REQ35 | Delivery model - Review of tasks currently undertaken by H & S Services | Could have |  | needs approval from | LGR Leadership/Board
Corporate and Enabling Services |  | Health & Safety | H&S-REQ36 | Learning and development - Health and Safety Competence Development Framework for employees and managers | Could have |  | help develop and deliver the framework L&D for all employees | Learning & Development
Corporate and Enabling Services |  | Health & Safety | H&S-REQ36 | Learning and development - Health and Safety Competence Development Framework for employees and managers | Could have |  | L&D on H&S framework to be delivered to | All services - all line managers
Corporate and Enabling Services |  | Health & Safety | H&S-REQ36 | Learning and development - Health and Safety Competence Development Framework for employees and managers | Could have |  | requires collaboration and approval | LGR Leadership/Board
Corporate and Enabling Services |  | Health & Safety | H&S-REQ37 | Assessing risk - Day one unification of risk assessments and safe working practices for common areas of work | Won't have | requires development of safe working practices and risk assessments with leadership |  | Health & Safety | H&S Leaders (start working on work packages)
Corporate and Enabling Services |  | Health & Safety | H&S-REQ38 | Governance - Unification of Corporate Risk Registers and agreed committee structures / formats | Won't have |  | requires collaboration with | Resilience and Emergency Planning
Corporate and Enabling Services |  | Health & Safety | H&S-REQ38 | Governance - Unification of Corporate Risk Registers and agreed committee structures / formats | Won't have |  | requires approval from | LGR Leadership/Board | Senior managers / service leader / H&S Committee
Corporate and Enabling Services |  | Health & Safety | H&S-REQ39 | Delivery model - Universal / shared “Service Providers / external | Won't have |  | needs support with identifying the service providers | Strategic Procurement / Strategy​ | Procurement and contracts
Corporate and Enabling Services |  | Health & Safety | H&S-REQ39 | Delivery model - Universal / shared “Service Providers / external | Won't have |  | requires support from | HR & OD
Corporate and Enabling Services |  | Health & Safety | H&S-REQ39 | Delivery model - Universal / shared “Service Providers / external | Won't have |  | needs help establishing budget for service providers | Finance
Corporate and Enabling Services |  | Health & Safety | H&S-REQ39 | Delivery model - Universal / shared “Service Providers / external | Won't have |  | service providers need communicating to | All services - all employees | Employee and Manager (to attend support and L&D)
Corporate and Enabling Services |  | Health & Safety | H&S-REQ40 | Governance - Universal providers of facilities contracts | Won't have |  | requires support from | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Health & Safety | H&S-REQ40 | Governance - Universal providers of facilities contracts | Won't have |  | requires support with the facilities contracts | Strategic Procurement / Strategy​ | Contractors and procurement
Corporate and Enabling Services |  | Health & Safety | H&S-REQ40 | Governance - Universal providers of facilities contracts | Won't have |  |  |  | Remaining interdependencies to map to a workstream: Facilities
Corporate and Enabling Services |  | Health & Safety | H&S-REQ41 | Communications - Electronic Health and Safety management and audit systems | Won't have |  | reliant on ICT infrastructure to house management and audit systems | ICT
Corporate and Enabling Services |  | Health & Safety | H&S-REQ41 | Communications - Electronic Health and Safety management and audit systems | Won't have |  | requires development of the budget for the management and audit ICT systems | Finance
Corporate and Enabling Services |  | Health & Safety | H&S-REQ41 | Communications - Electronic Health and Safety management and audit systems | Won't have |  | requires support with delivering the training of management and audit systems | Learning & Development | It just said L&D - assuming it's learning and development rather than legal and democratic?
Corporate and Enabling Services |  | Health & Safety | H&S-REQ42 | The team - Risk that current H&S resources, staffing and personnel will be insufficient to cover both unitary authorities | Won't have |  | requires support with staffing resources from | HR & OD
Corporate and Enabling Services |  | Health & Safety | H&S-REQ42 | The team - Risk that current H&S resources, staffing and personnel will be insufficient to cover both unitary authorities | Won't have |  | requires support delivering and facilitating training | Learning & Development | It just said L&D - assuming it's learning and development rather than legal and democratic?
Corporate and Enabling Services |  | Health & Safety | H&S-REQ42 | The team - Risk that current H&S resources, staffing and personnel will be insufficient to cover both unitary authorities | Won't have |  | requires approval from | LGR Leadership/Board
Corporate and Enabling Services |  | Health & Safety | H&S-REQ43 | Governance - Long term compliance contracts signed off | Won't have |  | needs support signing off contracts | Strategic Procurement / Strategy​ | Contractors and procurement
Corporate and Enabling Services |  | Health & Safety | H&S-REQ43 | Governance - Long term compliance contracts signed off | Won't have |  | requires approval from | LGR Leadership/Board
Total Day 1 Requirements for: Health and Safety = 43 Total inter/dependencies for: Health and Safety = 138
Corporate and Enabling Services |  | Records Management work package | RM-REQ1 | Secure storage of records – stores in premises with smoke detectors, CCTV, monitored intruder and fire alarms, and keyholder contacts for emergencies. Meeting legal requirement to keep personal data secure and confidential (under Data Protection Act 2018) | Must have |  | requires support with secure asset storage | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Records Management work package | RM-REQ1 | Secure storage of records – stores in premises with smoke detectors, CCTV, monitored intruder and fire alarms, and keyholder contacts for emergencies. Meeting legal requirement to keep personal data secure and confidential (under Data Protection Act 2018) | Must have |  | needs support meeting the legal requirements (data protection act 2018) of record storage |  | Remaining interdependencies to map to a workstream: Third party property consultants
Corporate and Enabling Services |  | Records Management work package | RM-REQ2 | Timely access to information - including Police requests, SARs, Legal, Social Care, Highways, Pensions, Human Resources. In order to ensure efficient service delivery and business continuity; and meet legal requirements to answer information requests (such as FOIA 2000, EIR 2004, DPA 2018) | Must have |  | requires support with data mangement and meeting legal requirements | Information Governance
Corporate and Enabling Services |  | Records Management work package | RM-REQ2 | Timely access to information - including Police requests, SARs, Legal, Social Care, Highways, Pensions, Human Resources. In order to ensure efficient service delivery and business continuity; and meet legal requirements to answer information requests (such as FOIA 2000, EIR 2004, DPA 2018) | Must have |  | needs collaboration with | FOI/SAR, Comments, Compliments & Complaints
Corporate and Enabling Services |  | Records Management work package | RM-REQ2 | Timely access to information - including Police requests, SARs, Legal, Social Care, Highways, Pensions, Human Resources. In order to ensure efficient service delivery and business continuity; and meet legal requirements to answer information requests (such as FOIA 2000, EIR 2004, DPA 2018) | Must have |  | the relevant information needs communicating to | All services - all employees
Corporate and Enabling Services |  | Records Management work package | RM-REQ3 | Legitimate access to information - including updated lists of access permissions for which staff can borrow records from Day 1 onwards. To meet legal requirement under Data Protection Act 2018 | Must have |  | requires support with accessing information and relevant permissions | Information Governance
Corporate and Enabling Services |  | Records Management work package | RM-REQ3 | Legitimate access to information - including updated lists of access permissions for which staff can borrow records from Day 1 onwards. To meet legal requirement under Data Protection Act 2018 | Must have |  | needs collaboration with | FOI/SAR, Comments, Compliments & Complaints
Corporate and Enabling Services |  | Records Management work package | RM-REQ3 | Legitimate access to information - including updated lists of access permissions for which staff can borrow records from Day 1 onwards. To meet legal requirement under Data Protection Act 2018 | Must have |  | the relevant information needs communicating to | All services - all employees
Corporate and Enabling Services |  | Records Management work package | RM-REQ4 | Staff knowledge to be able to search for and retrieve relevant records, manage and dispose of records, and provide Records Management advice. Also, three of the Records Management posts in County are professionally qualified as an essential requirement; which is a best practice standard (postgraduate Diploma / Master’s in Records Management or Archives, or recognised equivalent) | Must have | the retrevial of relevant records and appropriate disposal |  | HR & OD
Corporate and Enabling Services |  | Records Management work package | RM-REQ5 | Secure and timely transfer of requested records to teams at different Countywide locations (e.g. internal courier going daily to main sites in both new Authorities) | Must have | requires support transfering documentation |  | Strategic Procurement / Strategy​ | Procurement/contracts
Corporate and Enabling Services |  | Records Management work package | RM-REQ6 | ICT requirements – on top of standard Microsoft packages (including SharePoint) - provision and support of specialist software / hardware (and third party maintenance contracts) including the following: a. Allerdale – InformU b. Barrow – Epilog system, Technology Forge, Back Office system c. County - MS Access for databases, specialist scanning software and hardware (Kodak, Kofax, Rowe, Kiosk, Wicks Wilson), IrfanView for converting file formats, File Director (Countywide Fostering & Adoption case files). d. South Lakeland – Information@Work | Must have |  | requires Microsoft packages and specialist software/hardware | ICT
Corporate and Enabling Services |  | Records Management work package | RM-REQ6 | ICT requirements – on top of standard Microsoft packages (including SharePoint) - provision and support of specialist software / hardware (and third party maintenance contracts) including the following: a. Allerdale – InformU b. Barrow – Epilog system, Technology Forge, Back Office system c. County - MS Access for databases, specialist scanning software and hardware (Kodak, Kofax, Rowe, Kiosk, Wicks Wilson), IrfanView for converting file formats, File Director (Countywide Fostering & Adoption case files). d. South Lakeland – Information@Work | Must have |  | needs collaboration to provide third party maintenance contracts | Strategic Procurement / Strategy​ | Procurement/contracts
Corporate and Enabling Services |  | Records Management work package | RM-REQ6 | ICT requirements – on top of standard Microsoft packages (including SharePoint) - provision and support of specialist software / hardware (and third party maintenance contracts) including the following: a. Allerdale – InformU b. Barrow – Epilog system, Technology Forge, Back Office system c. County - MS Access for databases, specialist scanning software and hardware (Kodak, Kofax, Rowe, Kiosk, Wicks Wilson), IrfanView for converting file formats, File Director (Countywide Fostering & Adoption case files). d. South Lakeland – Information@Work | Must have |  | Countywide fostering and adoption case files | Children's
Corporate and Enabling Services |  | Records Management work package | RM-REQ7 | Health & Safety requirements – Risk Assessments written and implemented (Manual Handling etc), equipment provided and working (trolleys, ladders etc), adequate number Fire Wardens and First Aiders trained and onsite, weekly fire alarm tests carried out | Must have | needs collaboration to meet H&S requirements |  | Health & Safety
Corporate and Enabling Services |  | Records Management work package | RM-REQ8 | Storage space and a clear process for records being transferred – including urgent transfers like a Care Home or building closing. Risk breach of Information Security if records left in unoccupied buildings | Must have |  | needs support with record transfer and storage | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Records Management work package | RM-REQ8 | Storage space and a clear process for records being transferred – including urgent transfers like a Care Home or building closing. Risk breach of Information Security if records left in unoccupied buildings | Must have |  |  |  | Remaining interdependencies to map to a workstream: Third party property consultants / Information security
Corporate and Enabling Services |  | Records Management work package | RM-REQ9 | Building maintenance contacts for urgent premises jobs (including leaks, security or fire escape issues) | Must have | needs support from |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Records Management work package | RM-REQ10 | Countywide records split between East and West (where possible) – physically, and transfer lists. And Service Level Agreement for records that cannot be split and need to be hosted by one Authority (e.g. Pension volumes, HR records) | Should have | record split needs communicating with |  | All services - all employees
Corporate and Enabling Services |  | Records Management work package | RM-REQ11 | Finding aids and tracking systems across all 7 Councils up-to-date and electronic, ready for when they will be brought together in the 2 new Authorities. Including location guides, file loan records, lists and transfer / accession records. This is to ensure safe transfer of records to the new Authorities – but it will depend on engagement of Asset Owners / Operational Managers who know what the records are – and will also be challenging due to limited resources / time | Should have | is dependent as needs communicating with |  | All services - all employees
Corporate and Enabling Services |  | Records Management work package | RM-REQ12 | Disposals of records in stores up-to-date (including records on disposal hold due to IISCA / formerly Goddard Inquiry), and disposal logs kept (recording what has been destroyed). So that when services are aggregated and disaggregated, all Councils are only holding records still within their retention period. Meeting legal requirement not to keep personal data for longer than necessary (under Data Protection Act 2018) | Should have | is dependent as needs communicating with |  | All services - all employees
Corporate and Enabling Services |  | Records Management work package | RM-REQ13 | Archive transfers up-to-date. Including transferring specific types of records to Archives for permanent preservation under Public Records Acts 1958 and 1967 (such as Coroners records) | Should have |  |  |  | Remaining dependency to map to a workstream: County archive service
Corporate and Enabling Services |  | Records Management work package | RM-REQ14 | Retention Schedules up-to-date within each Council. These include various pieces of legislation that outline how long specific records should be kept by organisations | Should have | is dependent as needs communicating with |  | All services - all employees
Corporate and Enabling Services |  | Records Management work package | RM-REQ15 | Confidential waste contract in place, including ability to have onsite purge shreds (such as financial disposals due April 2023) | Should have | needs support with waste disposal contract |  | Contract Management/Monitoring | Procurement / contracts
Corporate and Enabling Services |  | Records Management work package | RM-REQ16 | Establish disposal permissions contacts for legacy records (for records created pre-April 2023) | Should have | is dependent as needs communicating with |  | All services - all employees
Corporate and Enabling Services |  | Records Management work package | RM-REQ17 | Resources to scan records if requested electronically (staff, equipment, and software) – including Children’s Services SAR requests that County currently search, retrieve, and scan records for | Should have | requires support to search, retrieve, and scan record |  | Policy Framework | Appropriate group / board for policies' - mapped to correct workstream?
Corporate and Enabling Services |  | Records Management work package | RM-REQ18 | Outstanding loans returned to record stores and not kept in offices | Could have | is dependent as needs communicating with |  | All services - all employees
Corporate and Enabling Services |  | Records Management work package | RM-REQ19 | Disposals of records in services / offices up-to-date | Could have | is dependent as needs communicating with |  | All services - all employees
Corporate and Enabling Services |  | Records Management work package | RM-REQ20 | Carry out record audits of each service – to establish what is held by services, volumes of records, how long they are being kept, and that they are listed on the Retention Schedule | Could have | is dependent as needs communicating with |  | All services - all employees
Corporate and Enabling Services |  | Records Management work package | RM-REQ21 | Potential site rationalisation for record stores | Could have |  | needs help rationalising | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Records Management work package | RM-REQ21 | Potential site rationalisation for record stores | Could have |  | needs help rationalising |  | Remaining interdependencies to map to a workstream: Third party property consultants
Corporate and Enabling Services |  | Records Management work package | RM-REQ22 | Update Records Management part of Information Security and Data Protection course (in County this has been down annually) | Could have |  | requires collaboration with | Information Governance | Information security / data protection
Corporate and Enabling Services |  | Records Management work package | RM-REQ22 | Update Records Management part of Information Security and Data Protection course (in County this has been down annually) | Could have |  | training needs issuing for data protection | Learning & Development
Corporate and Enabling Services |  | Records Management work package | RM-REQ23 | Retention Schedule links more with Information Asset Register | Could have | requires collaboration with |  | Information Governance
Corporate and Enabling Services |  | Records Management work package | RM-REQ24 | Communicate to all staff in new Authorities about Records Management and Retention Schedule | Could have | requires collaboration to communicate records management to all employees |  | Communications and Engagement
Corporate and Enabling Services |  | Records Management work package | RM-REQ25 | Future move towards electronic records, including potential classification scheme, implementation of organisation wide system, and joining up information assets (electronic and paper records) | Won't have |  | requires collaboration to establish the implementation of electronic records | ICT
Corporate and Enabling Services |  | Records Management work package | RM-REQ25 | Future move towards electronic records, including potential classification scheme, implementation of organisation wide system, and joining up information assets (electronic and paper records) | Won't have |  | needs communicating and support from | All services - all employees
Total Day 1 Requirements for: Records Management = 25 Total inter/dependencies for: Records Management = 35
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ1 | Development of corporate ID staff badges for each unitary authority |  | requires support with staff lists and new starters corporate badges |  | HR & OD | People, place, ICT, customer & digital - general workstream interdependencies to ensure requirements for Day 1 are in place. Fire Service – understand impacts from agreed service delivery model
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ2 | Workstream Scope Ascertain Day 1 scope for workstream (include e.g. Housing Maintenance, Parks & Open Spaces Maintenance etc.) |  | needs development with |  | Property, Asset Strategy and Property Maintenance |  | 2022-03-01
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ3 | Confirm HQ for Westmorland in Furness and Cumberland Unitary Authorities Identify and agree location for HQ for both the Shadow Authorities and the Day 1 Unitary Authorities Ensure appropriate Member accommodation Ensure ICT infrastructure is suitable Ability to provide individual offices for leaders, deputy leaders, leader PA’s etc Minimum of 3 flexible spaces to facilitate dominant political groupings |  |  | ensure ICT infrastructure is suitable and the required systems are in place for day 1 | ICT
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ3 | Confirm HQ for Westmorland in Furness and Cumberland Unitary Authorities Identify and agree location for HQ for both the Shadow Authorities and the Day 1 Unitary Authorities Ensure appropriate Member accommodation Ensure ICT infrastructure is suitable Ability to provide individual offices for leaders, deputy leaders, leader PA’s etc Minimum of 3 flexible spaces to facilitate dominant political groupings |  |  | Any impacts/ changes to staff and members requiring access to buildings | Legal & Democratic Services
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ3 | Confirm HQ for Westmorland in Furness and Cumberland Unitary Authorities Identify and agree location for HQ for both the Shadow Authorities and the Day 1 Unitary Authorities Ensure appropriate Member accommodation Ensure ICT infrastructure is suitable Ability to provide individual offices for leaders, deputy leaders, leader PA’s etc Minimum of 3 flexible spaces to facilitate dominant political groupings |  |  | Any impacts/ changes to staff and members requiring access to buildings | HR & OD
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ4 | Accommodations Assumptions Paper Establish key assumptions for both unitary authorities regarding accommodation requirements for Day 1 Operational delivery – propose no changes Day 1 FOH/Customer – propose no changes Day 1 All other – propose some change led by service requirement Day 1 Incorporate a 6/12/24 month road map for any significant changes within the accommodation of both the Councils Obtain clear understanding of the service requirements to ensure appropriate accommodation is provided Develop strategy for how staff will be accommodated Teams that need to relocate (e.g., Social Care) Logistics & Cost implications Understand requirement for Customer facing staff and how these will work on Day 1 (i.e., customer services) |  | general support regarding activity for shadow councils and key changes on the accommodations plan |  | Communications and Engagement
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ5 | W&F and Cumberland Business Continuity Policy and Critical Incident Plan Produced Identify and agree location to accommodate staff (inter-dependency with Emergency Planning) Appropriate ICT infrastructure required to support council operations |  |  | identify and agree location to accommodate staff | Resilience and Emergency Planning
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ5 | W&F and Cumberland Business Continuity Policy and Critical Incident Plan Produced Identify and agree location to accommodate staff (inter-dependency with Emergency Planning) Appropriate ICT infrastructure required to support council operations |  |  | appropriate ICT infrastructure required to support council operations | ICT
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ6 | Corporate Landlord Model Adopt a Corporate Landlord Model to effectively manage a large asset portfolio within each unitary authority. Liaise with Service Leads and finance leads to understand implications on Day 1 Agree clear baseline for health and safety compliance/safe and legal Day 1 Confirmation required on go-live date (May/June 2022) |  |  | agree clear baseline for H&S compliance for day1 | Health & Safety |  | May/June 2022
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ6 | Corporate Landlord Model Adopt a Corporate Landlord Model to effectively manage a large asset portfolio within each unitary authority. Liaise with Service Leads and finance leads to understand implications on Day 1 Agree clear baseline for health and safety compliance/safe and legal Day 1 Confirmation required on go-live date (May/June 2022) |  |  | liaise with finance leads to understand implications on day 1 | Finance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ7 | ICT Systems Concerto system identified as preferred CAFM system for Day 1 Support from ICT, Procurement, Finance and Legal Workstreams to implement Confirmation required on go-live date (March 2022) |  |  | to support implementation | ICT |  | 2022-03-01
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ7 | ICT Systems Concerto system identified as preferred CAFM system for Day 1 Support from ICT, Procurement, Finance and Legal Workstreams to implement Confirmation required on go-live date (March 2022) |  |  | to support implementation | Strategic Procurement / Strategy​
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ7 | ICT Systems Concerto system identified as preferred CAFM system for Day 1 Support from ICT, Procurement, Finance and Legal Workstreams to implement Confirmation required on go-live date (March 2022) |  |  | to support implementation | Finance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ7 | ICT Systems Concerto system identified as preferred CAFM system for Day 1 Support from ICT, Procurement, Finance and Legal Workstreams to implement Confirmation required on go-live date (March 2022) |  |  | to support implementation | Legal & Democratic Services
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ8 | Cost Per Asset Undertake an assessment of actual costs per asset to determine true cost of service delivery linked to adoption of Corporate Landlord Model Confirmation of cost per asset required by May/June 2022 |  | requires collaboration to finalise costings |  | Finance |  | May/June 2022
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ9 | Access Systems All access systems to facilitate the free movement of staff across both Councils – understood and mapped Accessibility facilitated and implemented across both Councils – Day 1 Agreement required on the livery/logos for both unitary authorities |  |  | Any impacts/ changes to staff and members requiring access to buildings | HR & OD
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ9 | Access Systems All access systems to facilitate the free movement of staff across both Councils – understood and mapped Accessibility facilitated and implemented across both Councils – Day 1 Agreement required on the livery/logos for both unitary authorities |  |  | Any impacts/ changes to staff and members requiring access to buildings | Legal & Democratic Services
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ10 | Capital Programme Delivery Model Agreement regarding delivery model to support £120m worth of Capital investment across both authorities from Day 1 Confirmation required on go-live date (May/June 2022) |  |  | requires support to develop the capital programme delivery model | Capital Programme |  | May/June 2022
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ10 | Capital Programme Delivery Model Agreement regarding delivery model to support £120m worth of Capital investment across both authorities from Day 1 Confirmation required on go-live date (May/June 2022) |  |  | understand agreed Capital programme works up to 2023/24 | Finance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ11 | Concerto must be operational by Day One. | Must have | requires support with set-up |  | ICT
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ12 | H&S Compliance must be backed up by novated service contracts. | Must have | needs collaboration with |  | Health & Safety
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ13 | We need engagement with various teams e.g., Adult Care, to ensure we have sufficient seats for them on Day One. | Must have | requires engagement to ensure sufficient seating |  | Adults
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ14 | We need to consider any rolling 12-month contracts e.g., key holding ones that may need to be amalgamated. | Must have |  |  |  | Inter/dependencies need inferring from the day 1 requirement
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ15 | Losing staff will affect our collective knowledge base, so we either need to try to retain as many staff as possible or appoint deputies, so that people can download their knowledge before they leave. | Must have | requires collaboration to improve staff retention |  | HR & OD
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ16 | In addition to an access system, we need a standardised desk and meeting room booking system. | Must have | needs support to develop a desk/room booking system |  | ICT
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ17 | We need engagement with Legal and Procurement. | Must have |  | requires engagement with | Legal & Democratic Services
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ17 | We need engagement with Legal and Procurement. | Must have |  | requires engagement with | Strategic Procurement / Strategy​
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ18 | We need a steer re. all asset related contracts, along with Section 24. Corporate procurement will be easier as they will have fewer suppliers. | Must have | needs support to identify asset related contracts |  | Contract Management/Monitoring
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ19 | We need to allow sufficient time for tender exercises. | Must have | need to look at the process, switch to unitary authority |  | Strategic Procurement / Strategy​
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ20 | We need to break the Must Haves down into greater detail to define SMART actions with an agreed timeline for delivery. | Must have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ21 | We need to understand all our contract requirements. | Must have | requires support from |  | Contract Management/Monitoring
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ22 | As other workstreams e.g., Health and Safety aren’t as advanced as we are and predominantly act as auditors, we need to accept responsibility for the H&S of our buildings in terms of SFG20 compliance and we need people who understand legionella requirements etc. Any H&S baseline must identify and address any gaps in the SFG20 standard. | Must have | requires collaboration to understand H&S responsibilities |  | Health & Safety
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ23 | We need to amalgamate our Business Continuity and Critical Incident Plans. | Must have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ24 | We need a Single Point of Contact and agreed Asset Strategies for each unitary. | Must have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ25 | We must have a structure in place for escalation and decision making. | Must have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ26 | The Governance workstream will need to engage with all of us. | Must have | requires engagement with |  | Information Governance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ27 | We must retain the detail of the FHSF and Town Deal funding conditions and firm up the commitment of the new authorities. | Must have |  |  |  | Inter/dependencies need inferring from the day 1 requirement
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ28 | Capital projects must spend their funding. We must not lose their early work and they all need to be fed into the Capital Programme Workstream. | Must have | requires collaboration with |  | Capital Programme
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ29 | We must have a process to handover a project for continuous asset maintenance. | Must have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ30 | We must have the go ahead for Concerto before we can begin data collection. | Must have | requires support from |  | ICT
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ31 | We must have an identified permissions route and budgets set for Planned and Reactive Maintenance, along with compatible Finance systems. | Must have | requires collaboration to identify budgets |  | Finance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ32 | We must identify the actual Must Haves baseline and Should Haves detail and begin to address the Weaknesses identified through the SWOT analysis of both unitaries. | Must have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ33 | Shared resources. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ34 | Agreed key assets and sites. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ35 | A system in place to capture asset detail and flag as much detail as possible as assets go into Concerto | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ36 | Sufficient resources to input all our asset data into Concerto, bearing in mind it took the County 18 months to complete this and we will need ICT and Legal input. | Should have |  | requires support with data input | ICT
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ36 | Sufficient resources to input all our asset data into Concerto, bearing in mind it took the County 18 months to complete this and we will need ICT and Legal input. | Should have |  | requires support with data input | Legal & Democratic Services
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ37 | A standardised agile working policy, noting the county work to a 6:10 desk ratio. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ38 | Begin to rationalise our assets. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ39 | The right resources appointed for any backfilling. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ40 | A significant asset base capable of supporting employment creation across both unitaries. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ41 | An established Commercial/Industrial/Employment portfolio with skills and capability to develop and manage sites/assets to support employment opportunities. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ42 | An established and experienced in-house capability with long track records of managing complex public sector/local government assets. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ43 | A standardised Carbon Management Strategy. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ44 | Established engagement and support for key programmes including Future High Streets Fund, Town Deals and Borderlands. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ45 | Provide a significant town centre presence, to generate footfall and be a focal point. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ46 | Maintain the vitality of our town centres and provide multi-functional hubs. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ47 | A range of customer and community enabled facilities to meet individual needs. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ48 | A significant infrastructure in place to support the digital agenda. | Should have | requires support to establish the digital agenda |  | ICT
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ49 | Continue the active engagement between wider public sector partners and anchor employers. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ50 | Try to achieve critical economies of scale and have a single vision for property led development to support high value employment opportunities. | Should have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ51 | Pursuing and delivering opportunities for significant anchor employers and supply chain demands could provide income streams and underpin the financial sustainability of the Councils. | Could have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ52 | Pooling our assets and approaching opportunities together with shared technical skills and the capacity to broaden development to support employment opportunities within a wider portfolio could increase income generation and enable the sharing of learning across the unitary teams, particularly in areas of compliance, contracting and general estate management. | Could have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ53 | Utilising our existing expertise to develop an apprenticeship programme for school leavers/graduates could safeguard/preserve the technical specialisms currently held within the service area/organisation. | Could have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ54 | Promoting the attractiveness of the unique characteristics of each unitary and the diversity of portfolio could make it attractive for new employees | Could have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ55 | Merging our asset base and instigating a programme of rationalisation to reduce our carbon footprint could enable a programme of investment to be developed in our retained stock to meet carbon reduction targets and provide a double dividend by reducing our running costs. Any land use associated with the asset base could then support a wider array of decarbonisation activity, including off/in-setting and demonstrate leadership within both unitaries, as well as be an exemplar across all sectors. | Could have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ56 | Using our assets to develop strong relationships with stakeholders and partners could deliver programmes associated with Natural Capital, Afforestation, Biodiversity, Pollinators and Renewable/Sustainable Energy. | Could have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ57 | Surplus properties identified as a consequence of LGR could have a significant value in terms of capital, along with the ability to offer new opportunities to support town centre regeneration and vitality. They could also have the potential to generate income. | Could have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Property, Asset Strategy and Property Maintenance | ASSET-REQ58 | Our portfolio could then enable and support digital hubs for service delivery and wider community access. | Could have | needs actioning as a department |  | Property, Asset Strategy and Property Maintenance
Total Day 1 Requirements for: Property and Assets = 58 Total inter/dependencies for: Property and Assets = 69
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ1 | Develop detailed Shadow Authority plans, including dependencies and interdependencies. |  |  |  |  | Dependencies and interdependencies have not been mapped to specific day 1 requirements Dependencies: 1. Legal support requirements across the Programme e.g., specialist Social Care advice 2. ICT – requirements for Day 1 e.g., Member’s email addresses in place 3. General Governance across services e.g., SIROs in place for Day 1 4. Assets – requirements for Day 1 5. Finance – Budget and Policy framework, Insurance for Day 1 6. HR – requirements for Day e.g. HR Policies Interdependencies: 7. Requirements for East & West Shadow Councils with Assets, ICT and external suppliers 8. Requirements with contract novation and contracts management with Procurement and Strategic Commissioning 9. Comms & Engagement – general support regarding activity for Shadow Councils, Shadow Websites 10. Customer & Digital and Comms & Engagement – e.g., Websites
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ2 | Develop more detailed business requirements relating to the scope of work for the Constitution and supporting Governance for the two new unitary authorities.
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ3 | Determine the approach for contract novation to the new unitary authorities.
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ4 | Common Seal |  |  |  |  | Remaining information that needs formatting as a Day 1 requirements with their interdependencies List of Duties - Gov list and LGA Prevent Safeguarding LADO Equality duty Civil Contingency Education School Place planning duties SEN School transport Admissions Meals School Finance Governors Early education and childcare Childrens Director of CS and Lead member responsibilities - Guidance 2013 Safeguarding LAC CIN
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ5 | Constitution ( need to break this down into Unitary requirements )
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ6 | Code of Conducts
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ7 | Member Allowance Scheme
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ8 | Statutory Chief Officers in place Head of Paid Service ( LGHA 1989 s4 ) MO ( LGHA 1989 s5) Chief Finance officer LGA 1972 Director of Childrens Services CA 2004 s18 Director of Public Health ( National Health Act 2006 s73 A ( 1) and Director of Adult Services ( local Authority Social Services Act 1970 s 6 ( A1) Returning Officer Electoral Registration Officer Scrutiny Officer
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ9 | Proper Officers
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ10 | SIROs in place / others PEOPLE THEME
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ11 | Scrutiny
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ12 | Civil contingency rota
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ13 | Insurance in place
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ14 | Legal case work– continuity of cases / systems
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ15 | Scheme of Delegation
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ16 | Authorisations – all officers
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ17 | Safeguarding
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ18 | Budget and Policy framework
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ19 | Functions / rights / liabilities settled
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ20 | Policies required in Law – RIPA ( need to list)
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ21 | Contracts work stream -Inter Authority agreements – transfer agreements
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ22 | Decision making / publication website
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ23 | Legal Case Management system
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ24 | Code of Conduct members/ officers
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ25 | Novation of contracts
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ26 | Lord lieutenancy / Civic
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ27 | Members induction
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ28 | Members portal / set up to fulfil role / ICT
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ29 | IT acceptance User policy agreed/signed by Members/Officers
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ30 | IT devices set up and issued
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ31 | IT Member email addresses set up
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ32 | Declaration of Interest Forms completed
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ33 | Relevant forms published on website e.g. Code of Conduct complaint form, privacy notice etc
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ34 | Councillor contact details published
Corporate and Enabling Services |  | Legal & Democratic Services | LEGAL-REQ35 | Conflict of Interest forms – Officers
Total Day 1 Requirements for: Legal and Democratic = 35 Total inter/dependencies for: Legal and Democratic = 45
Corporate and Enabling Services |  | HR & OD | HR-REQ1 | Payroll - early decision required if single system to be used or existing systems to be used or which HR payroll system will be adopted by unitary authorities. |  |  |  |  | Dependencies and interdependencies have not been mapped to specific day 1 requirements Dependencies: 1.Key dependency on early sight of design blueprints 2. Shadow Authority: Interim Appointments, Senior Committee Meeting Set-Up & Pay Policy 3. Clear link to the Comms & Engagement workstream: (employee comms alignment is critical) 4. How will HR be structured for Day 1 – joint service or independent services 5. Operating structure – finalised operating structure required to inform HR set-up 6. Finance - PAYE & Pension Scheme – how will these be set-up and managed for Day 1 and beyond 7. Close working with Themes required to identify any gaps in business requirements, the “ask”. 8. Fire Service – understand their future model Interdependencies: 9. Member Development: Joint working with Legal & Democratic Services and Communication & Engagement etc. 10. ICT - Which systems will be adopted by each unitary authority 11. Data hub – on establishment lists to support Blueprint activity
Corporate and Enabling Services |  | HR & OD | HR-REQ2 | Key decisions required on: o If there will there be a single preferred agency staff provider for vesting day o How will HR be structured for Day 1 – joint service or independent services
Corporate and Enabling Services |  | HR & OD | HR-REQ3 | Establishment lists need to be completed by January 2023 | [5 empty] | 2023-01-01
Total Day 1 Requirements for: HR&OD = 3 Total inter/dependencies for: HR&OD = 11
Corporate and Enabling Services |  | Communications and Engagement | COMMS-REQ1 | Comms Leads to capture Day 1 Requirements from the themes they support |  |  |  |  | Dependencies and interdependencies have not been mapped to specific day 1 requirements Dependencies: 1. OD and Human Resources workstream 2. In developing robust communications and engagement strategies for staff 3. In developing new values and behaviours 4. In organising learning and development opportunities as part of the transition 5. In developing leadership support for pre and post transition Interdependencies: 6. Branding – critical interdependency with various workstreams – this has already been raised with all workstream leads as a critical interdependent issue 7. Employee comms, engagement and welfare – interdependency with HR workstream 8. Common and clear core messaging – especially around employee reassurance
Corporate and Enabling Services |  | Communications and Engagement | COMMS-REQ2 | Demand Management Gap (Required link into Themes and other workstreams, to meet capacity or variation in demands)
Corporate and Enabling Services |  | Communications and Engagement | COMMS-REQ3 | Continue to build the overarching Communication Strategy and supporting activity in preparation for vesting day
Corporate and Enabling Services |  | Communications and Engagement | COMMS-REQ4 | Use Branding Checklist to identify and agree Day 1 Must Haves with the SA and plan for ‘lead times’ to ensure delivery
Corporate and Enabling Services |  | Communications and Engagement | COMMS-REQ5 | Communications and Engagement strategy to be discussed with shadow authority, covering all levels of comms and engagement from Informing through to Co Production
Corporate and Enabling Services |  | Communications and Engagement | COMMS-REQ6 | Consultation strategy and approach to be discussed with shadow authority, covering all levels of comms and engagement from Informing through to Co Production
Total Day 1 Requirements for: Communications and Engagement = 6 Total inter/dependencies for: Communications and Engagement = 8
Corporate and Enabling Services |  | Strategic Commissioning | STRATCOM-REQ1 | Work is progressing in this workstream, using guiding principles to develop the requirements. This workstream is functioning more dynamically than the other workstreams due to the nature of their function and that services that they support predominantly will need a contract / commissioning to allow them to provide service delivery to end users. |  |  |  |  | Dependencies and interdependencies have not been mapped to specific day 1 requirements Dependencies: 1. Dependency with Finance to understand budget ranges for services and how this aligns to the current contractual commitments across all seven Councils 2. Corporate branding will be part of the comms and engagement workstream with links to this workstream 3. Ability to be safe & legal on Day 1 is dependent on the service delivery models being agreed and applied i.e., Hosted service solutions and/or problematic contracts ‘dropped’ into one council under Reg 14 4. Terms & Conditions to be discussed (working alongside Legal & Democratic Workstream) 5. Dispute/Resolution procedure to be discussed with Legal Workstream 6. Systems with ICT Workstream Interdependencies: 6. There needs to be an alignment / sequencing of interdependencies, for example, clarification of Alternative arrangements for suppliers need to be in place when there are links with, Legal, Governance and Strategic Commissioning. 7. Awareness of any Delegated Authority 8. Awareness to ensure focus on Customer outcomes and service delivery is not impacted through this work. For example, some Providers may not wish to work with two councils due to the transactional/mgt costs/overheads associated with such; others may see more commercial advantage doing business with one particular council, to the detriment of the other obtaining some services. 9. Close working with People programme to understand requirements for Day 1 and impacts to services with any proposed changes.
Corporate and Enabling Services |  | Strategic Commissioning | STRATCOM-REQ2 | Awaiting response from external Law Firm (For Legal requirements to be agreed and shared)
Corporate and Enabling Services |  | Strategic Commissioning | STRATCOM-REQ3 | Require Specialist Legal Support setting up, within the specific areas of Children's, Adults & Public Health
Corporate and Enabling Services |  | Strategic Commissioning | STRATCOM-REQ4 | A requirement for a decision-making body in place, to then mobilise the activity required for this workstream
Corporate and Enabling Services |  | Strategic Commissioning | STRATCOM-REQ5 | Marketing Awareness of Social Care demand management (combined focus required): A significant proportion of the County’s Adults (80%), Children’s (60%) and Public Health service functions are commissioned and there is a real concern about how potential disaggregation of these contracts will impact the market
Total Day 1 Requirements for: Strategic Commissioning = 5 Total inter/dependencies for: Strategic Commissioning = 9
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ1 | Transformation Activity Plan Defined: Clarity regarding : a) 1 April 2023 Transition Activity already achieved b) 2023/24 Transition Activity planned but yet to achieve c) 2024/26 Medium Term Transformation Activity required d) 2026 & Beyond Longer term transformation ambitions | Must have |  | activity plan needs communicating to | All services - all employees | PMO to collate clarity of requirements for both Cumberland and Westmorland & Furness Shadow Authority Work Programme regarding • Blueprints • Day 1 Safe & Legal Plan • Benefits Realisation • Aggregation, Disaggregation & Integration AND All workstreams and services where Transformation and Change Management resources are required to deliver Council Plan and agreed Transformation programme
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ1 | Transformation Activity Plan Defined: Clarity regarding : a) 1 April 2023 Transition Activity already achieved b) 2023/24 Transition Activity planned but yet to achieve c) 2024/26 Medium Term Transformation Activity required d) 2026 & Beyond Longer term transformation ambitions | Must have |  | activity plan needs to adhere to policies | Policy Framework
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ1 | Transformation Activity Plan Defined: Clarity regarding : a) 1 April 2023 Transition Activity already achieved b) 2023/24 Transition Activity planned but yet to achieve c) 2024/26 Medium Term Transformation Activity required d) 2026 & Beyond Longer term transformation ambitions | Must have |  | requires support from | Performance & Business Intelligence
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ1 | Transformation Activity Plan Defined: Clarity regarding : a) 1 April 2023 Transition Activity already achieved b) 2023/24 Transition Activity planned but yet to achieve c) 2024/26 Medium Term Transformation Activity required d) 2026 & Beyond Longer term transformation ambitions | Must have |  | requires support from | Legal & Democratic Services
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ2 | Transformation Activity Plan costed To align to 2 new Unitary Council Plans and MTFPs to assess affordability and prioritisation requirements. | Must have |  | needs support with costing the transformation activity plan | Finance
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ2 | Transformation Activity Plan costed To align to 2 new Unitary Council Plans and MTFPs to assess affordability and prioritisation requirements. | Must have |  | requires support from | Legal & Democratic Services
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ2 | Transformation Activity Plan costed To align to 2 new Unitary Council Plans and MTFPs to assess affordability and prioritisation requirements. | Must have |  | needs communicating to | All services - all employees | Transition blueprint ambitions link to Benefits Realisation Plan, Implementation Planning and MTFP resource allocation Cumberland and Westmorland & Furness Shadow Authority Work Programme and 2023/24 MTFPs AND All workstreams and services where Transformation and Change Management resources are required to deliver Council Plan and agreed Transformation programme
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ3 | Sufficient skilled and experienced Transformation FTE or Change Management FTE in place to meet expected or affordable Transformation Activity Plan | Should have |  | requires support to decipher FTE allocation | HR & OD | Successful Transfer of Existing 7 Council Transformation Teams Plus retain some of the seconded LGR PMO employees Potential to be Supplemented by 3rd party resources (if affordable) / staff leavers / secondments / backfill of positions. NB : Current estimate is that existing FTE substantive cohort will need to double to meet required change needs post vesting day
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ3 | Sufficient skilled and experienced Transformation FTE or Change Management FTE in place to meet expected or affordable Transformation Activity Plan | Should have |  | requires sign off | LGR PMO
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ3 | Sufficient skilled and experienced Transformation FTE or Change Management FTE in place to meet expected or affordable Transformation Activity Plan | Should have |  | needs communicating to | All services - all employees | All workstreams and services where Transformation and Change Management resources are required to deliver Council Plan and agreed Transformation programme
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ4 | Dedicated Transformation / Programme Office in Unitary Council structure (recommended as a corporate centralised resource model) | Should have |  | requires support to develop the prog office stucture | HR & OD
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ4 | Dedicated Transformation / Programme Office in Unitary Council structure (recommended as a corporate centralised resource model) | Should have |  | requires collaboration to develop structure which adheres to regulation | Legal & Democratic Services | Shadow Authority (Legal & Democratic) Early links with Members and SRO’s
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ4 | Dedicated Transformation / Programme Office in Unitary Council structure (recommended as a corporate centralised resource model) | Should have |  | requires sign off | LGR PMO
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ4 | Dedicated Transformation / Programme Office in Unitary Council structure (recommended as a corporate centralised resource model) | Should have |  | needs communicating to | All services - all employees | All workstreams and services where Transformation and Change Management resources are required to deliver Council Plan and agreed Transformation programme
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ5 | Transformation Service referenced in Constitution and Council Plan Strategy documents (to ensure high profile given Strong Governance required to complete transition and achieve benefits realisation plans) | Should have |  | requires support from | Legal & Democratic Services | Shadow Authority (Legal & Democratic) Early links with Members and SRO’s
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ5 | Transformation Service referenced in Constitution and Council Plan Strategy documents (to ensure high profile given Strong Governance required to complete transition and achieve benefits realisation plans) | Should have |  | needs collaboration to define against policy | Policy Framework
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ5 | Transformation Service referenced in Constitution and Council Plan Strategy documents (to ensure high profile given Strong Governance required to complete transition and achieve benefits realisation plans) | Should have |  | needs communicating to | All services - all employees | All workstreams and services where Transformation and Change Management resources are required to deliver Council Plan and agreed Transformation programme
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ5 | Transformation Service referenced in Constitution and Council Plan Strategy documents (to ensure high profile given Strong Governance required to complete transition and achieve benefits realisation plans) | Should have |  | requires sign off | LGR PMO
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ6 | Project Management methodology and tools defined (may require ICT licences and training) To ensure consistency of approach, programme governance and tools | Should have |  | to provide skills assessment and training programme | HR & OD
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ6 | Project Management methodology and tools defined (may require ICT licences and training) To ensure consistency of approach, programme governance and tools | Should have |  | require ICT licences | ICT
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ7 | Ensure Staff Well-being and resilience support available for colleagues leading and delivering transformation programmes given a high profile and pressured environment is likely some resilience and support requirements in early stages | Should have |  | to provide capacity planning, wellbeing and support | HR & OD
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ7 | Ensure Staff Well-being and resilience support available for colleagues leading and delivering transformation programmes given a high profile and pressured environment is likely some resilience and support requirements in early stages | Should have |  | requires sign off | LGR PMO | Delivery of Must Haves should reduce need Link to PMO and Shadow Authorities
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ8 | Transformation service Skills, Training, Collaboration and Communication Programme in place Could include requirement for Additional ICT licences for example and training investment, comms support aligned Comms Support to Programmes (to raise Programme profile / presence) Dedicated Team Collaborative / collective space (virtual and/or physical environment) | Could have |  | requires support with OD skills and training | HR & OD
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ8 | Transformation service Skills, Training, Collaboration and Communication Programme in place Could include requirement for Additional ICT licences for example and training investment, comms support aligned Comms Support to Programmes (to raise Programme profile / presence) Dedicated Team Collaborative / collective space (virtual and/or physical environment) | Could have |  | requires collaboration to use ICT licences for training investment | ICT
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ8 | Transformation service Skills, Training, Collaboration and Communication Programme in place Could include requirement for Additional ICT licences for example and training investment, comms support aligned Comms Support to Programmes (to raise Programme profile / presence) Dedicated Team Collaborative / collective space (virtual and/or physical environment) | Could have |  | support to programmes to raise Programme profile / presence and support with ICT licences | Communications and Engagement
Corporate and Enabling Services |  | Transformation & Change Management | TRANS-REQ8 | Transformation service Skills, Training, Collaboration and Communication Programme in place Could include requirement for Additional ICT licences for example and training investment, comms support aligned Comms Support to Programmes (to raise Programme profile / presence) Dedicated Team Collaborative / collective space (virtual and/or physical environment) | Could have |  | support with developing dedicated Team Collaborative / collective space (virtual and/or physical environment) | Property, Asset Strategy and Property Maintenance
Total Day 1 Requirements for: Transformation and Change Management = 8 Total inter/dependencies for: Transformation and Change Management = 26
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ1 | Ability to Print/Scan on networked printers | Must have |  | requires MS office, and to generate payslips/ print letters | ICT | Need to be able to print letters for different services as well as internal payslips (Cumbria CC, Carlisle CC print 'exception' payslips where the employee does not have IT access - County print approx 2,500 a month. SLDC are all electronic with no paper exceptions). Currently for Cumbria CC, Carlisle CC, Copeland the ID badges enable access to the printers. The ID badges also records the dept for cross charging of printers. SYSTEMS USED: MS OFFICE
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ1 | Ability to Print/Scan on networked printers | Must have |  | support with access to the printers | HR & OD
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ2 | Ability to Produce ID and Door Access Badges | Must have |  | requires systems: paxton, specialist printer, CCC ID portal | ICT | These are for staff IDs, door entry and access to Printers as well as 'non chip' ones which act as ID and 'warrant of entry'. Cumbria County Council currently use Paxton for its Corporate Access and ID badges (for Parking officers or mental health practicioners etc). Planning Officers, Enforcement, Environmental Health, Building Control Surveyor require the Warrant of Entry Badges which are currently produced by a third party for Allerdale and Carlisle. Barrow currently print their own ID badges inhouse. SYSTEMS USED: Paxton, Specialist Printer and CCC ID Portal
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ2 | Ability to Produce ID and Door Access Badges | Must have |  | support with the generation of ID badges | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ3 | Access the Security ID badge request Portal (Cumbria County Council) | Must have | requires the system CCC ID Portal to request badges |  | ICT | Will the existing CCC ID badge request portal be set up in both new authorities? Due to volumes it is not practical to rely on an email to request. SYSTEMS USED: CCC ID Portal
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ4 | Ability to provide Visitor/Contractor Badges | Must have | support with the creation of visitor badges |  | Property, Asset Strategy and Property Maintenance | Where Business Support provide Front of House support they must provide/log visitors and contractors
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ5 | Access certain shared email address | Must have | provide access to email boxes |  | ICT | Currently we manage/access multiple email boxes, these email addresses will change under LGR and we will need to maintain access to them. The list is indicative of the mailboxes we currently manage - full details can be provided when necessary: bsan@cumbria.gov.uk, bsaw@cumbria.gov.uk, bsas@cumbria.gov.uk, bsaca@cumbria.gov.uk, csab@cumbria.gov.uk, ASC.outgoingmail@cumbria.gov.uk, equipment.services@cumbria.gov.uk,
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ6 | Ability to receive/log work requests from Service Users | Must have | requires the system WHD ticketing system |  | ICT | When the new services are designed they should include a method to request Business Support using a ticketing type system - there are workarounds but these are not practical due to volumne and the 'sharing' of work across the County that the County Council currently do. Cumbria CCC currently use the WHD Ticketing System. Can we assume that under the two new authorities there will be a ticketing based system, perhaps just two instances of WHD to start with? Alexandra has passed details of this system to Lynne Davidson. SYSTEMS USED: WHD Ticketing System
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ7 | Ability to Frank Mail | Must have |  | requires collaboration to understand pre-exisitng contract with royal mail | Contract Management/Monitoring | All existing councils have agreements with Royal Mail, these will need to be renewed/revised with the new authorities.
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ7 | Ability to Frank Mail | Must have |  | needs support from | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ8 | Access to Franking Machines | Must have | help understand the current franking machine contracts |  | Contract Management/Monitoring | Individual Contracts with Franking Machine companies (FPTeleset for Allerdale, Pitney Bowes for Carlise and Barrow, Quadiant and Pitney Bowes for Cumbria CC the Quadiant lease runs out Dec 22)
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ9 | Ability to use recognised courier services | Should have | help understand the current courier contracts |  | Contract Management/Monitoring | Currently we have contracts inplace with the following courier companies DPD (Cumbria CC), TNT (Carlisle) can these be simply transfer to the two new Unitaries? We raise a PO and use the third party portal
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ10 | Internal Courier Service - Cumbria CC use Harts Couriers to move 'internal' items between its County Wide Buildings | Should have |  | help understand the current courier contracts | Contract Management/Monitoring | At County the Business Support Budget used to part fund this. Wanted to include so that the Hart Contract continues.
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ10 | Internal Courier Service - Cumbria CC use Harts Couriers to move 'internal' items between its County Wide Buildings | Should have |  | requires support from | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ11 | Large batch external printing for such things at Council Tax - use a third party (UK Mail) | Must have | help understand the current large batch printing contracts |  | Contract Management/Monitoring | Allerdale, Copeland and Carlisle currently have contracts with UK Mail, will these be transferred to the new Authorities?
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ12 | Access to Envelope Stuffers | Should have |  | help understand the current service contracts | Contract Management/Monitoring | Machines at Carlisle (Parkhouse it is a leased Quadiant Machine and the contract ends Dec 22) Carlisle (Civic Centre) Barrow (Town Hall). Service Contracts for these are with the old authorities - is it OK to assume that Service Contracts like this are covered under IT workstream?
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ12 | Access to Envelope Stuffers | Should have |  | requires collaboration to decipher where service contracts sit | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ13 | Access to Letter Opener Machine | Could have |  | help understand the current service contracts | Contract Management/Monitoring | To do with electoral postal vote timings and voter registration - Service Contract is with old authority so if they break we need to get them fixed (Carlisle). The elections team at Allerdale also use one but not their BS team.
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ13 | Access to Letter Opener Machine | Could have |  | requires collaboration to decipher where service contracts sit | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ14 | Ability to place orders i.e. raise a purchase order on the new authorities ordering system - with appropriate approval/budget levels set (and know who the approved supplier contracts are with for the new authorities) | Must have |  | help understand the current service contracts | Strategic Procurement / Strategy​ | All districts. On a practical note when will we find out the 'guidance' on Procurement/P2P and what happens to orders placed under old authority but only fullfilled under new authority? Will we be able to match AP invoices received post Vesting day against 'open' Purchase Orders? SYSTEMS USED: E5, EPROC at Cumbria County
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ14 | Ability to place orders i.e. raise a purchase order on the new authorities ordering system - with appropriate approval/budget levels set (and know who the approved supplier contracts are with for the new authorities) | Must have |  | requires systems: E5, EPROC | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ15 | Ability to pay invoices (Business Support are involved in providing the relevant codes so that P2P can then auto pay) | Must have |  | requires system blue slip portal | ICT | Business Support in both new authorities need to be fully trained in any new coding/cost centre/approval process SYSTEMS USED: Blue Slip Portal at County Council
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ15 | Ability to pay invoices (Business Support are involved in providing the relevant codes so that P2P can then auto pay) | Must have |  | requires support with invoices | Finance
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ16 | Ability to raise an EMERGENCY payment for a court order (Carlisle City currently issues cheques but this method is being phased out and replaced by an electronic means of Emergency Payments) | Must have | requires support with payments |  | Finance | NB: In Allerdale the Finance team do the emergency payments. Whatever the new process is Business Support need to be full aware of their role in ensuring that the new process is followed.
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ17 | Barrow team (Housing stock specific) need the ability to make Court Applications for such things as Gas Warrants, Possession Proceedings on behalf of the Income and Debt recovery scheme | Must have |  | requires support to understand the debt recovery scheme | Legal & Democratic Services | Barrow use the Courts Website directly for this
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ17 | Barrow team (Housing stock specific) need the ability to make Court Applications for such things as Gas Warrants, Possession Proceedings on behalf of the Income and Debt recovery scheme | Must have |  | requires support from | Finance
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ18 | Branding - Need a PDF copy of the new logos so that we can update our letter templates and virtual letters that are auto generated from different systems but printed/posted by Business Support etc | Must have | needs support with branding and logos |  | Communications and Engagement | Need to map 'branding team' to a workstream All templates used by BS need to be updated. Branding needs to be included when we raise PO's for uniforms
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ19 | Carlisle City - Business Support receive cheques and physically input into 'Webpay' so that the customer payment goes to Council Tax or NNDR, Debtors, Legal, Land Charges, Development Control, Building Control, Licensing, Environmental Health, Parking etc and then physical cheques are then walked to the bank to pay in. | Must have | needs support with online web payments |  | Finance | SYSTEMS USED: Webpay
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ20 | Ability to book travel and accommodation | Should have | help understand the current service contracts |  | Contract Management/Monitoring | This may be 'must have' but a work around is that the individual claims back on expenses. Currently the Cumbria County Council WHD system is set up so any user can raise a request for travel/accom - propose this is simply expanded across both new authorities
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ21 | Carlisle need the ability to book out pool cars | Should have | requires support to organise booking pool cars |  | Fleet | Carlisle currently use an Outlook Calendar for this. For other existing Councils Business Support aren't involved in the process - so this is probably a short term need while Fleet go through their transformation process
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ22 | Ability to run the 'safer driving programme' | Must have | requires support to organise the 'safer driving programme' |  | Fleet | County administer the scheme for fleet, Carlisle goes through fleet and H&S, in Barrow HR request copies of paperwork but don't have pool cars. Alerdale H&S do their safter driving programme with paperwork by HR.
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ23 | Controlled Stationery Administration (including Controlled Stationary for Schools) | Should have | require collaboration to provide branded stationary |  |  | Need to map 'branding team' to a workstream These will need to be re-branded and controlled by new authorities (can be done inhouse providing PDF of branding supplied).
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ24 | Produce financial reports and email out (Carlisle) so need access to the Finance system | Must have |  | needs access to the finance system | Finance | Carlisle uses Citrix Client Engine Authority Financials SYSTEMS USED: Citrix Client Engine Authority Financials
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ24 | Produce financial reports and email out (Carlisle) so need access to the Finance system | Must have |  | requires the system: Citrix Client Engine Authority Financials | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ25 | Ability to do legal sealing | Must have | requires support from |  | Legal & Democratic Services | Carlisle and County do legal sealing - so assume a new seal will be produced for each authority (and authorised individuals)
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ26 | Ability to scan/print on A1 and A0 size | Should have |  | needs support to help with large document printing | ICT | Allerdale currently have a contract to do this printing with a third party. County do it inhouse and have plotter printers at multiple locations.
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ26 | Ability to scan/print on A1 and A0 size | Should have |  | help understand the current contracts | Contract Management/Monitoring
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ27 | Ability to print bus timetables on our specialist waterproof paper printer | Could have | require support to print on specalist paper |  | ICT | Currently only have one based in Parkhouse/Carlisle. As a work around they can be printed and laminated.
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ28 | Petty Cash Management | Must have | requires collaboration with |  | Finance | Carlisle and Barrow look after Petty Cash. Business Support need to know the new 'Petty Cash' process across the new authorities
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ29 | Ability to receive, count and receipt the cash for finance | Must have | requires collaboration with |  | Finance | In Barrow the Traffic Wardens empty the car park machines and pass to Business Support. Alerdale outsource to a third party to collect/bank the cash.
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ30 | Banking details and procedures for cashing up at Archives in Carlisle | Must have | requires collaboration with |  | Finance | Business Support cashes up at the 'archive' locations in Cumbria. G4S collect for the libraries but for legal and Commons Reg Business Support physically go to the bank
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ31 | Access to the Registration appointments which are currently recorded on the Registrars’ Stopford program | Must have |  | requires access to the registration appointments system - stopford | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ31 | Access to the Registration appointments which are currently recorded on the Registrars’ Stopford program | Must have |  | requires support from |  | Need to map 'archives and registration' to a workstream Business Support update data on the Registrars' system regarding appointments so will need access to whatever system (s) the new Unitaries use and at whichever locations the service will be provided from. SYSTEMS USED: Stopford
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ32 | Ability to take Credit Card Payments for some services | Must have | requires support to organise credit card payments |  | Finance | Kendal County Hall take Credit Card payments for Windermere Ferry. Parkhouse take MOT card payments over the phone.
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ33 | Access GIS system (and CITRIX and GGP) for Commons Registrations (Cumbria CC) | Must have |  | requires help to access GIS systems - Citrix and GGP | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ33 | Access GIS system (and CITRIX and GGP) for Commons Registrations (Cumbria CC) | Must have |  | requires support from |  | Need to map 'archives and registration' to a workstream This is to enable Business Support to conduct searches from Commons Registrations process SYSTEMS USED: Citrix, GGP
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ34 | Access mastergov.co.uk/cumbria with a username/password to enable Business Support to upload details for the Developmental Control team | Must have |  | requires the system: mastergov | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ34 | Access mastergov.co.uk/cumbria with a username/password to enable Business Support to upload details for the Developmental Control team | Must have |  | requires support from |  | Need to map 'environment and regulatory services' to a workstream Cumbria CC requirement - assume this system will need new logons for each new authority? SYSTEMS USED: Mastergov.co.uk/cumbria
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ35 | Access GENOHSIS system for H and Safety Business Support | Must have |  | requires the system: GENOHSIS | ICT | GENOHSIS is system used by Cumbria CC. SYSTEMS USED: GENOHSIS
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ35 | Access GENOHSIS system for H and Safety Business Support | Must have |  | needs collaboration with | Health & Safety
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ36 | Be able to burn DVDs/CDs for Legal Services | Could have |  | needs support burning DVDs/CDs | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ36 | Be able to burn DVDs/CDs for Legal Services | Could have |  | needs to collaborate with | Legal & Democratic Services
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ37 | Be able to receiving, deseminating and storage for digital post to the Legal & Democratic Services Team (we process the exceptions) | Should have |  | requires support from | ICT | Bus Support currently provide this service for the Legal Team
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ37 | Be able to receiving, deseminating and storage for digital post to the Legal & Democratic Services Team (we process the exceptions) | Should have |  | needs to collaborate with | Legal & Democratic Services
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ38 | Access to CIVICA Trading Standards System | Must have |  | needs to access the system CIVICA | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ38 | Access to CIVICA Trading Standards System | Must have |  | requires collaboration with |  | Need to map 'TRADING STANDARDS' to a workstream Cumbria CC (we have a LA reference that we use, assume these will change when new Unitaries are established) SYSTEMS USED: CIVICA
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ39 | Must know who will insure Fleet (currently for Cumbria CC it is Zurich) and Business support help process accident claims. | Must have | requires collaboration with |  | Fleet | Put as a 'Must have' due to time contraints that will be required to submit details should there be an insurance claim
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ40 | Access to TRANMAN for Cumbria CC Fleet Department | Must have |  | requires access to the system TRANMAN | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ40 | Access to TRANMAN for Cumbria CC Fleet Department | Must have |  | requires collaboration with | Fleet
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ41 | To maintain the physical paper filing for fleet to ensure we meet requirements of the O Licence | Must have | requirements collaboration to maintain paper filing |  | Fleet | For County this is currently done at Dalston.
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ42 | To book meeting rooms (using whatever booking system the new authorities will have e.g. Condecco or Outlook) | Must have |  | requires support using outlook, MS bookings | ICT | Copeland and Allerdale book rooms via Outlook Calendars. Allerdale also use MS Bookings. Carlisle use an Intranet Sharepoint Calendar System. Will room booking remain part of Admin and Bus Support? In County room bookings are done by FM for rooms set up on Condecco but Bus Support do them for outlook rooms. QUERY - when will we be able to book meeting rooms for after vesting day? Ideally we would like to be able to book rooms for meetings to take place in the new authorities several months before vesting day (e.g. Childrens and Adults services need to be able to send out letters with appointment details for several months in advance).
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ42 | To book meeting rooms (using whatever booking system the new authorities will have e.g. Condecco or Outlook) | Must have |  | requires collaboration ascertain space for bookings | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ43 | Access the contact centre system to enable us to provide support at busy times (Allerdale) | Must have |  | requires access to the contact centre system - BT cloud contract | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ43 | Access the contact centre system to enable us to provide support at busy times (Allerdale) | Must have |  | requires support from |  | Need to map 'contact centre' to a workstream SYSTEMS USED: BT Cloud Contract
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ44 | Ability to access to ONE system in order for a childs education healthcare plan (ECHP) to be issued to meet Stat guidelines | Must have |  | needs access to the ONE system | ICT | SYSTEMS USED: ONE System
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ44 | Ability to access to ONE system in order for a childs education healthcare plan (ECHP) to be issued to meet Stat guidelines | Must have |  | requires collaboration to issue the childs education healthcare plan | Children's
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ45 | Access to Objective Connect to share documentation with CSAB Board members | Must have |  | requires access to objective connect | ICT | This holds off of the Cumbria Safeguarding Board documentation. All CSAB Board members can share and access documentation securely. SYSTEMS USED: Objective Connect
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ45 | Access to Objective Connect to share documentation with CSAB Board members | Must have |  | requires collaboration with | Adults
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ46 | The Gamma system needs to be in place for CES customers, one for each authority. | Must have |  | requires support to develop reference numbers | ICT | Currently Adults Services has one reference number for the whole of Cumbria County Council. A new number for each authority will need to be created.
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ46 | The Gamma system needs to be in place for CES customers, one for each authority. | Must have |  | requires support to develop reference numbers | Adults
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ47 | Access to Adult Social Care customer information (IAS) to complete duties | Must have |  | requires access to IAS system | ICT | The S117 register is held on here. Will need access to own IAS tray, S117 Aftercare Register, Community Equipment Service Admin Tray, West Case Closures, Carlisle Case Closures, Eden Case Closures, South Lakes Case Closures, Furness Case Closures, Copeland Retention, Allerdale Retention, Carlisle Retention, Eden Retention, Furness Retention, South Lakes Retention SYSTEMS USED: IAS
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ47 | Access to Adult Social Care customer information (IAS) to complete duties | Must have |  | requires collaboration with | Adults
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ48 | Access to Community Equipment Service (ELMS) to complete duties | Must have |  | requires access to ELMS system | ICT | ELMS keep a record of equipment that people have. It also keeps a log of all equipment within the CES stores. Used by District Nurses and Occupational Therapists as well as all Business Support and CES staff SYSTEMS USED: ELMS
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ48 | Access to Community Equipment Service (ELMS) to complete duties | Must have |  | requires collaboration with | Adults
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ49 | To be able to archive physical files containing details of our Adults Social Care customers. | Must have | requires collaboration to archive physical files of adult social care customers |  | Adults | The electronic records are held on IAS (see above) in addition paper records are also needed to be kept until they reach the retention date. The paperwork includes 'historical' data i.e. County data which will then be 'owned' by one of the new authorities - access to it will be needed.
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ50 | Access that allows updates to be made on IAS / ELMS with date of deaths so cases can be closed and to raise collection of equipment on ELMS. To do this access to Tell us Once (with fob) is required | Must have |  | requires access to IAS/ELMS and helps with tell us once fob | ICT | Tell us Once is a DWP system. The fobs are from CCC data security team. DWP has CCC as one authority and that will need to split into two new authorities. SYSTEMS USED: Tell Us Once / IAS / ELMS / Tell us Once fob
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ50 | Access that allows updates to be made on IAS / ELMS with date of deaths so cases can be closed and to raise collection of equipment on ELMS. To do this access to Tell us Once (with fob) is required | Must have |  | requires collaboration to collate data | Children's
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ50 | Access that allows updates to be made on IAS / ELMS with date of deaths so cases can be closed and to raise collection of equipment on ELMS. To do this access to Tell us Once (with fob) is required | Must have |  | requires collaboration to collate data | Adults
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ51 | Access to the Canary Care system and equipment which the Business Support team manages on behalf of Adult Social Care Practitioners. | Must have |  | requires access to the canary care system | ICT | Canary Care sends an email notification to the relevant social worker email. The social then gets in touch with Business Support via email to then process the admin around getting the relevant kit/services for the social workers or practicioners to delivery. SYSTEMS USED: Canary Care Equipment & on-line System
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ51 | Access to the Canary Care system and equipment which the Business Support team manages on behalf of Adult Social Care Practitioners. | Must have |  | requires collaboration to process the relevant kit/services for the social workers | Adults
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ52 | Incoming Mail - scanning and indexing | Must have |  | requires support to access mail | ICT | Digital Mail is done by BS in Allerdale, South Lakeland, Carlisle. In Copeland Customer Service look after the Post Room which will part of BS going forward. For County we have the Digital Mail team. ALEXANDRA TO FIND OUT WHICH WORKSTREAM THIS FALLS UNDER! - Digital Mail team to be mapped to a workstream
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ52 | Incoming Mail - scanning and indexing | Must have |  | requires collaboration with digital mail
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ53 | Ability to access School's Portal to enable secure comminication to and from schools | Must have |  | requires access to the schools portal | ICT | This role is done by the 'Inclusion Team' specialist BSAs. SYSTEMS USED: Schools Portal
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ53 | Ability to access School's Portal to enable secure comminication to and from schools | Must have |  | requires communication to and from schools | Children's
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ54 | Ability to access CJSM as a secure communication channel with Police | Must have |  | requires communication with | Fire & Rescue and Blue Light Integration | Police - is this mapped to the right workstream? SYSTEMS USED: CJSM (secure communication with the Police)
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ54 | Ability to access CJSM as a secure communication channel with Police | Must have |  | requires communication with | Children's
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ54 | Ability to access CJSM as a secure communication channel with Police | Must have |  | requires access to CJSM system | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ55 | Ability to access LCS and its historical records to ensure the safeguarding of children and young people | Must have |  | requires collaboration with | Children's | This role is done by the 'Children and Young People', 'Early Help' and 'Inclusion' specialist BSAs. SYSTEMS USED: LCS
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ55 | Ability to access LCS and its historical records to ensure the safeguarding of children and young people | Must have |  | requires access to LCS system | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ56 | Ability to access The Foster Care Portal to ensure the secure communication between the service and foster carers | Must have |  | requires communication from fostering and adoption specalist BSAs | Children's | This role is done by the 'Fostering and Adoption' specialist BSAs. SYSTEMS USED: The Foster Care Portal
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ56 | Ability to access The Foster Care Portal to ensure the secure communication between the service and foster carers | Must have |  | requires access to the foster care portal | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ57 | Ability to access the "Letter Box" system to enable birth parents to communicate with their adopted children | Must have |  | requires communication from fostering and adoption specialist BSAs | Children's | This role is done by the 'Fostering and Adoption' specialist BSAs. SYSTEMS USED: Letter box system
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ57 | Ability to access the "Letter Box" system to enable birth parents to communicate with their adopted children | Must have |  | requires access to the letter box system | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ58 | Ability to access the "Core Plus" system to ensure the YOS statutory duties are fulfilled in line with the Youth Justice Board | Must have |  | requires communication from the youth offending team specialist BSAs | Children's | This role is done by the 'Youth Offending Team' specialist BSAs SYSTEMS USED: Core Plus System
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ58 | Ability to access the "Core Plus" system to ensure the YOS statutory duties are fulfilled in line with the Youth Justice Board | Must have |  | requires access to the core plus system | ICT
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ59 | Access to inhouse Housing Management System (Civica CX) | Must have | requires access to Civica CX |  | ICT | Barrow Business Support carry out a number of essential functions on their inhouse Housing Management system that will need to be safe and legal to use on day 1, functions include: ability to start and end tenancies; make rent account adjustments; process and create direct debits; run arrears policies for former tenant and current tenant arrears; run a number of system schedules including but not limited to schedules to post rents and benefit payments and adjustments; post direct debits and payment (including DWP payments) to rent accounts. To manage Leaseholders enquiries (repair and non repair related), produce Leasholder Service charge/minor repair statements/invoices. SYSTEMS USED: Civica CX
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ60 | Civica CX (Barrow) interfaces into Barrows finance system - these interfaces need to work with any new finance or Revs and Bens system | Must have |  | requires access to Civica CX | ICT | CX Housing interfaces with Oracle and AIM to receive and post payments from the finance system, it also outputs to Oracle (via a file share process that converts the file) to pay contractors and provide reconciliation data to finance. There is also an interface with the Revs and Bens system (Northgate) to send tenant data and receive entitlements and payments and adjustments to rent accounts. There is also an inteface with AUDIS for direct debits. SYSTEMS USED: Civica CX
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ60 | Civica CX (Barrow) interfaces into Barrows finance system - these interfaces need to work with any new finance or Revs and Bens system | Must have |  | requires support to understand revs and bens | Finance
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ61 | Access to the Cx Report tool to enable operational and validation reports to be produced | Must have |  | requires access to Civica CX, SQL server reports | ICT | Regulatory services - double check it's legal and democratic SQL Server Report Services are used linked to the Cx database for reporting. These reports are used for financial reconciliation and other reporting purposes and undepin the work of some Officers (Barrow Housing Team) SYSTEMS USED: Civica CX, SQL Server Reports
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ61 | Access to the Cx Report tool to enable operational and validation reports to be produced | Must have |  | requires collaboration to adhere to regulation | Legal & Democratic Services
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ62 | Ability to access the Planning & Building Control, Public Protections and in house Parking System to create licences, licence badges and taxi plates, producing letters and notices – a lot of standard letters and notices are linked as mergeable documents in Flare ; also used to store documents as scanned documents, photos etc | Must have |  | requires access to DBOSS, civica flair, imperial 3 sixty | ICT | Regulatory services - double check its legal and democratic Planning & Building Control have a bespoke inhouse system called DBOSS ; Public Protections inhouse system is Civica FLAIR; Parkings inhouse system is Imperial 3Sixty. Our systems are used for the processing of new planning applications, building control applications and land charges searches. Planning applications need to be online and in the public domain for consultation. Planning Committee reports need to be prepared and also be the public domain. Decision Notices for both planning and building control are time sensitive. The return of local land charges searches are also time sensitive. 3Sixty is used to download Fixed Penalty Notices and process these throught the escalation framework as well as to log and deal with parking appeals. The Flair system also holds all our licensing information, complaints that the Business Support housing team deals with as well as inspection information relating to food businesses. SYSTEMS USED: DBOSS, Civica Flair, Imperial 3 Sixty
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ62 | Ability to access the Planning & Building Control, Public Protections and in house Parking System to create licences, licence badges and taxi plates, producing letters and notices – a lot of standard letters and notices are linked as mergeable documents in Flare ; also used to store documents as scanned documents, photos etc | Must have |  | requires collaboration to adhere to regulation surrounding planning application | Legal & Democratic Services
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ63 | Ability to process and administer Right to Buy (RTB) Applications through to completion (Barrow specific) | Must have |  | requires access to web mapping and land registry | ICT | Barrow BC Business Support team administer the RTB process from application through to instructing the Valuer and composing offer notice to buyers as well as agreeing completion dates with conveyancers. BS will need to have the ability to instruct a Valuer and paperwork will need to refer to the new Authority (inc seal). Land Registry details will need to be up to date. The Head of Business Support at Barrow also check plans related to RTB applications so need access to WebMapping and Land Registry to do this SYSTEMS USED: Access to Web mapping and Land Registry
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ63 | Ability to process and administer Right to Buy (RTB) Applications through to completion (Barrow specific) | Must have |  | requires collaboration to adhere to regulation | Legal & Democratic Services
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ64 | Ability to manage their 19 shop leases via the CIVICA CX System | Must have |  | requires access to civica CX, land registry website | ICT | Barrow BC Business Support also manage shop lease accounts for 19 shops located on Housing estates. Access to Cx should enable us to continue to do this. This is Specific to Barrow Housing Business Support Specialists (For all of these landlord details will need to be up to date for us to legally act as their landlord under a new Authority) The Head of Business Support also drafts Head Terms of Lease for Shop Tennants. SYSTEMS USED: Civica CX, Land Registry Website
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ64 | Ability to manage their 19 shop leases via the CIVICA CX System | Must have |  | requires collaboration to adhere to regulation regarding leasing | Legal & Democratic Services
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ65 | Access to uptodate Landlord data for the Barrow Housing Team as they need to ensure that Tenants are notified of who their new landlord is through the correct legal process | Must have |  | requires support to illicit communications between landlords and tenants | ICT | Barrow BC Housing stock tenants, garage tenants and also leaseholders (both flats and commercial shops) will need to be notified legally as to the change in landlord.
Corporate and Enabling Services |  | Administration and Business Support | ADMIN-REQ65 | Access to uptodate Landlord data for the Barrow Housing Team as they need to ensure that Tenants are notified of who their new landlord is through the correct legal process | Must have |  | requires collaboration to adhere to regulation regarding leasing | Legal & Democratic Services
Total Day 1 Requirements for: Administration and Business Support = 65 Total inter/dependencies for: Administration and Business Support = 108
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ1 | Secure storage of records. Meet the legal requirement to keep personal data secure and confidential (under Data Protection Act 2018). | Must have |  | requires support for data protection | Records Management work package | District and Borough Councils links to County Records Management Service and other places of deposit/ archival storage.
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ1 | Secure storage of records. Meet the legal requirement to keep personal data secure and confidential (under Data Protection Act 2018). | Must have |  | needs collaboration for the safe storage of records | ICT
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ1 | Secure storage of records. Meet the legal requirement to keep personal data secure and confidential (under Data Protection Act 2018). | Must have |  | data protection information needs communicating to | All services - all employees
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ2 | Timely access to information - including Police requests, SARs, Legal, Social Care, Highways, Pensions, Human Resources. In order to ensure efficient service delivery and business continuity; and meet legal requirements to answer information requests (such as FOIA 2000, EIR 2004, DPA 2018). | Must have |  | requires support for data protection | Records Management work package | Deployment of automated search process and explore options.
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ2 | Timely access to information - including Police requests, SARs, Legal, Social Care, Highways, Pensions, Human Resources. In order to ensure efficient service delivery and business continuity; and meet legal requirements to answer information requests (such as FOIA 2000, EIR 2004, DPA 2018). | Must have |  | data protection information needs communicating to | All services - all employees
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ2 | Timely access to information - including Police requests, SARs, Legal, Social Care, Highways, Pensions, Human Resources. In order to ensure efficient service delivery and business continuity; and meet legal requirements to answer information requests (such as FOIA 2000, EIR 2004, DPA 2018). | Must have |  | requires support from | FOI/SAR, Comments, Compliments & Complaints
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ3 | Legitimate (Data Subject Access Requests) access to information. To meet legal requirement under Data Protection Act 2018. | Must have |  | requires support for data protection | Records Management work package
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ3 | Legitimate (Data Subject Access Requests) access to information. To meet legal requirement under Data Protection Act 2018. | Must have |  | data protection information needs communicating to | All services - all employees
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ3 | Legitimate (Data Subject Access Requests) access to information. To meet legal requirement under Data Protection Act 2018. | Must have |  | requires support from | FOI/SAR, Comments, Compliments & Complaints
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ4 | Transparency Arrangements – registering with Information Commissioners Office, publishing of data and information in line with Local Government Transparency Code 2015, Publication Scheme under FOI Act 2000, Privacy Notices (Corporate and Service Specific) in line with data protection legislation. | Must have |  | requires support for data protection and transparency arrangements | Records Management work package | Agreed templates and relevant information sourced and published. Proposal to fully incorporate into Information Governance Role Profiles so there is clear responsibility assigned Risk that any arrangement(s) slips and leads to a rise in FOIs that could be handled differently/ refused.
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ4 | Transparency Arrangements – registering with Information Commissioners Office, publishing of data and information in line with Local Government Transparency Code 2015, Publication Scheme under FOI Act 2000, Privacy Notices (Corporate and Service Specific) in line with data protection legislation. | Must have |  | transparency arrangements need communicating wto | All services - all employees
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ4 | Transparency Arrangements – registering with Information Commissioners Office, publishing of data and information in line with Local Government Transparency Code 2015, Publication Scheme under FOI Act 2000, Privacy Notices (Corporate and Service Specific) in line with data protection legislation. | Must have |  | requires support from | FOI/SAR, Comments, Compliments & Complaints
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ5 | Staff knowledge to be able to provide Information Governance advice. | Must have |  | requires collaboration with | HR & OD | Critical requirement. Funding to be identified for induction and refresher training for all Information Governance staff.
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ5 | Staff knowledge to be able to provide Information Governance advice. | Must have |  | requires technical knowledge from | Records Management work package
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ5 | Staff knowledge to be able to provide Information Governance advice. | Must have |  | requires relevant knowledge from | All services - all employees
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ5 | Staff knowledge to be able to provide Information Governance advice. | Must have |  | needs support from | FOI/SAR, Comments, Compliments & Complaints
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ6 | Data Protection Officer in place. To meet legal requirement under Data Protection Act 2018. Other posts required: • Caldicott Guardians • Senior Information Risk Officers (SIRO(s)) • Information Asset Owners (IAO) • Information Asset Administrators (IAA). | Must have |  | requires technical support from | Records Management work package | Identification of SIRO/ Caldicott Guardian (CG) is critical going forward. CG specifically needs to be assigned with clear responsibility/ resourcing. Identification and training of IAOs/IAAs must be identified and trained as a priority. It must also be included in Role Profiles to clearly embed responsibilities.
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ6 | Data Protection Officer in place. To meet legal requirement under Data Protection Act 2018. Other posts required: • Caldicott Guardians • Senior Information Risk Officers (SIRO(s)) • Information Asset Owners (IAO) • Information Asset Administrators (IAA). | Must have |  | requires training and communication to | All services - all employees
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ6 | Data Protection Officer in place. To meet legal requirement under Data Protection Act 2018. Other posts required: • Caldicott Guardians • Senior Information Risk Officers (SIRO(s)) • Information Asset Owners (IAO) • Information Asset Administrators (IAA). | Must have |  | needs collaboration with | FOI/SAR, Comments, Compliments & Complaints
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ7 | Risk Assessment Review - is there a requirement to carry out Data Protection Impact Assessments? Review of current Information Sharing Agreements currently in Place - notably with Police and Health Services. Data Breach protocols in place to meet requirements under data protection legislation. | Must have |  | requires technical support and risk assessment from | Records Management work package | Needs to be built into commissioning and other processes to allow early engagement.
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ7 | Risk Assessment Review - is there a requirement to carry out Data Protection Impact Assessments? Review of current Information Sharing Agreements currently in Place - notably with Police and Health Services. Data Breach protocols in place to meet requirements under data protection legislation. | Must have |  | requires support from | All services - all employees
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ7 | Risk Assessment Review - is there a requirement to carry out Data Protection Impact Assessments? Review of current Information Sharing Agreements currently in Place - notably with Police and Health Services. Data Breach protocols in place to meet requirements under data protection legislation. | Must have |  | requires support from | FOI/SAR, Comments, Compliments & Complaints
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ8 | Secure and timely transfer arrangements in place through appropriate Data Sharing and Data Processing Agreements - links to Information Sharing Gateway (ISG). | Must have |  | needs collaboration with | Strategic Procurement / Strategy​ | Proposal to link these two together and use the ISG to deliver both DPIAs/ ISAs. An ISG is fit for purpose and meets public sector requirements.
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ8 | Secure and timely transfer arrangements in place through appropriate Data Sharing and Data Processing Agreements - links to Information Sharing Gateway (ISG). | Must have |  | requires support from | Records Management work package
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ8 | Secure and timely transfer arrangements in place through appropriate Data Sharing and Data Processing Agreements - links to Information Sharing Gateway (ISG). | Must have |  | information needs communicating to | All services - all employees
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ9 | ICT requirements - on top of standard Microsoft packages (including SharePoint) - provision and support of specialist software/ hardware (and third party maintenance contracts) including the following: • Allerdale – InformU • Barrow – Epilog system, Technology Forge, Back Office system • Copeland - Pentana • County - SharePoint, Netcall, Liberty Create, Liquid Logic LAS & LCS/ EHM, ITrent, Objective Redact. • South Lakeland - Information@Work. | Must have |  | requires help with MS packages, sharepoint, and specalist soft/hardware | ICT
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ9 | ICT requirements - on top of standard Microsoft packages (including SharePoint) - provision and support of specialist software/ hardware (and third party maintenance contracts) including the following: • Allerdale – InformU • Barrow – Epilog system, Technology Forge, Back Office system • Copeland - Pentana • County - SharePoint, Netcall, Liberty Create, Liquid Logic LAS & LCS/ EHM, ITrent, Objective Redact. • South Lakeland - Information@Work. | Must have |  | requires support from | Strategic Procurement / Strategy​
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ9 | ICT requirements - on top of standard Microsoft packages (including SharePoint) - provision and support of specialist software/ hardware (and third party maintenance contracts) including the following: • Allerdale – InformU • Barrow – Epilog system, Technology Forge, Back Office system • Copeland - Pentana • County - SharePoint, Netcall, Liberty Create, Liquid Logic LAS & LCS/ EHM, ITrent, Objective Redact. • South Lakeland - Information@Work. | Must have |  | in collaboration with | Children's | Fostering & Adoption
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ10 | Health & Safety requirements - Risk Assessments written and implemented through Information Governance Board. | Must have | requires technical support from |  | Health & Safety | CCTV, home or lone working
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ11 | Storage space and a clear process for records being transferred – including urgent transfers like a Care Home or building closing. Risk breach of Information Security if records left in unoccupied buildings. | Must have |  | requires support to organise space and storage | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ11 | Storage space and a clear process for records being transferred – including urgent transfers like a Care Home or building closing. Risk breach of Information Security if records left in unoccupied buildings. | Must have |  | requires support to manage records and data security | Records Management work package
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ11 | Storage space and a clear process for records being transferred – including urgent transfers like a Care Home or building closing. Risk breach of Information Security if records left in unoccupied buildings. | Must have |  | requires technical support from |  | Need to map 'third party consultants' to a workstream
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ11 | Storage space and a clear process for records being transferred – including urgent transfers like a Care Home or building closing. Risk breach of Information Security if records left in unoccupied buildings. | Must have |  | require support with data protection and security |  | Need to map 'information security' to a workstream
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ12 | Disposals of records up-to-date and disposal logs kept (recording what has been destroyed). So that when services are aggregated and disaggregated, all Councils are only holding records still within their retention period. Meeting legal requirement not to keep personal data for longer than necessary (under Data Protection Act 2018). | Must have | requires collaboration and communication with |  | All services - all employees | Having an agreed Records Management Policy supported by a Retention and Disposal Schedule is critical for achieving compliance with the UK GDPR and cannot be overlooked. Even if it is an ‘in principle’ document, work on combining existing schedules should be straightforward as there is limited service crossover.
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ13 | Retention Schedules up-to-date within each Council. These include various pieces of legislation that outline how long specific records should be kept by organisations. | Must have |  | needs communicating to | All services - all employees | Having an agreed Records Management Policy supported by a Retention and Disposal Schedule is critical for achieving compliance with the UK GDPR and cannot be overlooked. Even if it is an ‘in principle’ document, work on combining existing schedules should be straightforward as there is limited service crossover.
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ13 | Retention Schedules up-to-date within each Council. These include various pieces of legislation that outline how long specific records should be kept by organisations. | Must have |  | requires support to understand GDPR compliance | Records Management work package
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ14 | Disposals of records in services/ offices up-to-date | Must have | requires communication of record disposal to |  | All services - all employees
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ15 | Carry out information audits of each service - to establish what is held by services, volume, how long they are being kept, and that they are listed on the Retention Schedule. | Must have | requires collaboration and communication with |  | All services - all employees
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ16 | Potential network rationalisation for digital records. | Must have | requires technical support from |  |  | Need to map 'third party consultants' to a workstream
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ17 | Update Information Security and Data Protection Training. | Must have |  | requires support from | HR & OD
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ17 | Update Information Security and Data Protection Training. | Must have |  | requires technical support from | Information Governance
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ17 | Update Information Security and Data Protection Training. | Must have |  | requires technical support from |  | Need to map 'information security' to a workstream
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ18 | Retention Schedule links more with Information Asset Register. | Must have | requires technical support from |  | Records Management work package
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ19 | Communicate to all staff in new Authorities about Information Governance and Data Protection. | Must have | requires support communicating to all staff about info governance |  | Communications and Engagement
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ20 | CCTV Governance | Must have | requires support from |  | Records Management work package | Responsibility for CCTV governance/arrangements has been laid out by the Biometrics and Surveillance Camera Commissioner, this includes registering a named Senior Responsible Officer. So, the new authorities would be required to have the same governance/registration arrangements in place as we do for Data Protection purposes with the Information Commissioner’s Office.
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ21 | Business Classification scheme in place for both unitary councils - including Records Retention Schedule, Information Asset Register and Record of Processing Activity - in accordance with Data Protection Legislation and Information Governance Standards. | Should have |  | legislative standards need communicating to | All services - all employees
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ21 | Business Classification scheme in place for both unitary councils - including Records Retention Schedule, Information Asset Register and Record of Processing Activity - in accordance with Data Protection Legislation and Information Governance Standards. | Should have |  | requires support setting up systems with | ICT
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ21 | Business Classification scheme in place for both unitary councils - including Records Retention Schedule, Information Asset Register and Record of Processing Activity - in accordance with Data Protection Legislation and Information Governance Standards. | Should have |  | requires collaboration to understand data security and legislative standards | Records Management work package
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ22 | Information Governance Framework in place for both unitary councils: • Acceptable Use Policy and Protocols • Data Quality Policy and Protocols • Information Compliance Policy and Protocols • Information Security Policy and Protocols • Information Sharing Policy and Protocols • Records Retention Policy and Protocols. | Should have |  | requires collaboration and communication of protocol with | All services - all employees
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ22 | Information Governance Framework in place for both unitary councils: • Acceptable Use Policy and Protocols • Data Quality Policy and Protocols • Information Compliance Policy and Protocols • Information Security Policy and Protocols • Information Sharing Policy and Protocols • Records Retention Policy and Protocols. | Should have |  | requires collaboration to establish protocols | Records Management work package
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ22 | Information Governance Framework in place for both unitary councils: • Acceptable Use Policy and Protocols • Data Quality Policy and Protocols • Information Compliance Policy and Protocols • Information Security Policy and Protocols • Information Sharing Policy and Protocols • Records Retention Policy and Protocols. | Should have |  | requires collaboration to establish protocols | ICT
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ22 | Information Governance Framework in place for both unitary councils: • Acceptable Use Policy and Protocols • Data Quality Policy and Protocols • Information Compliance Policy and Protocols • Information Security Policy and Protocols • Information Sharing Policy and Protocols • Records Retention Policy and Protocols. | Should have |  | requires collaboration to establish protocols | FOI/SAR, Comments, Compliments & Complaints
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ22 | Information Governance Framework in place for both unitary councils: • Acceptable Use Policy and Protocols • Data Quality Policy and Protocols • Information Compliance Policy and Protocols • Information Security Policy and Protocols • Information Sharing Policy and Protocols • Records Retention Policy and Protocols. | Should have |  | requires collaboration to establish protocols |  | Need to map 'information security management system' to a workstream
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ23 | Confidential waste contract in place, including ability to have onsite purge shreds. | Should have |  | requires support to decipher the procedure for confidential waste disposal | Strategic Procurement / Strategy​ | Approach to handling confidential waste needs to be established at an early stage. In office provision needs to be clear from the outset, mainly to avoid unnecessary data breaches.
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ23 | Confidential waste contract in place, including ability to have onsite purge shreds. | Should have |  | requires support to decipher the procedure for confidential waste disposal | Records Management work package
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ24 | Establish disposal permissions contacts for legacy records (for records created pre-April 2023). | Should have |  | requires communicating disposal protocol to | All services - all employees | Any conversations relating to Records Management shouldn’t be derailed by introducing this, the focus should be on new arrangements. Too much time has been spent securing permission to destroy legacy records. The upshot of this is that decision making should not be assigned to a specific individual. Retention should be dictated by two things: legal obligations and business requirements. This applies to both physical and electronic records.
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ24 | Establish disposal permissions contacts for legacy records (for records created pre-April 2023). | Should have |  | requires support to decipher the procedure for confidental disposal | Records Management work package
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ25 | Resources to scan records if requested electronically (staff, equipment, and software) - including Children’s Services SAR requests that County currently search, retrieve, and scan records for. Retention periods on Retention Schedules amalgamated and agreed for each new Authority. Records Management Policies and guidance amalgamated and put on intranet pages for each new Authority. Policies should be approved beforehand. CCTV Policy and Protocols including links to Surveillance Camera Code of Practice and Regulatory of Investigatory Powers Act 2000 (RIPA). | Should have |  | requires support and collaboration to establish record management policy/ retention schedules | FOI/SAR, Comments, Compliments & Complaints | Double check IG Board = information governance as the correct interdependency Relates to non-current/ archived records relating to Children. Review CCTV operation across all 7 authorities. CCTV/ Surveillance is a separate work-stream in my opinion and links in with a number of other teams/ services.
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ25 | Resources to scan records if requested electronically (staff, equipment, and software) - including Children’s Services SAR requests that County currently search, retrieve, and scan records for. Retention periods on Retention Schedules amalgamated and agreed for each new Authority. Records Management Policies and guidance amalgamated and put on intranet pages for each new Authority. Policies should be approved beforehand. CCTV Policy and Protocols including links to Surveillance Camera Code of Practice and Regulatory of Investigatory Powers Act 2000 (RIPA). | Should have |  | requires support and collaboration to establish record management policy/ retention schedules | All services - all employees
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ25 | Resources to scan records if requested electronically (staff, equipment, and software) - including Children’s Services SAR requests that County currently search, retrieve, and scan records for. Retention periods on Retention Schedules amalgamated and agreed for each new Authority. Records Management Policies and guidance amalgamated and put on intranet pages for each new Authority. Policies should be approved beforehand. CCTV Policy and Protocols including links to Surveillance Camera Code of Practice and Regulatory of Investigatory Powers Act 2000 (RIPA). | Should have |  | requires support and collaboration to establish record management policy/ retention schedules | Records Management work package
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ25 | Resources to scan records if requested electronically (staff, equipment, and software) - including Children’s Services SAR requests that County currently search, retrieve, and scan records for. Retention periods on Retention Schedules amalgamated and agreed for each new Authority. Records Management Policies and guidance amalgamated and put on intranet pages for each new Authority. Policies should be approved beforehand. CCTV Policy and Protocols including links to Surveillance Camera Code of Practice and Regulatory of Investigatory Powers Act 2000 (RIPA). | Should have |  | requires support and collaboration to establish record management policy/ retention schedules | Information Governance
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ25 | Resources to scan records if requested electronically (staff, equipment, and software) - including Children’s Services SAR requests that County currently search, retrieve, and scan records for. Retention periods on Retention Schedules amalgamated and agreed for each new Authority. Records Management Policies and guidance amalgamated and put on intranet pages for each new Authority. Policies should be approved beforehand. CCTV Policy and Protocols including links to Surveillance Camera Code of Practice and Regulatory of Investigatory Powers Act 2000 (RIPA). | Should have |  | requires support and collaboration to establish record management policy/ retention schedules | Strategic Procurement / Strategy​
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ25 | Resources to scan records if requested electronically (staff, equipment, and software) - including Children’s Services SAR requests that County currently search, retrieve, and scan records for. Retention periods on Retention Schedules amalgamated and agreed for each new Authority. Records Management Policies and guidance amalgamated and put on intranet pages for each new Authority. Policies should be approved beforehand. CCTV Policy and Protocols including links to Surveillance Camera Code of Practice and Regulatory of Investigatory Powers Act 2000 (RIPA). | Should have |  | requires support and collaboration to establish record management policy/ retention schedules | Property, Asset Strategy and Property Maintenance
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ26 | Future move towards electronic records, including potential classification scheme, implementation of organisation wide system, and joining up information assets (electronic and paper records). | Could have |  | requires support to move towards electronic records | ICT
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ26 | Future move towards electronic records, including potential classification scheme, implementation of organisation wide system, and joining up information assets (electronic and paper records). | Could have |  | requires collaboration and communication of electronic record management | All services - all employees
Corporate and Enabling Services |  | Information Governance | INFGOV-REQ26 | Future move towards electronic records, including potential classification scheme, implementation of organisation wide system, and joining up information assets (electronic and paper records). | Could have |  | requires collaboration to establish electronic record management | Records Management work package
Total Day 1 Requirements for: Information Governance = 26 Total inter/dependencies for: Information Governance = 66

## Day1 Reqs&Depends (ICT)
Day1 Requirements & Inter/Dependencies (ICT)
|  |  |  | DEFINITIONS: |  |  |  | KEY FOR COMMENTS SECTION:
|  |  |  | Dependency: Reliance on just one other area to address requirement |  |  |  | Question about whether the workstream has been mapped correctly
|  |  |  | Interdependency: Reliance across multiple areas to address requirement |  |  |  | Remaining interdependencies that I cannot map / unsure about mapping to existing workstreams
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency (what is required from elsewhere in the programme?) | Interdependency (numerous interdependencies from elsewhere in the programme) | With | Comment | Date needed by | Approved?
ICT |  | End User Computing | ICT-REQ1 | Staff will have access to the systems and data they need to be able to do their jobs | Must have | is dependant on |  | ICT
ICT |  | Systems | ICT-REQ2 | Payroll system for new authorities to be in place | Must have |  | is interdependent | HR & OD
ICT |  | Systems | ICT-REQ2 | Payroll system for new authorities to be in place | Must have |  | is interdependent | Finance
ICT |  | End User Computing | ICT-REQ3 | Accommodation Plan setting out the physical local of all services for each council | Must have | is dependant on |  | Property, Asset Strategy and Property Maintenance
ICT |  | Telephony | ICT-REQ4 | Telephony systems are in place for new organisations | Must have |  | is interdependent | Customer & Digital
ICT |  | Telephony | ICT-REQ4 | Telephony systems are in place for new organisations | Must have |  | is interdependent | ICT
ICT |  | ICT | ICT-REQ5 | New contact centre numbers will be in place for new authorities - configured to a new call routing configuration | Must have |  | is interdependent | ICT
ICT |  | ICT | ICT-REQ5 | New contact centre numbers will be in place for new authorities - configured to a new call routing configuration | Must have |  | is interdependent | Customer & Digital
ICT |  | ICT | ICT-REQ6 | IT systems for contact centres to be in place. | Must have | is dependant on |  | Customer & Digital
ICT |  | ICT | ICT-REQ7 | Integration and/or data sharing with other partners in the health and care system to be in in place | Should have |  | is interdependent | ICT
ICT |  | ICT | ICT-REQ7 | Integration and/or data sharing with other partners in the health and care system to be in in place | Should have |  | is interdependent | Adults
ICT |  | Virtual Private Networks | ICT-REQ8 | GIS / Spatial Services to be in place | Must have |  | is interdependent | ICT
ICT |  | Virtual Private Networks | ICT-REQ8 | VPN and mobile access to county applications, i.e. Supported Living | Must have |  | is interdependent | Adults
ICT |  | Data Centres | ICT-REQ9 | Data centres in place and operational as required for each authority - with a minimum set of requirements such as backup power supply and contracts in place for replacement equipment | Must have | is dependant on |  | ICT
ICT |  | Data Centres | ICT-REQ10 | Staff across both councils will need access to data centres as required | Must have | is dependant on |  | ICT
ICT |  | Data Centres | ICT-REQ11 | Relevant access control and permissions in place for the data centre | Must have | is dependant on |  | ICT
ICT |  | End User Computing | ICT-REQ12 | ICT will require procurement and legal progress guidance for each of the new authorities. | Should have |  | is interdependent | Contract Management/Monitoring
ICT |  | End User Computing | ICT-REQ12 | ICT will require procurement and legal progress guidance for each of the new authorities. | Should have |  | is interdependent | Legal & Democratic Services
ICT |  | ICT Service Support | ICT-REQ13 | The right skills and resources / capacity to effectively deliver ICT support services to each new Council | Must have |  | is interdependent | HR & OD
ICT |  | ICT Service Support | ICT-REQ13 | The right skills and resources / capacity to effectively deliver ICT support services to each new Council | Must have |  | is interdependent | Finance
ICT |  | ICT Service Support | ICT-REQ13 | The right skills and resources / capacity to effectively deliver ICT support services to each new Council | Must have |  | is interdependent | ICT
ICT |  | End User Computing | ICT-REQ14 | Clear process for deploying laptops / tablets / mobile phone equipment to staff and new starters for each authority. | Must have | is dependant on |  | ICT
ICT |  | Active Directory Domains | ICT-REQ15 | Clear process for making changes to Active Directory domains in place for each authority | Must have | is dependant on |  | ICT
ICT |  | Virtual Private Networks | ICT-REQ16 | Virtual Private Networks in place for both authorities | Must have | is dependant on |  | ICT
ICT |  | Virtual Private Networks | ICT-REQ17 | All staff who need it have VPN access to the council's systems | Must have | is dependant on |  | ICT
ICT |  | Microsoft Enterprise Agreement | ICT-REQ18 | One Microsoft Enterprise agreement to be in place for each new unitary | Must have |  | is interdependent | ICT
ICT |  | Microsoft Enterprise Agreement | ICT-REQ18 | One Microsoft Enterprise agreement to be in place for each new unitary | Must have |  | is interdependent | Legal & Democratic Services
ICT |  | ICT | ICT-REQ19 | Microsoft Cloud / O365 to be set up and configured for both authorities ready for day 1 | Must have | is dependant on |  | ICT
ICT |  | Non Microsoft Cloud | ICT-REQ20 | Other cloud services required for day 1 to be in place | Won't have | is dependant on |  | ICT | Actions: Understanding of what existing cloud services are currently in place and need to novate to new councils. No actions required for day 1.
ICT |  | Information Security | ICT-REQ21 | All ICT systems and services will be compliant with legal and regulatory obligations / Cyber security measures to be in place to meet accreditation requirements | Must have |  | is interdependent | Information Governance
ICT |  | Information Security | ICT-REQ21 | All ICT systems and services will be compliant with legal and regulatory obligations / Cyber security measures to be in place to meet accreditation requirements | Must have |  | is interdependent | Legal & Democratic Services
ICT |  | Information Security | ICT-REQ22 | IT networks will be PSN compliant | Must have | is dependant on |  | ICT
ICT |  | Information Security | ICT-REQ23 | ICT data and systems will meet the National Data Guardian's 10 data security standards | Must have | is dependant on |  | ICT
ICT |  | Information Security | ICT-REQ24 | An Acceptable Use Policy will be in place and all users will have read it, understood it and signed to confirm they accept it. | Must have | is dependant on |  | ICT
ICT |  | Information Security | ICT-REQ25 | Agreed Information Security Policies will be in place | Must have | is dependant on |  | ICT
ICT |  | LLPG | ICT-REQ26 | LLPG to be updated with new LA boundaries and in place | Must have | is dependant on |  | ICT
ICT |  | GIS | ICT-REQ27 | GIS / Spatial Services to be in place | Should have | is dependant on |  | ICT
ICT |  | ICT | ICT-REQ28 | Intranet sites for new authorities to be in place | Should have |  | is interdependent | ICT
ICT |  | ICT | ICT-REQ28 | Intranet sites for new authorities to be in place | Should have |  | is interdependent | Communications and Engagement
ICT |  | ICT | ICT-REQ29 | Websites for new authorities to be in place - replacing all existing council websites | Must have |  | is interdependent | ICT
ICT |  | ICT | ICT-REQ30 | Websites for new authorities to be in place and customer will continue to be able to access online services | Must have |  | is interdependent | Communications and Engagement
ICT |  | ICT | ICT-REQ30 | Websites for new authorities to be in place and customer will continue to be able to access online services | Must have |  | is interdependent | Customer & Digital
ICT |  | Back Up and Disaster Recovery | ICT-REQ31 | Back up and disaster recovery to be in place | Must have | is dependant on |  | ICT
ICT |  | Active Directory Domains | ICT-REQ32 | Access to all employees' calendars within each authority will be in place | Must have | is dependant on |  | ICT
ICT |  | End User Computing | ICT-REQ33 | Print facilities across the main offices will be in place | Should have | is dependant on |  | ICT
ICT |  | Networks | ICT-REQ34 | Wi-Fi access to be in place across all relevant council buildings for each unitary | Should have | is dependant on |  | ICT
ICT |  | Systems | ICT-REQ35 | Door access /entry badges to be in place across relevant council office buildings | Must have |  | is interdependent | ICT
ICT |  | Systems | ICT-REQ35 | Door access /entry badges to be in place across relevant council office buildings | Must have |  | is interdependent | Property, Asset Strategy and Property Maintenance
ICT |  | ICT | ICT-REQ36 | ICT Strategies for each authority to be in place | Should have | is dependant on |  | ICT
ICT |  | ICT Service Support | ICT-REQ37 | ICT Customer service level agreements to be in place for each new authority to manage customer expectations in relation to core ICT services | Should have | is dependant on |  | ICT
ICT |  | ICT Service Support | ICT-REQ38 | ICT Incident management systems to be in place to moitor and respond to service disruptions within SLA | Should have | is dependant on |  | ICT
ICT |  | ICT Service Support | ICT-REQ39 | Ongoing ICT contracts are novated to one of the new authorities | Must have |  | is interdependent | Legal & Democratic Services
ICT |  | ICT Service Support | ICT-REQ39 | Ongoing ICT contracts are novated to one of the new authorities | Must have |  | is interdependent | Council-wide Purchasing (Category Management)​
ICT |  | ICT Service Support | ICT-REQ40 | Ongoing ICT contracts are novated to one of the new authorities | Must have |  | is interdependent | Contract Management/Monitoring
ICT |  | Networks | ICT-REQ41 | Local and Wide Area Networks to continue to provide services as required | Must have | is dependant on |  | ICT
ICT |  | Active Directory Domains | ICT-REQ42 | Active Directory Domains will be connected to enable staff access to systems which both Councils need to access | Must have | is dependant on |  | ICT
ICT |  | ICT Service Support | ICT-REQ43 | ICT Helpdesk including internal customer portal to be in place | Must have | is dependant on |  | ICT
ICT |  | ICT Service Support | ICT-REQ44 | ICT asset register and management process to be in place and up to date | Should have | is dependant on |  | ICT
ICT |  | End User Computing | ICT-REQ45 | Agreed approach to the recycling on redundant equipment to be in place | Could have | is dependant on |  | ICT

## Day1 Reqs & Depends (Finance)
Day1 Requirements & Inter/Dependencies (Finance)
|  |  |  | DEFINITIONS: |  |  |  | KEY FOR COMMENTS SECTION:
|  |  |  | Dependency: Reliance on just one other area to address requirement |  |  |  | Question about whether the workstream has been mapped correctly
|  |  |  | Interdependency: Reliance across multiple areas to address requirement |  |  |  | Remaining interdependencies that I cannot map / unsure about mapping to existing workstreams
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency (what is required from elsewhere in the programme?) | Interdependency (numerous interdependencies from elsewhere in the programme) | With | Comment | Date needed by | Approved?
Finance and Commercial |  | Finance | FIN-REQ1 | Bank Account Set-up Existing bank accounts for all council bodies to be extended for 12 months New bank accounts for unitary authorities to be procured. | Must have | is dependent on |  | ICT
Finance and Commercial |  | Finance | FIN-REQ2 | 2023/24 Financial Budget Approved Work package created, split into three elements: Financial Sustainability Aggregation/ Disaggregation with engagement with LGA Benefits Realisation (consideration to commission to strategic partner for completion) | Must have
Finance and Commercial |  | Finance | FIN-REQ3 | Cash and Petty Cash Arrangements Long-term strategy and management Appropriate Insurance in Place Specific work package created | Must have
Finance and Commercial |  | Finance | FIN-REQ4 | Cash and Petty Cash Arrangements Long-term strategy and management Appropriate Insurance in Place Specific work package created | Must have
Finance and Commercial |  | Finance | FIN-REQ5 | Ability to Collect Debt In Contained within Ledger and Systems work package Requirement to understand ‘all council debt’ position to determine final approach to Day 1 Community finance need to liaise with and include Adult Social Care in debt envelope Confirmation required around where Debt Disputes should reside within the programme | Must have | is dependent on |  | Adults
Finance and Commercial |  | Finance | FIN-REQ6 | Goods & Services Contained within Ledger and Systems work package Consolidated ‘suppler list to be collated for all councils | Must have
Finance and Commercial |  | Finance | FIN-REQ7 | Pension Fund Decision regarding pension fund set-up (single/ multiple pension funds) for new Pension Agreement Presentation to Leaders Forum (4th February) Administration approach to be investigated once Pension Fund set-up agreed | Must have | is dependent on |  | Pension Fund
Finance and Commercial |  | Finance | FIN-REQ8 | Revenues and Benefits Mechanism Scope to be agreed | Must have
Finance and Commercial |  | Finance | FIN-REQ9 | Housing Revenue Account Collections Funds Mechanisms Only one HRA service in Cumbria (Barrow) – this will automatically fall into Westmorland & Furness | Must have
Finance and Commercial |  | Finance | FIN-REQ10 | Ability to Manage Cash Flow (loans & investments) Contained within Treasury and Banking work package District/Borough Working Group established | Must have | is dependent on |  | Treasury Management and Insurance
Finance and Commercial |  | Finance | FIN-REQ11 | Ability to Manage Audit & Risk Specific work package created | Must have | is dependent on |  | Audit
Finance and Commercial |  | Finance | FIN-REQ12 | Ability to Manage Financial Transactions Contained within Ledger and Systems work package – this includes payment cards etc | Must have
Finance and Commercial |  | Finance | FIN-REQ13 | FCA Registration Further discovery required to determine best approach Registrations can commence following Parliamentary approval of Unitary Authorities | Must have
Finance and Commercial |  | Finance | FIN-REQ14 | Accountable Bodies, Companies and Partnerships Develop and agree robust governance procedure | Must have
Finance and Commercial |  | Finance | FIN-REQ15 | Merchant Services Registration of new accounts to ensure payments can be received (i.e., Council Tax) Dependency with ICT for core system application operational for Day 1 | Must have | is dependent on |  | ICT
Finance and Commercial |  | Finance | FIN-REQ16 | Grants Key dependencies with Strategic Commissioning workstream – specific focus on ‘income in’ grants | Must have | is dependent on |  | Strategic Commissioning
Finance and Commercial |  | Finance | FIN-REQ17 | Systems Feeder systems (i.e., schools) to be identified and in place with the appropriate controls for Day 1 All Day 1 systems to be identified including any disaggregation requirement Legacy system closedown approach Key dependency with ICT Workstream | Must have | is dependent on |  | ICT
Finance and Commercial |  | Finance | FIN-REQ18 | New bank accounts for unitary authorities. Clarity on authority procedure required to ascertain approval for procurement | Must have
Finance and Commercial |  | Finance | FIN-REQ19 | Petty Cash long-term strategy development. | Must have
Finance and Commercial |  | Finance | FIN-REQ20 | Ability to raise Invoices requires a strategic decision required no later than March 2022 | Must have
Finance and Commercial |  | Finance | FIN-REQ21 | Ability to Manage Cash Flow (loans & investments) - Decision required around how advice and guidance will be provided to the Shadow Authorities regarding Budget creation | Must have
Finance and Commercial |  | Finance | FIN-REQ22 | Decision required around how advice and guidance will be provided to the Shadow Authorities regarding Budget creation | Must have

## Day1 Reqs&Depends (People)
Day1 Requirements & Inter/Dependencies (People)
|  |  |  | DEFINITIONS: |  |  |  | KEY FOR COMMENTS SECTION:
|  |  |  | Dependency: Reliance on just one other area to address requirement |  |  |  | Question about whether the workstream has been mapped correctly
|  |  |  | Interdependency: Reliance across multiple areas to address requirement |  |  |  | Remaining interdependencies that I cannot map / unsure about mapping to existing workstreams
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency (what is required from elsewhere in the programme?) | Interdependency (numerous interdependencies from elsewhere in the programme) | With | Comment | Date needed by | Approved?
People | Children's - General Requirements | Children's | CHIL-REQ1 | Live cases allocated to appropriate authorities and case reporting system that contains the case history for the appropriate authority | Must have
People | Children's - General Requirements | Children's | CHIL-REQ2 | Secure data sharing methodology / governance / compliance in place | Must have
People | Children's - General Requirements | Children's | CHIL-REQ3 | All ongoing works are allocated owners and have uninterrupted transition | Must have
People | Children's - General Requirements | Children's | CHIL-REQ4 | Appropriate meeting space in each locality for partners | Must have
People | Children's - General Requirements | Children's | CHIL-REQ5 | Access to legal advice | Must have | requires support from |  | Legal & Democratic Services
People | Children's - General Requirements | Children's | CHIL-REQ6 | All legal documents such as contracts, agreement and partnerships must be rewritten and in place prior to go live. | Must have | requires support from |  | Legal & Democratic Services
People | Children's - General Requirements | Children's | CHIL-REQ7 | Management of legal documents that we hold (e.g., instruments of governance) is securely in place across both areas. | Must have | requires support from |  | Legal & Democratic Services
People | Children's - General Requirements | Children's | CHIL-REQ8 | Complaints and Tribunal process’/Legal Support | Must have | requires support from |  | Legal & Democratic Services
People | Children's - General Requirements | Children's | CHIL-REQ9 | Mediation Contracts | Must have | requires support from |  | Legal & Democratic Services
People | Children's - General Requirements | Children's | CHIL-REQ10 | Social work, children's homes and EHCP social care advice are statutory, and laws and regulation shape these services. | Must have | requires support from |  | Legal & Democratic Services
People | Children's - General Requirements | Children's | CHIL-REQ11 | Data sharing agreement | Must have | requires support from |  | Legal & Democratic Services
People | Children's - General Requirements | Children's | CHIL-REQ12 | Access to insurance documents | Must have | requires support from |  | Legal & Democratic Services
People | Children's - General Requirements | Children's | CHIL-REQ13 | Audit and assurance | Must have | requires support from |  | Legal & Democratic Services
People | Children's - General Requirements | Children's | CHIL-REQ14 | Arrangements in place for safe transfer of cases - may be ongoing cases where practitioner will change and so need to agree a process to do this safely and in a ‘person centred’ way between new unitary councils and teams. | Must have | requires support from |  | Legal & Democratic Services
People | Children's - General Requirements | Children's | CHIL-REQ15 | Email | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ16 | Telephones | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ17 | ICT Networks, systems, VPN and support | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ18 | Access to ICT systems: HR, Finance, InTouch | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ19 | Access to service specific ICT Systems | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ20 | Access to Apps like Google Authenticator | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ21 | Social Media | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ22 | CRM Systems & Portals | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ23 | Access to booking systems for meeting rooms/ Pool Cars/ Holidays | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ24 | Acces to Websites | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ25 | VPN Access | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ26 | Access to shared mailbox accounts | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ27 | Access to customer and staff files | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ28 | Access to submit expenses | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ29 | Ability to share information electronically (Police & Health) | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ30 | Whatsapp & Text Messaging | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ31 | Electronic Files to be available | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ32 | Records from current Cumbria system integrated. | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ33 | Case recording system | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ34 | Licencing | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ35 | GDPR compliant data sharing model | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ36 | Information sharing agreements with partners | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ37 | Records from current Cumbria system integrated. | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ38 | Plan for data ownership and transitioning contract management & QA data to new council structures (GDPR considerations also) resulting in successful transfer of data all current supplier/contract info/support files etc | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ39 | Hardware (PCs) | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ40 | Software and up to date licenses | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ41 | SharePoint access | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ42 | Shared drives mapped and accessible | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ43 | Printing / Scanning facilities | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ44 | Appropriate web pages updated / operational | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ45 | Public website mapping / access | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ46 | Liquid Logic System live | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ47 | Capital 1 | Must have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ48 | Completely separate (new) Case Management Systems for each Unitary Authority | Won't have | requires support from |  | ICT
People | Children's - General Requirements | Children's | CHIL-REQ49 | Each authority must be registered with Ofsted | Must have | requires support from |  | Governance & Policy
People | Children's - General Requirements | Children's | CHIL-REQ50 | All statutory roles in place | Must have | requires support from |  | Governance & Policy
People | Children's - General Requirements | Children's | CHIL-REQ51 | Appropriate business support functions agreed and functional | Must have | requires support from |  | Governance & Policy
People | Children's - General Requirements | Children's | CHIL-REQ52 | Delegations scheme in place | Must have | requires support from |  | Governance & Policy
People | Children's - General Requirements | Children's | CHIL-REQ53 | Access to mandatory training | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ54 | Access to DBS compliance / DBS compliance | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ55 | Minimum staffing levels to provide minimum statuary compliance | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ56 | ID badges | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ57 | Appropriate capacity in place to maintain service provision with particular focus on vesting day / transition | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ58 | Appropriate cost centre allocation and delegations of authority | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ59 | Critical commercial agreements in place | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ60 | T&C signed off for ‘appropriate persons’ | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ61 | New budget codes | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ62 | Finance Team in place to administer | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ63 | Funding and delivery of ongoing projects – these have been split where required, and have project leadership/oversight/monitoring/evaluation in place to ensure continued delivery across both authorities | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ64 | Income in advance to be allocated between the new authorities, including reserves | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ65 | System established for ordering resources and digital blue-slip payments for one-off purchases. Also used for reimbursing learners where cash, cheque or debit card payment received | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ66 | Contracts agreed with external suppliers for procurement | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ67 | Financial Year end transactions would need to be carried forward into the new authority | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ68 | System in place for reimbursing small cash payments i.e., small item course resources (currently £10 available per course) and mileage transactions | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ69 | Migration of Finance documents from CCC drives [evidence of invoices, outstanding orders etc.) | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ70 | Financial Cost Centres and invoicing procedures and other financial systems such as E5 are all up and running on day 1. | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ71 | Access to budgets | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ72 | Controcc payments to providers | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ73 | Joint funding agreements will need to transfer to new Council's i.e. we have an agreement with North CCG in Learning Disabilities to 50/50 fund S.117 cases. | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ74 | Systems ELMS (equipment ordering) Pre-paid cards for DPs, CHC/Strata/D-RAR | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ75 | Contract Management Schedules agreed for statutory/high risk/high value contracts- quarterly financial reporting, QA, KPI’s and other key reporting | Must have | requires support from |  | Finance
People | Children's - General Requirements | Children's | CHIL-REQ76 | Defined complaints / escalation process in place / interim solutions in place | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ77 | Appropriate commercial communications channels established between authorities and providers | Must have | requires support from |  | Communications and Engagement
People | Children's - General Requirements | Children's | CHIL-REQ78 | Services (internal / external) need to be aware of how to navigate/ communicate / access the service functions | Must have | requires support from |  | Communications and Engagement
People | Children's - General Requirements | Children's | CHIL-REQ79 | Definition and agreement of asset ownership used by the services and allocation of space as appropriate | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ80 | Office spaces for staff, facilities to meet with families, Places for family time | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ81 | All relevant partner agreements / contract in place as not to disrupt service provision | Must have | requires support from |  | Commissioning & Procurement
People | Children's - General Requirements | Children's | CHIL-REQ82 | Office Space | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ83 | Chair/ Desk | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ84 | ID Badges aligned to geographical area | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ85 | Uniform | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ86 | Library Access | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ87 | Clarity on Office bases | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ88 | Access to meeting rooms for staff and customers | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ89 | Pool Cars/ hire cars | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ90 | New signage and branding | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ91 | Key fobs/ badges | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ92 | An ‘incident room’ for the first few days to ‘mop up’ calls and queries arising that can’t be answered via normal channel – perhaps located in one office with landline connection. | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ93 | Stationary | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ94 | Postal system | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ95 | Logos for each authority | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ96 | Confidential waste | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ97 | Access to printers/ scanners | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ98 | Refuge collection | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ99 | Grounds maintenance, white goods contract | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ100 | Cleaning Contracts | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ101 | Building maintance, (out of hours service) | Must have | requires support from |  | Assets
People | Children's - General Requirements | Children's | CHIL-REQ102 | New signage and branding | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ103 | New customer facing website/ telephone numbers/ social media | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ104 | Business Cards | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ105 | Letter headed paper | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ106 | FAQ document for customers/parents/schools. | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ107 | Local Website reflects the new arrangements | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ108 | Service users need to know who to contact in each area and what we do. An accessible business continuity, with named people for parents, schools and key partners (especially safeguarding hub, social care and Operation Encompass) to be aware of. | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ109 | Social Workers, Foster carers, Residential Homes and schools will need to know how to access Emotional Health and Wellbeing support for children looked after and on the edge of care clear communication of contact details. | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ110 | We will need a duty phone number for 24-hour emergency contact line in this area. | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ111 | New email signatures | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ112 | Links with cross-organisation partners | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ113 | Cumbria Outdoors takes booking up to 2 years in advance, and it is essential that all booking systems which are currently held on CCC Internal Drive system are accessible and financial systems allow for transfer of balances/deposits paid etc | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ114 | Clear position on current countywide leadership posts - Snr's, Service Managers, AMHP Lead etc. | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ115 | Easy referal method | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ116 | ID Badges | Must have | requires support from |  | Customer & Digital
People | Children's - General Requirements | Children's | CHIL-REQ117 | Access for staff to training and professional development | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ118 | Motivated & Engaged Staff | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ119 | Clear leadership responsibilities | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ120 | ID Badges | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ121 | Staff paid on day 1, HR/Payroll system transfer, Compliance with TUPE regs including - contracts/terms and conditions, job specs, HR policies/procedures, pensions | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ122 | Occupational Health Records | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ123 | Disabled/ specialist use equiptment | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ124 | Performance Management Framework | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ125 | Access to HR Services & Support | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ126 | Performance Data | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ127 | Relevant Policies and Procedures | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ128 | H&S Procedures | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ129 | Recruitment | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ130 | Clear staffing structure, clear line managerial responsibility, clear work locations | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ131 | Understanding of ongoing grievances, capabilities, disciplinaries and ensure arrangements in place to support continuity including Occupational Health | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ132 | Business continuety plans | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ133 | Evidence based allocation of staff to geographical areas based upon demand | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ134 | Clear Complaints procedure | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ135 | Fire Alarm contracts, Health & Safety audits | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ136 | Key roles would need appointed for day one for both services to be safe and legal – MIS Manager, Quality Team, ALS Coordinator, Senior Manager (Ofsted Nominee), Curriculum Leads, Advanced Practitioners, Exams Officer | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ137 | Contracts for staff are in place that support them being able to deliver courses across both authorities and new staff are appointed to take over delivery of courses | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ138 | HR Files transferred to new LA - Including relevant quals and licences | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ139 | Management structures in place | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ140 | Handbooks have been updated ready for handover. | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ141 | Knowledge of staffing structures including who is who in safeguarding and other relevant departments | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ142 | Staffing Structure to meet needs with accountable officers with decision making authority | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ143 | Skills inventory for any new working arrangements/team. | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ144 | Staff know who they are working for, what their role is, and who is managing and supervising them. | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ145 | Adequate resourcing for new LA | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ146 | All staff clear about their employer and contracts, work base, pay and conditions. | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ147 | All staff are well prepared for day one so they can respond with confidence in their work with the people accessing services. | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ148 | All staff contracts updated | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ149 | Complaints/MP enquiries/Compliments arrangements in place | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ150 | Disaggregation of centrally held records onto new records systems. | Must have | requires support from |  | HR & OD
People | Children's - General Requirements | Children's | CHIL-REQ151 | Letters to customers reflecting new authority | Must have | requires support from |  | Communications and Engagement
People | Children's - General Requirements | Children's | CHIL-REQ152 | Advice for stakeholders | Must have | requires support from |  | Communications and Engagement
People | Children's - General Requirements | Children's | CHIL-REQ153 | Clear new ways to contact LA | Must have | requires support from |  | Communications and Engagement
People | Children's - General Requirements | Children's | CHIL-REQ154 | Consistent way for customers to contact / access the services | Must have | requires support from |  | Communications and Engagement
People | Children's - General Requirements | Children's | CHIL-REQ155 | Website in place for fostering, homes stays and SGO. | Must have | requires support from |  | Communications and Engagement
People | Children's - General Requirements | Children's | CHIL-REQ156 | Clear public facing messages for people accessing services/individuals | Must have | requires support from |  | Communications and Engagement
People | Children's - General Requirements | Children's | CHIL-REQ157 | Public sites show new numbers including duty numbers and contact arrangements | Must have | requires support from |  | Communications and Engagement
People | Children's - General Requirements | Children's | CHIL-REQ158 | Service users need to be aware of who we are, what we do and how to communicate (including the GSAs – we need a plan for ‘visible’ business continuity, with named people for schools and other partners to be aware of. | Must have | requires support from |  | Communications and Engagement
People | Children's - General Requirements | Children's | CHIL-REQ159 | Posters, newletters or guide book on new LA | Must have | requires support from |  | Communications and Engagement
People | Children's - General Requirements | Children's | CHIL-REQ160 | There is a clear steer message from the Director in the new LA | Must have | requires support from |  | Communications and Engagement
People | Children's - General Requirements | Children's | CHIL-REQ161 | Developed communication plan for providers and key stakeholders | Must have | requires support from |  | Communications and Engagement
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ1 | An IRO assigned to all children who require one on day one | Must have
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ2 | A LADO assigned to all cases on day one | Must have
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ3 | All SEND IAS cases assigned | Must have
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ4 | Child death process agreed and in place | Must have
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ5 | CSCP in place and operational | Must have
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ6 | Safeguarding hub policies and process in place | Must have
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ7 | Business support for IRO – meetings in place (in person) minutes | Must have
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ8 | Meeting rooms for meeting with children/families/professionals - CLA reviews, CP Conference and Reviews - possible HYBRID requirements (access to existing rooms) | Must have
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ9 | Room booking process in place that will allow in advance of 1st April for 6 months in advance for CLA reviews and 3 months for CP | Must have
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ10 | IRO access to independent legal advice | Must have
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ11 | LADO email box and voicemail access | Must have | requires support from |  | ICT
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ12 | EVOLVE risk management tool needs to be in place | Must have | requires support from |  | ICT
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ13 | Defined working agreements for those service transitioning to a disaggregated model | Must have | requires support from |  | Governance & Policy
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ14 | Defined polices in place and understood | Must have | requires support from |  | Governance & Policy
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ15 | Partnerships governing board operational | Must have | requires support from |  | Governance & Policy
People | Children's - QA & Partnership Services CYP | Children's - Integration & Partnerships | CHIL-I&P-REQ16 | Advocacy and independent visiting for children's contracts need to be resolved and in place | Must have | requires support from |  | Commissioning & Procurement
People | Children's - Social Care | Children's - Children & Young People | CHIL-C&YP-REQ1 | Medical advisor appointed (Fostering / Adoption) | Must have
People | Children's - Social Care | Children's - Children & Young People | CHIL-C&YP-REQ2 | (Fostering / Adoption) Agency Decision Maker in place | Must have
People | Children's - Social Care | Children's - Children & Young People | CHIL-C&YP-REQ3 | Referral route into day to day services + emergency duty response line | Must have
People | Children's - Social Care | Children's - Children & Young People | CHIL-C&YP-REQ4 | Daily reporting of internal placement availability | Must have
People | Children's - QA & Partnership Services CYP | Children's - Children & Young People | CHIL-C&YP-REQ5 | Partner responsibilities (including services that are in transition) and robust GDPR information sharing agreements | Must have
People |  | Children's - Children & Young People | CHIL-C&YP-REQ6 | Business support - clear scope of service provision - minute taker to take notes for statutory meetings etc | Must have
People |  | Children's - Children & Young People | CHIL-C&YP-REQ7 | S151 officer and SRO in place (Statutory roles) | Must have
People |  | Children's - Children & Young People | CHIL-C&YP-REQ8 | Named director of children's services | Must have
People |  | Children's - Children & Young People | CHIL-C&YP-REQ9 | SGO support must be in place | Must have
People |  | Children's - Children & Young People | CHIL-C&YP-REQ10 | Registered managers and responsible individuals will all have to be transferred to the new councils ( will need to be registered in advance) | Must have
People |  | Children's - Children & Young People | CHIL-C&YP-REQ11 | Statutory complaints process for children’s needs to be in place | Must have
People |  | Children's - Children & Young People | CHIL-C&YP-REQ12 | Dedicated head of YOS | Must have
People | Children's - Social Care | Children's - Children & Young People | CHIL-C&YP-REQ13 | Fostering Register for each area | Must have
People | Children's - Social Care | Children's - Children & Young People | CHIL-C&YP-REQ14 | A list of training to be available for foster carers to attend and book onto. | Must have
People | Children's - Social Care | Children's - Children & Young People | CHIL-C&YP-REQ15 | Carers to be registered with Learning and development in each area. | Must have
People | Children's - Social Care | Children's - Children & Young People | CHIL-C&YP-REQ16 | Safeguarding Adults Board | Must have
People | Children's - Social Care | Children's - Children & Young People | CHIL-C&YP-REQ17 | Disaggregation of centrally managed adoption allowances and Adoption Support Fund claims, funding and contracts/invoices. | Must have
People |  | Children's - Children & Young People | CHIL-C&YP-REQ18 | E-PROC and E-5 system operating in both authorities | Must have | requires support from |  | ICT
People |  | Children's - Children & Young People | CHIL-C&YP-REQ19 | People Safe App – in place | Must have | requires support from |  | ICT
People |  | Children's - Children & Young People | CHIL-C&YP-REQ20 | IRO in place for required services | Must have | requires support from |  | Governance & Policy
People |  | Children's - Children & Young People | CHIL-C&YP-REQ21 | Decision panels in place for required services | Must have | requires support from |  | Governance & Policy
People |  | Children's - Children & Young People | CHIL-C&YP-REQ22 | Agreed process for referrals and contact | Must have | requires support from |  | Governance & Policy
People |  | Children's - Children & Young People | CHIL-C&YP-REQ23 | LADO pathways in place | Must have | requires support from |  | Governance & Policy
People |  | Children's - Children & Young People | CHIL-C&YP-REQ24 | External resource must be appropriately registered | Must have | requires support from |  | HR & OD
People |  | Children's - Children & Young People | CHIL-C&YP-REQ25 | On call roster in place | Must have | requires support from |  | HR & OD
People |  | Children's - Children & Young People | CHIL-C&YP-REQ26 | Access to multi agency staff | Must have | requires support from |  | Finance
People |  | Children's - Children & Young People | CHIL-C&YP-REQ27 | NYAS advocacy service in place (Reg 44 visits / missing from home) | Must have | requires support from |  | Finance
People |  | Children's - Children & Young People | CHIL-C&YP-REQ28 | Process in place to maintain payments for foster careers / adoption allowances / SGO and resident orders | Must have | requires support from |  | Finance
People |  | Children's - Children & Young People | CHIL-C&YP-REQ29 | Access to section 17, provision for monies to be made available: children in need / children in care / care leavers / care for children in residential placement | Must have | requires support from |  | Finance
People |  | Children's - Children & Young People | CHIL-C&YP-REQ30 | TRIX-X in place | Must have | requires support from |  | Finance
People |  | Children's - Children & Young People | CHIL-C&YP-REQ31 | Financial system in place for payments for contact, transitions, Adoption allowances, Adoption Support Fund. | Must have | requires support from |  | Finance
People |  | Children's - Children & Young People | CHIL-C&YP-REQ32 | Consistent financial system in place to support payments for foster careers | Must have | requires support from |  | Finance
People |  | Children's - Children & Young People | CHIL-C&YP-REQ33 | Financial system in place for payments for contact, transitions, Fostering/SGO allowances, Adoption Support Fund. | Must have | requires support from |  | Finance
People |  | Children's - Children & Young People | CHIL-C&YP-REQ34 | Incoming referrals / information / safeguarding checks - clearly mapped out | Must have | requires support from |  | Customer & Digital
People |  | Children's - Children & Young People | CHIL-C&YP-REQ35 | Consistent approach to record keeping | Must have | requires support from |  | Customer & Digital
People |  | Children's - Children & Young People | CHIL-C&YP-REQ36 | Disaggregation of managed post adoption contact service- letterbox and direct contact | Must have | requires support from |  | Customer & Digital
People |  | Children's - Children & Young People | CHIL-C&YP-REQ37 | Agree key lines of comms with all stakeholders | Must have | requires support from |  | Communications and Engagement
People |  | Children's - Children & Young People | CHIL-C&YP-REQ38 | All children and adopters who are the responsibility of the service have an allocated social worker and know how to contact them | Must have | requires support from |  | Communications and Engagement
People |  | Children's - Children & Young People | CHIL-C&YP-REQ39 | Our Licencing bodies i.e. Duke of Edinburgh Award Operating licence, AALA , Association of Heads of Outdoor Education Centres Gold etc will need to be informed of any change in order for amendment of Local Authority name to be issued on any licences. | Must have | requires support from |  | Communications and Engagement
People |  | Children's - Children & Young People | CHIL-C&YP-REQ40 | Adoption Panel chair and members appointed and properly constituted | Must have | requires support from |  | Legal & Democratic Services
People |  | Children's - Children & Young People | CHIL-C&YP-REQ41 | Child death processes would need to be confirmed and in place | Must have | requires support from |  | Governance & Policy
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ1 | Sufficient child care in place | Must have
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ2 | Adult Social care liaison officer | Must have
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ3 | LSS service in place to honour existing agreements with schools | Must have
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ4 | Both authorities will need to establish UK PRN | Must have
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ5 | Both authorities will need to be JCQ compliant | Must have
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ6 | Safeguarding in place | Must have
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ7 | Procedure for ongoing prosecution of non attendance | Must have
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ8 | LADO- link with DSLs in schools -Designated School Lead for safeguarding so we are kept informed if there is a serious safeguarding issue on day 1 | Must have
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ9 | Inform DfE, Regional Schools Commissioner -RSC -and Ofsted of changes | Must have
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ10 | OFSTED Registration to both Councils | Must have
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ11 | Requirements around provision of education for Permanently Excluded students/reintegration into mainstream schools from Alternative Provision etc will mean some continuity is required; there will be ongoing casework crossing vesting day. | Must have
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ12 | Database needs to be in place to capture all known Home Educators | Must have | requires support from |  | ICT
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ13 | ePEP | Must have | requires support from |  | ICT
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ14 | 30hr codes - check EYPP eligibility | Must have | requires support from |  | ICT
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ15 | Learner record System in place to provide assurance and tracking of ESFA guidance (Pro Solution inc Web tool kit) | Must have | requires support from |  | ICT
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ16 | Signable software | Must have | requires support from |  | ICT
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ17 | STRTA | Must have | requires support from |  | ICT
ICT
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ19 | Database of all known home educators needs to be securely in place in each new LA. | Must have | requires support from |  | ICT
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ20 | Permission and access to Schools portal | Must have | requires support from |  | ICT
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ21 | Clearly defined referral system for referral service | Must have | requires support from |  | Governance & Policy
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ22 | Decision making panel in place | Must have | requires support from |  | Governance & Policy
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ23 | ESFA grant funding matrix / accreditation | Must have | requires support from |  | Finance
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ24 | Tutors working across both authorities | Must have |  | requires support from | Finance
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ25 | Tutors working across both authorities | Must have |  | requires support from | Commissioning & Procurement
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ26 | Novation of agreements (pre booked training / sub contractor arrangements) | Must have |  | requires support from | Finance
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ27 | Novation of agreements (pre booked training / sub contractor arrangements) | Must have |  | requires support from | Commissioning & Procurement
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ28 | Customer pre booked (Cumbria outdoors) transfer of deposits) and website booking access | Must have |  | requires support from | Finance
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ29 | Customer pre booked (Cumbria outdoors) transfer of deposits) and website booking access | Must have |  | requires support from | Commissioning & Procurement
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ30 | E – procurement needs to be in place | Must have |  | requires support from | Finance
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ31 | E – procurement needs to be in place | Must have |  | requires support from | Commissioning & Procurement
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ32 | Process needed for zero hours tutors’ holiday pay fast input | Must have | requires support from |  | Finance
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ33 | Enrolment documentation for new learners needs to be agreed and in place | Must have | requires support from |  | Customer & Digital
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ34 | Website e-enrolment forms needs to be live. | Must have | requires support from |  | Customer & Digital
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ35 | Mid year delivering qualifications needs to communicate with learners if any changes in provision | Must have | requires support from |  | Communications and Engagement
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ36 | External stakeholders (eg Ofsted, DfE) have contact details for service leads for cascade of information and contact for specific issues | Must have | requires support from |  | Communications and Engagement
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ37 | Transport | Must have | requires support from |  | Assets
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ38 | Clear commissioning structure will appropriate delegations | Must have | requires support from |  | Commissioning & Procurement
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ39 | Habitation contract | Must have | requires support from |  | Commissioning & Procurement
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ40 | Sub contractors that deliver against grants | Must have | requires support from |  | Commissioning & Procurement
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ41 | Arrangements for student placements and other learner support including an ASYE programme and degree apprenticeships | Must have | requires support from |  | HR & OD
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ42 | DBS in place for all relevant staff - recognised in new authorities and arrangements have been made for re-issue. | Must have | requires support from |  | HR & OD
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ43 | Requirements around provision of education for Permanently Excluded students/reintegration into mainstream schools from Alternative Provision etc will mean some continuity is required; there will be ongoing casework crossing vesting day | Must have | requires support from |  | Legal & Democratic Services
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ44 | Both new local authorities will need established as training providers and hold a UKPRN. This is a condition of the ESFA funding | Must have | requires support from |  | Governance & Policy
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ45 | To be able to continue to deliver qualifications and run exams each new local authority must be compliant with JCQ regulations. | Must have | requires support from |  | Governance & Policy
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ46 | Appropriate licences are in place for tutors to continue to deliver online classes | Must have | requires support from |  | Governance & Policy
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ47 | Policies in place for both organisations – e.g. Additional Learner Support; Safeguarding; Quality | Must have | requires support from |  | Governance & Policy
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ48 | Service Level Agreement including governance arrangements | Must have | requires support from |  | Governance & Policy
People | Children's - Education Services | Children's - Education & Skills | CHIL-E&S-REQ49 | Both new local authorities will need to be registered with Ofsted and have an Ofsted Nominee | Must have | requires support from |  | Governance & Policy
People | Adults - General Requirements | Adults | ADUL-REQ1 | Laptops/ Computers | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ2 | Mobile Phone/ Landlines, chargers | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ3 | ICT Networks, systems, VPN and support | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ4 | Access to ICT systems: HR, Finance, InTouch | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ5 | Access to service specific ICT Systems | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ6 | Access to Apps like Google Authenticator | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ7 | Social Media | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ8 | CRM Systems & Portals | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ9 | Access to booking systems for meeting rooms/ Pool Cars/ Holidays | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ10 | Acces to Websites | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ11 | VPN Access | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ12 | Access to shared mailbox accounts | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ13 | Emails, Outlook, MS Teams, Egress | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ14 | Access to customer and staff files | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ15 | Access to shared drives | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ16 | SharePoint access | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ17 | Access to Liquid Logic | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ18 | Access to submit expenses | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ19 | Access to exisiting files | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ20 | Ability to share information electronically (Police & Health) | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ21 | Whatsapp & Text Messaging | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ22 | Electronic Files to be available | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ23 | Records from current Cumbria system integrated. | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ24 | Case recording system | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ25 | Licencing | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ26 | GDPR compliant data sharing model | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ27 | Information sharing agreements with partners | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ28 | Records from current Cumbria system integrated. | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ29 | Plan for data ownership and transitioning contract management & QA data to new council structures (GDPR considerations also) resulting in successful transfer of data all current supplier/contract info/support files etc | Must have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ30 | Completely separate (new) Case Management Systems for each Unitary Authority | Won't have | requires support from |  | ICT
People | Adults - General Requirements | Adults | ADUL-REQ31 | New budget codes | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ32 | Finance Team in place to administer | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ33 | Funding and delivery of ongoing projects – these have been split where required, and have project leadership/oversight/monitoring/evaluation in place to ensure continued delivery across both authorities | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ34 | Income in advance to be allocated between the new authorities, including reserves | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ35 | System established for ordering resources and digital blue-slip payments for one-off purchases. Also used for reimbursing learners where cash, cheque or debit card payment received | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ36 | Contracts agreed with external suppliers for procurement | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ37 | Financial Year end transactions would need to be carried forward into the new authority | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ38 | System in place for reimbursing small cash payments i.e., small item course resources (currently £10 available per course) and mileage transactions | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ39 | Migration of Finance documents from CCC drives [evidence of invoices, outstanding orders etc.) | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ40 | Financial Cost Centres and invoicing procedures and other financial systems such as E5 are all up and running on day 1. | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ41 | Access to budgets | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ42 | Controcc payments to providers | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ43 | Joint funding agreements will need to transfer to new Council's i.e. we have an agreement with North CCG in Learning Disabilities to 50/50 fund S.117 cases. | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ44 | Systems ELMS (equipment ordering) Pre-paid cards for DPs, CHC/Strata/D-RAR | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ45 | Contract Management Schedules agreed for statutory/high risk/high value contracts- quarterly financial reporting, QA, KPI’s and other key reporting | Must have | requires support from |  | Finance
People | Adults - General Requirements | Adults | ADUL-REQ46 | Office Space | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ47 | Chair/ Desk | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ48 | ID Badges aligned to geographical area | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ49 | Uniform | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ50 | Library Access | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ51 | Clarity on Office bases | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ52 | Access to meeting rooms for staff and customers | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ53 | Pool Cars/ hire cars | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ54 | New signage and branding | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ55 | Key fobs/ badges | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ56 | An ‘incident room’ for the first few days to ‘mop up’ calls and queries arising that can’t be answered via normal channel – perhaps located in one office with landline connection. | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ57 | Stationary | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ58 | Postal system | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ59 | Logos for each authority | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ60 | Confidential waste | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ61 | Access to printers/ scanners | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ62 | Refuge collection | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ63 | Grounds maintenance, white goods contract | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ64 | Cleaning Contracts | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ65 | Building maintance, (out of hours service) | Must have | requires support from |  | Assets
People | Adults - General Requirements | Adults | ADUL-REQ66 | New signage and branding | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ67 | New customer facing website/ telephone numbers/ social media | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ68 | Business Cards | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ69 | Letter headed paper | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ70 | FAQ document for customers/parents/schools. | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ71 | Local Website reflects the new arrangements | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ72 | Service users need to know who to contact in each area and what we do. An accessible business continuity, with named people for parents, schools and key partners (especially safeguarding hub, social care and Operation Encompass) to be aware of. | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ73 | Social Workers, Foster carers, Residential Homes and schools will need to know how to access Emotional Health and Wellbeing support for children looked after and on the edge of care clear communication of contact details. | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ74 | We will need a duty phone number for 24-hour emergency contact line in this area. | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ75 | New email signatures | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ76 | Links with cross-organisation partners | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ77 | Cumbria Outdoors takes booking up to 2 years in advance, and it is essential that all booking systems which are currently held on CCC Internal Drive system are accessible and financial systems allow for transfer of balances/deposits paid etc | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ78 | Clear position on current countywide leadership posts - Snr's, Service Managers, AMHP Lead etc. | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ79 | Easy referal method | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ80 | ID Badges | Must have | requires support from |  | Customer & Digital
People | Adults - General Requirements | Adults | ADUL-REQ81 | Access for staff to training and professional development | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ82 | Motivated & Engaged Staff | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ83 | Clear leadership responsibilities | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ84 | ID Badges | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ85 | Staff paid on day 1, HR/Payroll system transfer, Compliance with TUPE regs including - contracts/terms and conditions, job specs, HR policies/procedures, pensions | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ86 | Occupational Health Records | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ87 | Disabled/ specialist use equiptment | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ88 | Performance Management Framework | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ89 | Access to HR Services & Support | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ90 | Performance Data | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ91 | Relevant Policies and Procedures | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ92 | H&S Procedures | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ93 | Recruitment | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ94 | Clear staffing structure, clear line managerial responsibility, clear work locations | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ95 | Understanding of ongoing grievances, capabilities, disciplinaries and ensure arrangements in place to support continuity including Occupational Health | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ96 | Business continuety plans | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ97 | Evidence based allocation of staff to geographical areas based upon demand | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ98 | Clear Complaints procedure | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ99 | Fire Alarm contracts, Health & Safety audits | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ100 | Key roles would need appointed for day one for both services to be safe and legal – MIS Manager, Quality Team, ALS Coordinator, Senior Manager (Ofsted Nominee), Curriculum Leads, Advanced Practitioners, Exams Officer | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ101 | Contracts for staff are in place that support them being able to deliver courses across both authorities and new staff are appointed to take over delivery of courses | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ102 | HR Files transferred to new LA - Including relevant quals and licences | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ103 | Management structures in place | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ104 | Handbooks have been updated ready for handover. | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ105 | Knowledge of staffing structures including who is who in safeguarding and other relevant departments | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ106 | Staffing Structure to meet needs with accountable officers with decision making authority | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ107 | Skills inventory for any new working arrangements/team. | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ108 | Staff know who they are working for, what their role is, and who is managing and supervising them. | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ109 | Adequate resourcing for new LA | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ110 | All staff clear about their employer and contracts, work base, pay and conditions. | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ111 | All staff are well prepared for day one so they can respond with confidence in their work with the people accessing services. | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ112 | All staff contracts updated | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ113 | Complaints/MP enquiries/Compliments arrangements in place | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ114 | Disaggregation of centrally held records onto new records systems. | Must have | requires support from |  | HR & OD
People | Adults - General Requirements | Adults | ADUL-REQ115 | Letters to customers reflecting new authority | Must have | requires support from |  | Communications and Engagement
People | Adults - General Requirements | Adults | ADUL-REQ116 | Advice for stakeholders | Must have | requires support from |  | Communications and Engagement
People | Adults - General Requirements | Adults | ADUL-REQ117 | Clear new ways to contact LA | Must have | requires support from |  | Communications and Engagement
People | Adults - General Requirements | Adults | ADUL-REQ118 | Consistent way for customers to contact / access the services | Must have | requires support from |  | Communications and Engagement
People | Adults - General Requirements | Adults | ADUL-REQ119 | Website in place for fostering, homes stays and SGO. | Must have | requires support from |  | Communications and Engagement
People | Adults - General Requirements | Adults | ADUL-REQ120 | Clear public facing messages for people accessing services/individuals | Must have | requires support from |  | Communications and Engagement
People | Adults - General Requirements | Adults | ADUL-REQ121 | Public sites show new numbers including duty numbers and contact arrangements | Must have | requires support from |  | Communications and Engagement
People | Adults - General Requirements | Adults | ADUL-REQ122 | Service users need to be aware of who we are, what we do and how to communicate (including the GSAs – we need a plan for ‘visible’ business continuity, with named people for schools and other partners to be aware of. | Must have | requires support from |  | Communications and Engagement
People | Adults - General Requirements | Adults | ADUL-REQ123 | Posters, newletters or guide book on new LA | Must have | requires support from |  | Communications and Engagement
People | Adults - General Requirements | Adults | ADUL-REQ124 | There is a clear steer message from the Director in the new LA | Must have | requires support from |  | Communications and Engagement
People | Adults - General Requirements | Adults | ADUL-REQ125 | Developed communication plan for providers and key stakeholders | Must have | requires support from |  | Communications and Engagement
People | Adults - General Requirements | Adults | ADUL-REQ126 | Access to legal services | Must have | requires support from |  | Legal & Democratic Services
People | Adults - General Requirements | Adults | ADUL-REQ127 | All legal documents such as contracts, agreement and partnerships must be rewritten and in place prior to go live. | Must have | requires support from |  | Legal & Democratic Services
People | Adults - General Requirements | Adults | ADUL-REQ128 | Management of legal documents that we hold (e.g., instruments of governance) is securely in place across both areas. | Must have | requires support from |  | Legal & Democratic Services
People | Adults - General Requirements | Adults | ADUL-REQ129 | Complaints and Tribunal process’/Legal Support | Must have | requires support from |  | Legal & Democratic Services
People | Adults - General Requirements | Adults | ADUL-REQ130 | Mediation Contracts | Must have | requires support from |  | Legal & Democratic Services
People | Adults - General Requirements | Adults | ADUL-REQ131 | Data sharing agreement | Must have | requires support from |  | Legal & Democratic Services
People | Adults - General Requirements | Adults | ADUL-REQ132 | Access to insurance documents | Must have | requires support from |  | Legal & Democratic Services
People | Adults - General Requirements | Adults | ADUL-REQ133 | Audit and assurance | Must have | requires support from |  | Legal & Democratic Services
People | Adults - General Requirements | Adults | ADUL-REQ134 | Arrangements in place for safe transfer of cases - may be ongoing cases where practitioner will change and so need to agree a process to do this safely and in a ‘person centred’ way between new unitary councils and teams. | Must have | requires support from |  | Legal & Democratic Services
People | Adults - General Requirements | Adults | ADUL-REQ135 | Carers Assessments Advocacy | Must have | requires support from |  | Legal & Democratic Services
People | Adults - General Requirements | Adults | ADUL-REQ136 | Confirmation of arrangements when the Director is Nearest Relative under the MHA | Must have | requires support from |  | Legal & Democratic Services
People | Adults - General Requirements | Adults | ADUL-REQ137 | Access to brokerage for whole ASC service | Must have | requires support from |  | Legal & Democratic Services
People | Adults - General Requirements | Adults | ADUL-REQ138 | Clearly identified Quality Assurance processes and resources in place to support safe delivery of services | Must have | requires support from |  | Legal & Democratic Services
People | Adults - General Requirements | Adults | ADUL-REQ139 | Reg 44 visits | Must have | requires support from |  | Legal & Democratic Services
People | Adults - Social Care / Workforce | Adults - Social Work | ADUL-SW-REQ1 | New Careers Case Recording system IT linked to social care/Early Help/ONE – each LA will need to be able to record careers service interventions to ensure other services working with the YP are aware of delivery | Must have | requires support from |  | ICT
People | Adults - Social Care / Workforce | Adults - Social Work | ADUL-SW-REQ2 | Arrangements in place for approval of packages of care, financial assessments and charging | Must have | requires support from |  | Finance
People | Adults - Social Care / Workforce | Adults | ADUL-SW-REQ3 | Social work, children's homes and EHCP social care advice are statutory, and laws and regulation shape these services. | Must have | requires support from |  | Legal & Democratic Services
People | Adults - Social Care / Workforce | Adults - Social Work | ADUL-SW-REQ4 | Haverigg (prison) care and support | Must have
People | Adults - Cumbria Care | Adults - Cumbria Care | ADUL-CC-REG1 | Cumbria Care On-Call System | Must have | requires support from |  | ICT
People | Adults - Commissioned Services | Adults - Commissioned Services | ADUL-CS-REG1 | Cash, debit card payments in Libraries for Adult Learning – facility would need to be available. | Must have | requires support from |  | Finance
People | Adults - Commissioned Services | Adults - Commissioned Services | ADUL-CS-REG2 | Clarity regarding commissioned services and where are they aligned. | Must have
People | Adults - Commissioned Services | Adults - Commissioned Services | ADUL-CS-REG3 | Clarity for sponsor roles in commissioned services | Must have
People | Adults - Non Commissioned Services | Adults - Non Commissioned Services | ADUL-NCS-REG1 | Blue Badge assessments | Must have | requires support from |  | HR & OD
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG1 | Agreement in place around NHS systems and non-alignment with NHS boundaries (directly broker hospital placements in North) | Must have
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG2 | Agreements in place regarding the allocations of the funding | Must have
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG3 | Agreement in place around NHS systems and non-alignment with NHS boundaries (directly broker hospital placements in North) | Must have
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG4 | Re-mapping of service directory / contract register for new areas + linked service availability | Must have
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG5 | Re-mapping of delivery/supply risks on new unitary footprints | Must have
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG6 | Separate contract for servicing and repair of lifts and hoists (Sumed contract expires 2024) | Could have
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG7 | Systems in place to identify where service users receive services | Must have
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG8 | New policies and contracts that are aligned to new LA | Must have | requires support from |  | Governance & Policy
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG9 | Register of all applicable contracts, including call-offs and renovations | Must have | requires support from |  | Governance & Policy
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG10 | Enforceable/certain contractual arrangements covering all existing care packages | Must have | requires support from |  | Governance & Policy
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG11 | A procurement strategy | Must have | requires support from |  | Governance & Policy
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG12 | Contract pipeline in place | Must have | requires support from |  | Governance & Policy
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG13 | Regular risk assessment to identify emerging issues | Must have | requires support from |  | Governance & Policy
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG14 | Enforceable/certain contractual arrangements covering all existing care packages | Must have | requires support from |  | Governance & Policy
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG15 | Contractual arrangements in place to enable new placements in order to continue to meet statutory duties; | Must have | requires support from |  | Governance & Policy
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG16 | Market Position Statement / Market Sustainability Plan (statutory) | Must have | requires support from |  | Governance & Policy
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG17 | Clearly defined governance and decision-making processes (include schemes of delegation) | Must have | requires support from |  | Governance & Policy
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG18 | Clearly identified Quality Assurance processes and resources in place to support safe delivery of services | Must have | requires support from |  | Governance & Policy
People | Adults - Commissioning | Adults - Commissioning | ADUL-COM-REG19 | Clear agreements about transfer points between authorities where a child/family is accessing a service which will continue in the medium term and where a change of social worker or therapist will impact on the outcomes. | Must have | requires support from |  | Governance & Policy
People | Adults - Commissioning | Adults - Partnerships | ADUL-PAR-REQ1 | Servicing of partnerships needs to have been considered and future representations agreed | Must have | requires support from |  | Legal & Democratic Services
People | Adults - Commissioning | Adults - Partnerships | ADUL-PAR-REQ2 | All contracts such as Partnership agreements and commercial agreements will need to be rewritten with the correct council entity | Must have | requires support from |  | Governance & Policy
People | Public Health | Public Health | PH-REQ1 | Laptops/ Computers | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ2 | Mobile Phone/ Landlines, chargers | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ3 | ICT Networks, systems, VPN and support | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ4 | Access to ICT systems: HR, Finance, InTouch | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ5 | Access to service specific ICT Systems | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ6 | Access to Apps like Google Authenticator | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ7 | Social Media | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ8 | CRM Systems & Portals | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ9 | Access to booking systems for meeting rooms/ Pool Cars/ Holidays | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ10 | Acces to Websites | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ11 | VPN Access | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ12 | Access to shared mailbox accounts | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ13 | Emails, Outlook, MS Teams, Egress | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ14 | Access to customer and staff files | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ15 | Access to shared drives | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ16 | SharePoint access | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ17 | Access to Liquid Logic | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ18 | Access to submit expenses | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ19 | Access to exisiting files | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ20 | Ability to share information electronically (Police & Health) | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ21 | Whatsapp & Text Messaging | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ22 | Electronic Files to be available | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ23 | Records from current Cumbria system integrated. | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ24 | Case recording system | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ25 | Licencing | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ26 | GDPR compliant data sharing model | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ27 | Information sharing agreements with partners | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ28 | Records from current Cumbria system integrated. | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ29 | Plan for data ownership and transitioning contract management & QA data to new council structures (GDPR considerations also) resulting in successful transfer of data all current supplier/contract info/support files etc | Must have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ30 | Completely separate (new) Case Management Systems for each Unitary Authority | Won't have | requires support from |  | ICT
People | Public Health | Public Health | PH-REQ31 | New budget codes | Must have | requires support from |  | Finance
People | Public Health | Public Health | PH-REQ32 | Finance Team in place to administer | Must have | requires support from |  | Finance
People | Public Health | Public Health | PH-REQ33 | Funding and delivery of ongoing projects – these have been split where required, and have project leadership/oversight/monitoring/evaluation in place to ensure continued delivery across both authorities | Must have | requires support from |  | Finance
People | Public Health | Public Health | PH-REQ34 | Income in advance to be allocated between the new authorities, including reserves | Must have | requires support from |  | Finance
People | Public Health | Public Health | PH-REQ35 | System established for ordering resources and digital blue-slip payments for one-off purchases. Also used for reimbursing learners where cash, cheque or debit card payment received | Must have | requires support from |  | Finance
People | Public Health | Public Health | PH-REQ36 | Contracts agreed with external suppliers for procurement | Must have | requires support from |  | Finance
People | Public Health | Public Health | PH-REQ37 | Financial Year end transactions would need to be carried forward into the new authority | Must have | requires support from |  | Finance
People | Public Health | Public Health | PH-REQ38 | System in place for reimbursing small cash payments i.e., small item course resources (currently £10 available per course) and mileage transactions | Must have | requires support from |  | Finance
People | Public Health | Public Health | PH-REQ39 | Migration of Finance documents from CCC drives [evidence of invoices, outstanding orders etc.) | Must have | requires support from |  | Finance
People | Public Health | Public Health | PH-REQ40 | Financial Cost Centres and invoicing procedures and other financial systems such as E5 are all up and running on day 1. | Must have | requires support from |  | Finance
People | Public Health | Public Health | PH-REQ41 | Access to budgets | Must have | requires support from |  | Finance
People | Public Health | Public Health | PH-REQ42 | Controcc payments to providers | Must have | requires support from |  | Finance
People | Public Health | Public Health | PH-REQ43 | Joint funding agreements will need to transfer to new Council's i.e. we have an agreement with North CCG in Learning Disabilities to 50/50 fund S.117 cases. | Must have | requires support from |  | Finance
People | Public Health | Public Health | PH-REQ44 | Systems ELMS (equipment ordering) Pre-paid cards for DPs, CHC/Strata/D-RAR | Must have | requires support from |  | Finance
People | Public Health | Public Health | PH-REQ45 | Office Space | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ46 | Chair/ Desk | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ47 | ID Badges aligned to geographical area | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ48 | Uniform | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ49 | Library Access | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ50 | Clarity on Office bases | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ51 | Access to meeting rooms for staff and customers | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ52 | Pool Cars/ hire cars | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ53 | New signage and branding | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ54 | Key fobs/ badges | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ55 | An ‘incident room’ for the first few days to ‘mop up’ calls and queries arising that can’t be answered via normal channel – perhaps located in one office with landline connection. | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ56 | Stationary | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ57 | Postal system | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ58 | Logos for each authority | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ59 | Confidential waste | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ60 | Access to printers/ scanners | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ61 | Refuge collection | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ62 | Grounds maintenance, white goods contract | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ63 | Cleaning Contracts | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ64 | Building maintance, (out of hours service) | Must have | requires support from |  | Assets
People | Public Health | Public Health | PH-REQ65 | New signage and branding | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ66 | New customer facing website/ telephone numbers/ social media | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ67 | Business Cards | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ68 | Letter headed paper | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ69 | FAQ document for customers/parents/schools. | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ70 | Local Website reflects the new arrangements | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ71 | Service users need to know who to contact in each area and what we do. An accessible business continuity, with named people for parents, schools and key partners (especially safeguarding hub, social care and Operation Encompass) to be aware of. | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ72 | Social Workers, Foster carers, Residential Homes and schools will need to know how to access Emotional Health and Wellbeing support for children looked after and on the edge of care clear communication of contact details. | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ73 | We will need a duty phone number for 24-hour emergency contact line in this area. | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ74 | New email signatures | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ75 | Links with cross-organisation partners | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ76 | Cumbria Outdoors takes booking up to 2 years in advance, and it is essential that all booking systems which are currently held on CCC Internal Drive system are accessible and financial systems allow for transfer of balances/deposits paid etc | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ77 | Clear position on current countywide leadership posts - Snr's, Service Managers, AMHP Lead etc. | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ78 | Easy referal method | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ79 | ID Badges | Must have | requires support from |  | Customer & Digital
People | Public Health | Public Health | PH-REQ80 | Access for staff to training and professional development | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ81 | Motivated & Engaged Staff | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ82 | Clear leadership responsibilities | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ83 | ID Badges | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ84 | Staff paid on day 1, HR/Payroll system transfer, Compliance with TUPE regs including - contracts/terms and conditions, job specs, HR policies/procedures, pensions | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ85 | Occupational Health Records | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ86 | Disabled/ specialist use equiptment | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ87 | Performance Management Framework | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ88 | Access to HR Services & Support | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ89 | Performance Data | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ90 | Relevant Policies and Procedures | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ91 | H&S Procedures | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ92 | Recruitment | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ93 | Clear staffing structure, clear line managerial responsibility, clear work locations | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ94 | Understanding of ongoing grievances, capabilities, disciplinaries and ensure arrangements in place to support continuity including Occupational Health | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ95 | Business continuety plans | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ96 | Evidence based allocation of staff to geographical areas based upon demand | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ97 | Clear Complaints procedure | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ98 | Fire Alarm contracts, Health & Safety audits | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ99 | Key roles would need appointed for day one for both services to be safe and legal – MIS Manager, Quality Team, ALS Coordinator, Senior Manager (Ofsted Nominee), Curriculum Leads, Advanced Practitioners, Exams Officer | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ100 | Contracts for staff are in place that support them being able to deliver courses across both authorities and new staff are appointed to take over delivery of courses | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ101 | HR Files transferred to new LA - Including relevant quals and licences | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ102 | Management structures in place | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ103 | Handbooks have been updated ready for handover. | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ104 | Knowledge of staffing structures including who is who in safeguarding and other relevant departments | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ105 | Staffing Structure to meet needs with accountable officers with decision making authority | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ106 | Skills inventory for any new working arrangements/team. | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ107 | Staff know who they are working for, what their role is, and who is managing and supervising them. | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ108 | Adequate resourcing for new LA | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ109 | All staff clear about their employer and contracts, work base, pay and conditions. | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ110 | All staff are well prepared for day one so they can respond with confidence in their work with the people accessing services. | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ111 | All staff contracts updated | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ112 | Complaints/MP enquiries/Compliments arrangements in place | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ113 | Disaggregation of centrally held records onto new records systems. | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ114 | Medical Adviser appointed | Must have | requires support from |  | HR & OD
People | Public Health | Public Health | PH-REQ115 | Advice and information for customers/ online Living Well in Cumbria | Must have | requires support from |  | Communications and Engagement
People | Public Health | Public Health | PH-REQ116 | Letters to customers reflecting new authority | Must have | requires support from |  | Communications and Engagement
People | Public Health | Public Health | PH-REQ117 | Advice for stakeholders | Must have | requires support from |  | Communications and Engagement
People | Public Health | Public Health | PH-REQ118 | Clear new ways to contact LA | Must have | requires support from |  | Communications and Engagement
People | Public Health | Public Health | PH-REQ119 | Consistent way for customers to contact / access the services | Must have | requires support from |  | Communications and Engagement
People | Public Health | Public Health | PH-REQ120 | Website in place for fostering, homes stays and SGO. | Must have | requires support from |  | Communications and Engagement
People | Public Health | Public Health | PH-REQ121 | Clear public facing messages for people accessing services/individuals | Must have | requires support from |  | Communications and Engagement
People | Public Health | Public Health | PH-REQ122 | Public sites show new numbers including duty numbers and contact arrangements | Must have | requires support from |  | Communications and Engagement
People | Public Health | Public Health | PH-REQ123 | Service users need to be aware of who we are, what we do and how to communicate (including the GSAs – we need a plan for ‘visible’ business continuity, with named people for schools and other partners to be aware of. | Must have | requires support from |  | Communications and Engagement
People | Public Health | Public Health | PH-REQ124 | Posters, newletters or guide book on new LA | Must have | requires support from |  | Communications and Engagement
People | Public Health | Public Health | PH-REQ125 | There is a clear steer message from the Director in the new LA | Must have | requires support from |  | Communications and Engagement
People | Public Health | Public Health | PH-REQ126 | Developed communication plan for providers and key stakeholders | Must have | requires support from |  | Communications and Engagement
People | Public Health | Public Health | PH-REQ127 | Access to legal services | Must have | requires support from |  | Legal & Democratic Services
People | Public Health | Public Health | PH-REQ128 | All legal documents such as contracts, agreement and partnerships must be rewritten and in place prior to go live. | Must have | requires support from |  | Legal & Democratic Services
People | Public Health | Public Health | PH-REQ129 | Management of legal documents that we hold (e.g., instruments of governance) is securely in place across both areas. | Must have | requires support from |  | Legal & Democratic Services
People | Public Health | Public Health | PH-REQ130 | Complaints and Tribunal process’/Legal Support | Must have | requires support from |  | Legal & Democratic Services
People | Public Health | Public Health | PH-REQ131 | Mediation Contracts | Must have | requires support from |  | Legal & Democratic Services
People | Public Health | Public Health | PH-REQ132 | Social work, children's homes and EHCP social care advice are statutory, and laws and regulation shape these services. | Must have | requires support from |  | Legal & Democratic Services
People | Public Health | Public Health | PH-REQ133 | Data sharing agreement | Must have | requires support from |  | Legal & Democratic Services
People | Public Health | Public Health | PH-REQ134 | Access to insurance documents | Must have | requires support from |  | Legal & Democratic Services
People | Public Health | Public Health | PH-REQ135 | Audit and assurance | Must have | requires support from |  | Legal & Democratic Services
People | Public Health | Public Health | PH-REQ136 | Arrangements in place for safe transfer of cases - may be ongoing cases where practitioner will change and so need to agree a process to do this safely and in a ‘person centred’ way between new unitary councils and teams. | Must have | requires support from |  | Legal & Democratic Services

## Day1 Reqs&Depends (Place) - old (hidden)
Day1 Requirements & Inter/Dependencies (Place)
|  |  |  | DEFINITIONS: |  |  |  | KEY FOR COMMENTS SECTION:
|  |  |  | Dependency: Reliance on just one other area to address requirement |  |  |  | Question about whether the workstream has been mapped correctly
|  |  |  | Interdependency: Reliance across multiple areas to address requirement |  |  |  | Remaining interdependencies that I cannot map / unsure about mapping to existing workstreams
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency (what is required from elsewhere in the programme?) | Interdependency (numerous interdependencies from elsewhere in the programme) | With | Comment | Date needed by | Approved?
Place |  | Waste | WASTE-REQ1 | Staff able to do the job, these will need contracts | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ2 | Be able to dispose of waste | Must have | developed together with |  | Fleet
Place |  | Waste | WASTE-REQ3 | Have appropriate vehicles that are under an O’Licence, insured | Must have | has a connection with |  | Transport
Place |  | Waste | WASTE-REQ4 | Have access to fuel | Must have | has a connection with |  | Finance
Place |  | Waste | WASTE-REQ5 | Be able to access routes and in cab data exchange | Must have | requires support from |  | ICT | Requires support from ICT - Service Continuity and ICT - Infrastructure
Place |  | Waste | WASTE-REQ6 | Customer interface in the way residents are used to contacting us now, this may require access to each-others’ systems | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ6 | Customer interface in the way residents are used to contacting us now, this may require access to each-others’ systems | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ7 | Essential outputs for householders (i.e. Collection calendars) | Must have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ8 | Clear lines of management / accountability and ability to redirect resources to support priority services eg from other operational services | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ9 | Priority access to fleet maintenance and support | Must have | requires support from |  | Fleet
Place |  | Waste | WASTE-REQ10 | Officers authorised to place orders etc | Must have | developed together with |  | Finance
Place |  | Waste | WASTE-REQ11 | Team of staff empowered and confident to make decisions | Must have | developed together with |  | HR & OD
Place |  | Waste | WASTE-REQ12 | Hosted arrangement - Clear transfer of the services which would sit within Host Authority. Staffing, communication routes, Officer/Member governance confirmed. | Must have | requires support from |  | All services - all employees
Place |  | Waste | WASTE-REQ13 | Waste data collection and submission resourcing and arrangements confirmed (ie. WasteDataFlow). | Must have | developed together with |  | ICT
Place |  | Waste | WASTE-REQ14 | Governance Model | Must have | developed together with |  | All services - all employees
Place |  | Waste | WASTE-REQ15 | Duly appointed Shareholder Group for AWSL (Governance) and Partnering Board – a contractual requirement | Must have | developed together with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ16 | Methodology for valuing fuel stock for example as at 31/3/23 | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ17 | IT must work e.g. VPN, in-cab devices, | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ18 | DVLA to be advised of vehicle responsibility – Road Fund licence V5 – who will be responsible for taxing the vehicles 1/4/23 | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ19 | LOLER – bin lifts/tail lifts - are we using one supplier for Cumberland | Must have | requires further discussion with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ20 | Ability to check licences - internal or external | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ21 | Tachograph analysis – RHA/FTA | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ22 | Trade Waste Contracts assigned to Cumberland | Must have | developed together with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ23 | Contingency offtakers in Cumberland e.g. bulky waste to Barrow in the past | Must have
Place |  | Waste | WASTE-REQ24 | Decision on AWSL new name if any | Must have
Place |  | Waste | WASTE-REQ25 | Waste Carriers Licence currently in the name of AWSL | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ26 | An understanding about the ownership of CWM | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ27 | Scheme of financial delegation for officers | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ28 | AWSL, CWM and Tivoli (waste element) contracts assigned to Cumberland | Must have | requires further discussion with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ29 | Portfolio Holder in place | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ30 | Alignment on fees and charges | Must have | requires further discussion with |  | Finance
Place |  | Waste | WASTE-REQ31 | Staffing and therefore reporting structure to be in place | Must have | requires further discussion with |  | HR & OD
Place |  | Waste | WASTE-REQ32 | Cumberland branding on RCVs | Must have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ33 | Standardisation of Customer Service roles across Cumberland | Must have |  | requires support from | HR & OD
Place |  | Waste | WASTE-REQ33 | Standardisation of Customer Service roles across Cumberland | Must have |  | developed together with | Customer & Digital
Place |  | Waste | WASTE-REQ34 | Will Cumberland provide H&S advice to AWSL? | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ35 | Will Cumberland provide current SLA services to AWSL? | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ36 | Access to data – ICT systems/Sharepoint | Must have | requires support from |  | ICT | ICT developed with Service Continuity, Applications and Architecture
Place |  | Waste | WASTE-REQ37 | Waste, Green Waste & Recycling collections - Front-line services must happen on day one as they did in March 2022 | Must have | requires support from |  | All services - all employees
Place |  | Waste | WASTE-REQ38 | Vehicles must be legal & safe. Must be insured, serviced & MoT’d. | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ39 | Fuel - Fuel cards or supplies must be available for vehicles | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ40 | Insurance - Vehicles must be insured | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ41 | Vehicle Accident Packs - Must be up-dated with new insurance details etc | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ42 | Bring site emptying - Recycling banks must be emptied. | Must have
Place |  | Waste | WASTE-REQ43 | Waste disposal - Transfer Stations must be open and accepting materials | Must have | developed together with |  | HR & OD
Place |  | Waste | WASTE-REQ44 | Environmental Permits for Ecclerigg & Ulverston Waste Transfer Stations - Must be transferred to WandF. May be covered by the Change Order. Possible joint meeting with CCC, EDC, BBC & EA to resolve. | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ45 | Staff - We must have staff in place, paid, covered by insurance, qualified to do their jobs. | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ46 | Sickness & Holidays - Must be in place for non-desk-based staff. | Must have |  | requires support from | HR & OD
Place |  | Waste | WASTE-REQ46 | Sickness & Holidays - Must be in place for non-desk-based staff. | Must have |  | Requires futher dicussion with | Finance
Place |  | Waste | WASTE-REQ47 | Credit cards - As required, for emergency use. Possibly retain pre-WaF cards. | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ48 | IT systems - Laptops and phone must work. | Must have |  | requires support from | ICT | ICT developed with Service Continuity, Applications and Architecture
Place |  | Waste | WASTE-REQ48 | Software - Core MS Office systems must work. Content must have transferred. Any specific systems must work. | Must have |  | requires support from | ICT | ICT developed with Service Continuity, Applications and Architecture
Place |  | Waste | WASTE-REQ49 | Software - Core MS Office systems must work. Content must have transferred. Any specific systems must work. | Must have |  |  | Finance
Place |  | Waste | WASTE-REQ50 | Utilities - All depots & buildings must have gas, electric, water etc. | Must have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ50 | Utilities - All depots & buildings must have gas, electric, water etc. | Must have |  | requires support from | Finance
Place |  | Waste | WASTE-REQ51 | Payroll - Processes in place to pay staff and process overtime or other claims. | Must have |  | requires support from | HR & OD
Place |  | Waste | WASTE-REQ51 | Payroll - Processes in place to pay staff and process overtime or other claims. | Must have |  | developed together with | Finance
Place |  | Waste | WASTE-REQ52 | Communications - Staff and the public must know what is going on. May require access to each other's systems | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ52 | Communications - Staff and the public must know what is going on. May require access to each other's systems | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ53 | Website - Website content must be transferred & checked. Collection information (calendars) must be available. | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ53 | Website - Website content must be transferred & checked. Collection information (calendars) must be available. | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ54 | Processes - Systems must be in place to log missed collections, bin requests and queries; and allocate to the correct operational area. | Must have | requires support from |  | ICT | ICT developed with Service Continuity, Applications and Architecture
Place |  | Waste | WASTE-REQ55 | Bulky waste - Requests must be received and forwarded to the correct contractor. | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ55 | Bulky waste - Requests must be received and forwarded to the correct contractor. | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ56 | Clinical waste - Requests must be received and forwarded to the correct contractor. | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ56 | Clinical waste - Requests must be received and forwarded to the correct contractor. | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ57 | Hosted arrangement - Clear transfer of the services which would sit within Host Authority. Staffing, communication routes, Officer/Member governance confirmed. | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ58 | Waste data collection and submission resourcing and arrangements confirmed (ie. WasteDataFlow). | Must have | developed together with |  | ICT
Place |  | Waste | WASTE-REQ59 | Branded Calendars are essential from day one | Must have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ60 | Clear lines of Management and accountability – to be able to redirect resources if needed | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ61 | Waste Carrier License's | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ62 | Understanding ownership of CWM | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ63 | Contract assigned to a correct legal entity – mechanism to be agreed (legal advice required) | Must have |  | requires support from | Strategic Commissioning
Place |  | Waste | WASTE-REQ63 | Contract assigned to a correct legal entity – mechanism to be agreed (legal advice required) | Must have |  | developed together with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ64 | Authority representative to be agreed and Governance between Contractor and Authorities | Must have |  | requires support from | Legal & Democratic Services
Place |  | Waste | WASTE-REQ64 | Authority representative to be agreed and Governance between Contractor and Authorities | Must have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ65 | Up to date Authorised Vehicle List for new authorities – AVL to ensure no end dates of 31 March/April 2023 | Must have |  | requires support from | Fleet
Place |  | Waste | WASTE-REQ65 | Up to date Authorised Vehicle List for new authorities – AVL to ensure no end dates of 31 March/April 2024 | Must have |  | developed together with | Transport
Place |  | Waste | WASTE-REQ65 | Up to date Authorised Vehicle List for new authorities – AVL to ensure no end dates of 31 March/April 2025 | Must have |  | developed together with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ66 | New authorities to understand AVL procedure | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ67 | Agreed process for updating and issuing AVL (currently CCC Service Centre) | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ68 | Waste transfer notes for the 2 authorities | Must have | developed together with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ69 | Agreement on HWRC permit system – is it run by one authority or 2? | Must have |  | requires further discussion with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ70 | Agreement on use of HWRCs – can all residents use all sites in Cumberland and Westmorland and Furness? | Must have |  | requires support from |  | Assets
Place |  | Waste | WASTE-REQ70 | Agreement on use of HWRCs – can all residents use all sites in Cumberland and Westmorland and Furness? | Must have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ71 | Agree scope of Helpline and contact arrangements – confirm telephone number, training for helpline team. | Must have |  | requires support from | Strategic Commissioning
Place |  | Waste | WASTE-REQ71 | Agree scope of Helpline and contact arrangements – confirm telephone number, training for helpline team. | Must have |  | developed together with | Customer & Digital
Place |  | Waste | WASTE-REQ72 | Reporting lines to be communicated to RCL | Must have
Place |  | Waste | WASTE-REQ73 | Agreement to pay CCC invoices for the period to 31 March 2023 and new authorities from 01 April 2023 | Must have |  | requires further discussion with | Finance
Place |  | Waste | WASTE-REQ74 | Inter Authority Agreement in place to process payments | Must have |  | requires support from | Finance
Place |  | Waste | WASTE-REQ74 | Inter Authority Agreement in place to process payments | Must have |  | requires support from | Strategic Commissioning
Place |  | Waste | WASTE-REQ75 | How to deal with CCC legacy issues: Accrual/provision | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ76 | Responsibilities for Waste Data Flow to be agreed between new authorities (currently districts for recycling/bring sites and CCC for residua) | Must have |  | requires support from | ICT
Place |  | Waste | WASTE-REQ76 | Responsibilities for Waste Data Flow to be agreed between new authorities (currently districts for recycling/bring sites and CCC for residua) | Must have |  | developed together with | All services - all employees
Place |  | Waste | WASTE-REQ77 | Budgets to be set | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ78 | Access to data – ICT systems/Sharepoint | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ79 | Bulky waste collection | Should have
Place |  | Waste | WASTE-REQ80 | Charges for replacement receptacles | Should have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ80 | Charges for replacement receptacles |  |  | requires support from | Communications and Engagement
Place |  | Waste | WASTE-REQ81 | Consistency in uniform / PPE / badging etc | Should have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ82 | Vehicle livery | Should have | requires support from |  | Fleet
Place |  | Waste | WASTE-REQ83 | Single approach to recruitment, selection and training of new staff starting from 01 April 2023 on common T+Cs, salaries etc | Should have | requires support from |  | Legal & Democratic Services
|  | Waste | WASTE-REQ84 | Consistency in policies and procedures i.e. assisted collections, collection of side waste, missed collections | Should have |  | requires support from | Legal & Democratic Services
Place |  | Waste | WASTE-REQ84 | Consistency in policies and procedures i.e. assisted collections, collection of side waste, missed collections | Should have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ85 | Combined service budgets – clear lines of responsibility | Should have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ86 | Office locations agreed | Should have | requires support from |  | HR & OD | Assets
Place |  | Waste | WASTE-REQ87 | Agreed trade tipping rates | Should have | developed together with |  | Finance
Place |  | Waste | WASTE-REQ88 | Better understanding of Renewi policies that effect the waste collection element of Cumberland | Should have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ89 | Agreement on how to handle complaints and FOIs | Should have | requires further discussion with |  | Customer & Digital
Place |  | Waste | WASTE-REQ90 | Data - Systems should be in place to record data for the new authority. Must happen by end 1st month. | Should have | developed together with |  | ICT | Requires support from ICT - Service Continuity and ICT - Infrastructure, ICT applications
Place |  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | requires support from | Legal & Democratic Services
|  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | developed together with | HR & OD
|  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | developed together with | Strategic Commissioning
|  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | developed together with | Communications and Engagement
Place |  | Waste | WASTE-REQ92 | A better understanding of the contract for the Disposal element of the work | Should have | requires further discussion with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ93 | Consistency in salaries for operational staff – supervisors / loaders / drivers etc | Could have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ94 | Potential to share resources eg at management / supervisory level | Could have | requires further discussion with |  | HR & OD
Place |  | Waste | WASTE-REQ95 | Potential to share vehicles and other resources | Could have |  | requires further discussion with | Fleet
Place |  | Waste | WASTE-REQ95 | Potential to share vehicles and other resources | Could have |  | has a connection with | Transport
Place |  | Waste | WASTE-REQ96 | Agreed position towards membership of national sector organisations and agreement on first point of contact (ie. LARAC, NAWDO, etc) | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ97 | A move towards consistency of IT use | Could have | requires further discussion with |  | ICT
Place |  | Waste | WASTE-REQ98 | An understanding about how current trade waste contracts could possibly be transferred to CWM | Could have |  | requires further discussion with | Strategic Commissioning
Place |  | Waste | WASTE-REQ98 | An understanding about how current trade waste contracts could possibly be transferred to CWM | Could have |  | requires support from | Legal & Democratic Services
Place |  | Waste | WASTE-REQ99 | Standardised H&S procedures e.g. near misses, gate checks, seat belt checks, crew engagement, safety reps | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ100 | ICT – access to Scada system for closed landfill | Could have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ101 | What will permit scheme look like? Pedestrian and Annual Permits? | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ102 | Policies - Existing policies transfer by area. Some policies could have been aligned (closed lid, side waste, lane end). | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ103 | Processes - Some processes could be aligned (assisted collections, requests for larger bins). | Could have |  |  |  | No detail provided
Place |  | Waste | WASTE-REQ104 | National Waste Strategy - Depends on timing of announcement and required actions. | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ105 | Re-branding of PPE - Some could have been done. Potential for hybrid clothing (SLDC fleece, WaF coat etc). | Could have | requires further discussion with |  | Communications and Engagement
Place |  | Waste | WASTE-REQ106 | Agreed position towards membership of national sector organisations and agreement on first point of contact (ie. LARAC, NAWDO, etc) | Could have |  |  |  | No detail provided
Place |  | Waste | WASTE-REQ107 | H&S and Performance, how that is monitored within Westmorland and Furness | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ108 | Awareness training for all waste service employees | Could have | requires support from |  | HR & OD | Assets
Place |  | Waste | WASTE-REQ109 | Environment Agency Permit transfer/UU discharge consents to legal entity (is there a requirement to apply or is this covered by the SCO?) | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ110 | Ability to pay EA subsistence fees for closed landfill from 01 April 2023 | Could have |  | requires support from | Finance
Place |  | Waste | WASTE-REQ110 | Ability to pay EA subsistence fees for closed landfill from 01 April 2023 | Could have |  | requires further discussion with | Strategic Commissioning
Place |  | Waste | WASTE-REQ111 | DCF registration – currently CWM | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ112 | Approach to branding strategy to be agreed and position on Performance Framework to be set out (eg how long CCC branding can remain in place before deductions apply) signs and PPE for site operatives | Could have |  | requires further discussion with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ112 | Approach to branding strategy to be agreed and position on Performance Framework to be set out (eg how long CCC branding can remain in place before deductions apply) signs and PPE for site operatives | Could have |  | developed together with | Customer & Digital
Place |  | Waste | WASTE-REQ113 | Agreement on paying royalty/rents – currently sitting with waste team | Could have | requires further discussion with |  | Finance
Place |  | Waste | WASTE-REQ114 | New authorities to brief CWM site operatives – clear and unambiguous message about what the changes mean for the HWRC sites and customers | Could have |  | requires further discussion with | HR & OD
Place |  | Waste | WASTE-REQ114 | New authorities to brief CWM site operatives – clear and unambiguous message about what the changes mean for the HWRC sites and customers | Could have |  | developed together with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ115 | Commercial gate fees to be agreed with new authorities (currently only Copeland and Allerdale) | Could have | requires further discussion with |  | Finance
Place |  | Waste | WASTE-REQ116 | Agreement on policies eg charities, side waste | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ117 | Schedule of assets for the new authorities (MBT, HWRC, closed landfill) | Could have | requires support from |  | Workstream - Assets | Assets
Place |  | Waste | WASTE-REQ118 | ICT – access to Scada system for closed landfill | Could have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ119 | What will permit scheme look like? Pedestrian and Annual Permits? | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ119 | What will permit scheme look like? Pedestrian and Annual Permits? | Could have |  | has a connection with | Customer & Digital
Place |  | Waste | WASTE-REQ120 | Consistency in service standards | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ121 | Consistency in service design | Won't have | requires further discussion with |  | Waste | Assets
Place |  | Waste | WASTE-REQ122 | Consistency towards commercial waste collections | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ123 | Waste and Recycling policy alignment | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ124 | Consistency in collection frequency | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ125 | Consistency in container type and size | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ126 | Depot rationalisation/location | Won't have |  | requires support from | Workstream - Assets | Assets
Place |  | Waste | WASTE-REQ126 | Depot rationalisation/location | Won't have |  | developed together with | Waste | Assets
Place |  | Waste | WASTE-REQ127 | Re-routing and re-rounding following removal of boundaries | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ128 | Efficient direct delivery from the North of Allerdale to Hespin Wood but could have! | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ129 | Decision on in-house v LATCo model | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ130 | Opportunity to rationalise/standardise Bring Banks | Won't have | requires support from |  | Waste
Place |  | Waste | WASTE-REQ131 | Consistency in service standards | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ132 | Consistency in service design | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ133 | Consistency towards commercial waste collections | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ134 | Re-branding of bins & boxes - Not urgent, can be done as new items, bins etc are ordered. | Won't have | requires support from |  | Communications & Engagement
Place |  | Waste | WASTE-REQ134 | Re-branding of vehicles - Not urgent, can be done as new vehicles are ordered or as prioritised. | Won't have | requires support from |  | Communications & Engagement
Place |  | Waste | WASTE-REQ135 | In-cab systems - Too complex to introduce by day 1. | Won't have | requires further discussion with |  | ICT
Place |  | Waste | WASTE-REQ136 | Round changes - Any round or route changes must be embedded by December 2022. | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ137 | Waste and Recycling Policy alignment and Consistency in collection frequency and containers | Won't have | requires further discussion with |  | Waste | Assets
Place |  | Waste | WASTE-REQ138 | Reviewed Bring Sites within Westmorland and Furness | Won't have | requires further discussion with |  |  | Assets
Place |  | Waste | WASTE-REQ139 | Agreement on enforcement powers, eg suspected trade waste abuse at HWRCs | Won't have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ140 | New HWRC permit scheme | Won't have | requires further discussion with |  | Strategic Commissioning
Place |  | Climate Change/Net Zero | CLIMATE-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have | developed together with | developed together with | Planning and Building Control |  |  | Summer 2022
Place |  | Climate Change/Net Zero | CLIMATE-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have |  |  | Street Scene and Open Spaces |  |  | Summer 2022
Place |  | Climate Change/Net Zero | CLIMATE-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have |  |  | Community/Localism
Place |  | Climate Change/Net Zero | CLIMATE-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have |  |  | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ2 | Officer to work on Annual Status Report (Due to be submitted to DEFRA by June) | Must have | requires support from | requires support from | Legal & Democratic Services |  |  | By June 2023
Place |  | Climate Change/Net Zero | CLIMATE-REQ2 | Officer to work on Annual Status Report (Due to be submitted to DEFRA by June) | Must have | requires support from | requires support from | Street Scene and Open Spaces
Place |  | Climate Change/Net Zero | CLIMATE-REQ2 | Officer to work on Annual Status Report (Due to be submitted to DEFRA by June) | Must have | requires support from | requires support from | Public Health
Place |  | Climate Change/Net Zero | CLIMATE-REQ2 | Officer to work on Annual Status Report (Due to be submitted to DEFRA by June) | Must have | requires support from | requires support from | Public Protection
Place |  | Climate Change/Net Zero | CLIMATE-REQ3 | ACB Arrangements for existing projects and supporting resources - check acronym | Must have | [5 empty] | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ4 | Formal Grant Agreement and funding arrangements have been transferred eg Account Body Status | Must have | requires further discussion with | Legal & Democratic Services | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ4 | Formal Grant Agreement and funding arrangements have been transferred eg Account Body Status | Must have | requires further discussion with |  | Finance |  |  | 2023-04-02
Place |  | Climate Change/Net Zero | CLIMATE-REQ4 | Formal Grant Agreement and funding arrangements have been transferred eg Account Body Status | Must have | requires further discussion with |  | Grants Portfolio |  |  | 2023-04-03
Place |  | Climate Change/Net Zero | CLIMATE-REQ4 | Formal Grant Agreement and funding arrangements have been transferred eg Account Body Status | Must have | requires further discussion with |  | Contract Management/Monitoring |  |  | 2023-04-04
Place |  | Climate Change/Net Zero | CLIMATE-REQ5 | Policy in place to ensure compliance with current legislation eg Environment Act 2021 Requirements - incl Biodiversity Net Gain | Must have |  | requires support from | Policy Framework |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ5 | Policy in place to ensure compliance with current legislation eg Environment Act 2021 Requirements - incl Biodiversity Net Gain | Must have |  | requires support from | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ6 | Staffing and financial resource to ensure requirements can be met | Must have |  | is dependant on as a precursor | HR & OD |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ6 | Staffing and financial resource to ensure requirements can be met | Must have |  | is dependant on as a precursor | Finance
Place |  | Climate Change/Net Zero | CLIMATE-REQ7 | Flood and Water Management Act - Lead Local Flood Authority | Must have | requires further discussion with |  | Highways |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ8 | Robust Climate Risk Assessment | Must have |  | developed together with | Risk Management & Business Continuity |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ8 | Robust Climate Risk Assessment | Must have |  | developed together with | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ9 | Procurement policy covering social value incl Environmental Stability (PPN 06/20, 06/21, Social Value Act) | Must have |  | requires further discussion with | Strategic Procurement / Strategy​ |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ9 | Procurement policy covering social value incl Environmental Stability (PPN 06/20, 06/21, Social Value Act) | Must have |  | requires further discussion with | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ10 | Sustainability assessment of planning decisions | Must have |  | developed together with | Planning and Building Control |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ10 | Sustainability assessment of planning decisions | Must have |  | developed together with | Housing
Place |  | Climate Change/Net Zero | CLIMATE-REQ11 | Coast Protection Authorities and Coastal Erosion Risk Management Authorities | Must have | developed together with |  | Highways |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ12 | Civil Contingencies Act 2004 - dealing with emergencies (Community Risk Register) | Must have | is dependant on as a precursor |  | Resilience and Emergency Planning |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ13 | Assurance that LGR Programme interdependencies with cross-cutting themes are managed (eg via climate impact assessment) | Must have | is dependant on as a precursor |  | All services - all line managers |  |  | Now onwards
Place |  | Climate Change/Net Zero | CLIMATE-REQ14 | Net Zero target | Should have |  | requires further discussion with | All services - all line managers |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ14 | Net Zero target | Should have |  | requires further discussion with | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ14 | Net Zero target | Should have |  | requires further discussion with | Transformation & Change Management
Place |  | Climate Change/Net Zero | CLIMATE-REQ15 | Route map for compliance with Climate Change Act - Net Zero by 2037/2049 | Should have |  | requires further discussion with | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ15 | Route map for compliance with Climate Change Act - Net Zero by 2037/2050 | Should have |  | requires further discussion with | Transformation & Change Management |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ16 | Clear links with partnerships | Should have |  | developed together with | Community/Localism |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ16 | Clear links with partnerships | Should have |  | developed together with | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ17 | Strategy: Action Plan for Climate Change, Environment and Biodiversity | Should have |  | requires further discussion with | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ17 | Strategy: Action Plan for Climate Change, Environment and Biodiversity | Should have |  | requires further discussion with | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ18 | Adaptation strategy and plan | Should have |  | requires support from | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ18 | Adaptation strategy and plan | Should have |  | requires support from | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ19 | Procurement policy that priorities Climate/Sustainability above mandatory levels | Should have | is dependant on as a precursor |  | Strategic Procurement / Strategy​ |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ20 | Climate Data monitoring | Should have | requires further discussion with |  | Performance & Business Intelligence |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ20 | Climate Governance - Board, Steering Group | Should have | is dependant on as a precursor |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ20 | Climate Governance - Board, Steering Group | Should have | is dependant on as a precursor |  | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ21 | Local Energy strategy | Should have |  | requires further discussion with | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ21 | Local Energy strategy | Should have |  | requires further discussion with | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ21 | Local Energy strategy | Should have |  | requires further discussion with | Capital Programme
Place |  | Climate Change/Net Zero | CLIMATE-REQ21 | Local Energy strategy | Should have |  | requires further discussion with | Economic Development
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Long term financial plan for mitigation and adaptation | Should have | is dependant on as a precursor |  | Finance |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Internal climate change action plan (emissions reduction etc) linked to Corporate KPIs | Should have |  | requires further discussion with | Policy Framework |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Internal climate change action plan (emissions reduction etc) linked to Corporate KPIs | Should have |  | requires further discussion with | All services - all line managers |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Biodiversity to be integrated to work stream and corporate priorities | Should have | developed together with |  | All services - all line managers |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Key expert staff in place around climate change, biodiversity, decarbonisation | Should have | requires support from |  | HR & OD |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ23 | Assessment of climate and ecological implications of key decisions | Should have |  | requires further discussion with | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ23 | Assessment of climate and ecological implications of key decisions | Should have |  |  | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ23 | Website - information for public on climate change, links to strategies, carbon footprint etc | Should have | requires further discussion with |  | Communications and Engagement |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ24 | Stakeholder Engagement Plan | Should have | requires further discussion with |  | Communications and Engagement |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ24 | Stakeholder Engagement Plan | Should have | requires further discussion with |  | Community/Localism
Place |  | Climate Change/Net Zero | CLIMATE-REQ25 | Budget (for Climate Communication, projects community engagement) | Should have | is dependant on as a precursor |  | Finance |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ26 | Climate Comms Strategy | Should have | requires further discussion with |  | Communications and Engagement |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ27 | HR Policies (eg recruitment, performance training) linked to sustainability | Should have | requires further discussion with |  | HR & OD |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ28 | Declaration of Climate Emergency | Could have | has a connection with |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ29 | Climate Champions in all different services within new authorities | Could have | requires further discussion with |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ30 | Retain successful council partnerships | Could have | requires further discussion with |  | Community/Localism |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ31 | Carbon literacy training to be implemented in induction for staff | Could have | requires further discussion with |  | Learning & Development |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ32 | Nominations to existing external partnerships (eg ZCCP) | Could have | developed together with |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ33 | Carbon accounting methodology and mechanisms | Could have | developed together with |  | Performance & Business Intelligence
Place |  | Climate Change/Net Zero | CLIMATE-REQ34 | Adaptation strategy and plan - duplication (also down as Should Have) | Could have |  |  | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ35 | Net Zero Operational target (also down as Should Have) | Could have |  |  | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ36 | Net Zero geographical target (does this differ from above?) | Could have |  |  | Policy Framework |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ37 | Memberships (APSE etc) | Could have | developed together with |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ38 | Net Zero software / tool | Could have | developed together with |  | Performance & Business Intelligence |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ39 | Clear roles and responsibilities to ensure delivery | Could have | is dependant on as a precursor |  | HR & OD |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ40 | Net Zero Skills audits | Could have | is dependant on as a precursor |  | Learning & Development |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ41 | Budgets for consultants | Could have |  | is dependant on as a precursor | Finance |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ41 | Budgets for consultants | Could have |  | is dependant on as a precursor | Highways
Place |  | Climate Change/Net Zero | CLIMATE-REQ41 | Budgets for consultants | Could have |  | is dependant on as a precursor | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ42 | Electric Vehicle transition / infrastructure plan | Could have |  | developed together with | Fleet
Place |  | Climate Change/Net Zero | CLIMATE-REQ42 | Electric Vehicle transition / infrastructure plan | Could have |  | developed together with | Transport
Place |  | Climate Change/Net Zero | CLIMATE-REQ43 | Net Zero operational emissions | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ44 | Council-owned energy company | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ45 | Community energy ownership schemes | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ46 | Mechanisms for non-financial climate and nature related disclosures | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ47 | Ability to achieve Net Zero by 2037 (ie budget, resources, policies etc) | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ48 | Sufficient resources or budget to address climate and nature crises urgently enough | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ49 | Low carbon affordable mobility strategy | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ50 | Robust and funded active travel infrastructure | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ51 | Internal biodiversity net gain principle for council projects | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ52 | Carbon Accounting (duplication - also down as Could Have) | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ53 | Tree Planting target | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ54 | Updated Local Plan - sustainability embedded into policies | Won't have |  |  |  | No detail provided
Place |  | Housing |  | Budgets & managing performance within departments, approval limits established, performance reporting in place | Must Have | is reliant upon decisions being made by
|  | Housing |  | Out Of Hours Service | Must Have | is reliant upon decisions being made by
|  | Housing |  | Branded Website with links and Duty to Refer emails | Must Have | developed together with
|  | Housing |  | Fees & Charges should align | Must Have | is reliant upon decisions being made by
|  | Housing |  | Essential standard policies for statutory services, e.g. DFG | Must Have | is reliant upon decisions being made by
|  | Housing |  | IT relevant to service - Locata. Flare, Civica CBL, Northgate, Idox, Anite, Info at work, Civicare, HIA foundations case manager, Abavus my council services, Ferret, Case management systems. Flare is needed but may not be fuctioning by vesting day. | Must Have | requires support from
|  | Housing |  | Branding, name badges and ID for stat visits | Must Have | requires support from
|  | Housing |  | Core Support Services such as: Finance, Business Support, Legal, HR & IT. Able to recruit. | Must Have | requires support from
|  | Housing |  | Supported Accomodation Contract/Grant Agreements | Must Have | requires support from
|  | Housing |  | Contractor relationships and processes need to continue for day one. | Must Have | is reliant upon decisions being made by
|  | Housing |  | DA Crisis contact numbers | Must Have | requires further discussion with
|  | Housing |  | CBL Fully operational | Must Have | requires support from
|  | Housing |  | Consitution for Officers delegations | Must Have | is reliant upon decisions being made by
|  | Housing |  | Customers can dial in and email, self serve on day 1 - different legacy council has different triage proesses and that needs to be maintained for day 1 | Must Have | requires support from
|  | Housing |  | Executive functions to take reports | Must Have | is reliant upon decisions being made by
|  | Housing |  | DFG funding payments, approvals, financial delegations. | Must Have | requires support from
|  | Housing |  | Process for dealing with homeless appeals / approvals | Must Have | is reliant upon decisions being made by
|  | Housing |  | Green homes grant structures / team | Must Have | is reliant upon decisions being made by
|  | Housing |  | Government delta returns & HCLIC need to be possible. (Flag discussion around aggregation of returns for new council). | Must Have | requires support from
|  | Housing |  | procedure for referrals from OTs and Health absed childrens OT need to be agreed and tested | Must Have | is reliant upon decisions being made by
|  | Housing |  | Training on day 1 changes for the teams | Must Have | requires support from
|  | Housing |  | Service for homeless families to assess applications and be able to provide temp accomodation and wider support for children/safeguarding process | Must Have | requires support from
|  | Housing |  | Landlord functions and Urgent response for Council tenants (e.g. repairs). Where there are districts providing Landlord services, standards and policies need to be aligned for Day 1. | Must Have | requires support from
|  | Housing |  | Procedures, hand off points between teams etc | Should Have | requires support from
|  | Housing |  | Premises to operate from and teams in place in each service area to meet service demand. | Should Have | requires support from
|  | Housing |  | Plans to identify existing contracts and how to align, novate etc | Should Have | requires support from
|  | Housing |  | Identifying non priority Policies and plan to review these and timescale | Should Have | requires further discussion with
|  | Housing |  | Revised Constitution | Should Have | requires support from
|  | Housing |  | Identify areas that may need new procurement | Should Have | requires support from
|  | Housing |  | A plan to align relevant Strategies, e.g. Housing Strategy - what will the priorities be? | Should Have | requires further discussion with
|  | Housing |  | Plan to review partnerships | Should Have | requires support from
|  | Housing |  | Effective policies for DFGs, HHSRS and HMOs | Should Have | requires further discussion with
|  | Housing |  | Local Plan policies in place | Should Have | requires support from
|  | Housing |  | Identitly of new teams and processes to manage them effectively | Should Have | developed together with
|  | Housing |  | review HIA, options going forward. :better homes agency" | Should Have | requires further discussion with
|  | Housing |  | funding agreements, LAD, domestic abuse | Should Have | requires support from
|  | Housing |  | Direcction of travel for aligning Planning Policies | Should Have | requires further discussion with
|  | Housing |  | internal procedures, reviewed. process based. | Should Have | requires support from
|  | Housing |  | updated letterheads,licence docs, offcial paperwork to the customer | Should Have | requires further discussion with
|  | Housing |  | started to review staffing and roles, Job Descriptions | Should Have | requires support from
|  | Housing |  | Analysis of which partnerships are still required and new partnershps needed | Should Have | requires further discussion with
|  | Housing |  | Clear guidelines and timelines for staff on emerging structures still not in place | Should Have | requires support from
|  | Housing |  | identify policies that are required and considered to approval at new Executive | Should Have | requires support from
|  | Housing |  | review IT systems, not common accross and consider options. | Should Have | requires support from
|  | Housing |  | consolidation of some policy. updated to improve services | Should Have | requires further discussion with
|  | Housing |  | Common Quality Standards | Should Have | requires further discussion with
|  | Housing |  | Staff training programme in place and rolling out to embedd new culture, policies changes, new IT, workarounds etc | Should Have | requires support from
|  | Housing |  | Clear decision making and escalation routes | Should Have | requires further discussion with
|  | Housing |  | streamine none day 1 critical policy and process for discretionary activity so no postcode lottery | Should Have | requires support from
|  | Housing |  | Plans around HIA development and timeline | Should Have
|  | Housing |  | Streamlined Homelessness and Housing Strategies Private sector Housing Grants policies | Should Have | requires support from
|  | Housing |  | review of policies and procedures, KPI's/monitoring frameworks partner agencies arrangements | Should Have | requires further discussion with
|  | Housing |  | team management lines for comms, 1-1s, team meetings in place | Should Have | requires support from
|  | Housing |  | Staff training programmes, appraisal processes agreed | Should Have | requires further discussion with
|  | Housing |  | full team | Should Have | is reliant upon decisions being made by
|  | Housing |  | internal policies/training for colleagues ie GDPR, safeguarding, E&D, new LA priorities | Should Have | requires support from
|  | Housing |  | Partnerships reviewed and resstrucutred eg Cumbria Housing Group (and subgroups) and the Social Landlord/LA group plus agree what is happening with local partnerships | Should Have | requires support from
|  | Housing |  | team know who to report to if different to current arrangments | Should Have | requires further discussion with
|  | Housing |  | appraisals and training plans & priorities of the new council, to aid delivery | Should Have | requires support from
|  | Housing |  | Strategic partnerships | Could Have | requires support from
|  | Housing |  | Strategic housing priorities | Could Have
|  | Housing |  | Integrated DFG team with OTs, etc | Could Have
|  | Housing |  | Alignment of contracts - Locata | Could Have | requires support from
|  | Housing |  | Consistent template agreements, e.g. grants etc | Could Have | requires further discussion with
|  | Housing |  | Some alignment of key policies | Could Have | requires support from
|  | Housing |  | One service team across the whole LA, ie homelessness | Could Have | requires further discussion with
|  | Housing |  | MDT of colleagues dealing with DFG's - OT's, Asc, HIA | Could Have
|  | Housing |  | Working partnership groups with Rp,s developers, Vol sector, | Could Have | requires support from
|  | Housing |  | Align the HoC properties with BBC housing stock to be managed inhouse | Could Have | requires support from
|  | Housing |  | Model for delivering Green Homes/sustainable warnth & bididng for new fundign opportunities | Could Have | requires further discussion with
|  | Housing |  | Domestic Abuse strategy | Could Have | requires further discussion with
|  | Housing |  | settled teams who all know their own roles/responsibilities | Could Have | requires support from
|  | Housing |  | Local Housing Company | Could Have | requires support from
|  | Housing |  | Shared contracts in place for DFGs, ECO | Could Have | requires further discussion with
|  | Housing |  | A model for a new HIA or Better Homes Agency | Could Have
|  | Housing |  | Started work around joint working polcies, practices | Could Have | requires further discussion with
|  | Housing |  | Rebranding of Officer equipment, letters, communication | Could Have | requires support from
|  | Housing |  | Started to look at Intergration of DFG within ASC | Could Have | requires further discussion with
|  | Housing |  | Uniformed Services for Homeless Services, Housing Asssitance, tenancy advocacy | Could Have
|  | Housing |  | empty homes strategy in plae for each unitary | Could Have | requires support from
|  | Housing |  | Integrated needs assessment for complex cases ASC/Homelessness/DFGs etc | Could Have
|  | Housing |  | acess to data within east and west so staff can cover all areas not jsut legalcy footprint and provide OOH effectively | Could Have | requires support from
|  | Housing |  | Integrated OT/DFG teams | Could Have | is reliant upon decisions being made by
|  | Housing |  | HIA for each new Unitary | Could Have
|  | Housing |  | one OOH shared system integrated with Social Care duty teams | Could Have
|  | Housing |  | shared budgets for homeless prevention | Could Have | requires support from
|  | Housing |  | LHC registered and linking with econmic regen plans | Could Have
|  | Housing |  | Social Care white paper delivery/transition plan | Could Have | requires further discussion with
|  | Housing |  | One DFG service/meanstesting/ top ups etc | Could Have
|  | Housing |  | Every strategy related not likely to be in place. | Won't Have
|  | Housing |  | All contracts aligned. | Won't Have | requires support from
|  | Housing |  | Aligned evidence base, e.g. stock condition survey or other evidence supporting strategic development - homeless reviews | Won't Have
|  | Housing |  | Consistent approach/funding opportunities in some areas, e.g. empty homes | Won't Have | requires support from
|  | Housing |  | Definitive operating model | Won't Have
|  | Housing |  | new team/structure in place, forums/working groups/partnerships | Won't Have | requires support from
|  | Housing |  | One Team - all speaking with one voice | Won't Have | requires support from
|  | Housing |  | all the necessary policies/procedures in place and/or aligned | Won't Have
|  | Housing |  | same team structure across the LA | Won't Have | requires further discussion with
|  | Housing |  | budgets | Won't Have | requires support from
|  | Housing |  | a new vision/culture - YET | Won't Have
|  | Housing |  | aligned pay/conditions | Won't Have | requires support from
|  | Housing |  | settled teams/colleagues | Won't Have | developed together with
|  | Housing |  | job descriptions/role profiles consistent | Won't Have | requires support from
|  | Housing |  | All new teams and systems in place | Won't Have | requires support from
|  | Housing |  | Consistent approach to Officers decisions, autonomy | Won't Have
|  | Housing |  | Shared IT systems for areas of work, specific to work area. FLARE, CASE MANAGER | Won't Have | requires support from
|  | Housing |  | Culture change, Carlisle works on three C's | Won't Have | requires support from
|  | Housing |  | Shared department budgets, equipment, training, resources | Won't Have | developed together with
|  | Housing |  | VR on the table around staffing | Won't Have | is reliant upon decisions being made by
|  | Housing |  | Full commonality in response across the new area | Won't Have
|  | Housing |  | Fully intergated teams and structures | Won't Have | requires support from
|  | Housing |  | Common contractual arrangements | Won't Have | requires support from
Housing
Housing
Housing
Housing
Housing
Housing
Housing
Housing
Housing
Housing

## Day1 Reqs&Depends (Place) (hidden)
Day1 Requirements & Inter/Dependencies (Place)
|  |  |  | DEFINITIONS: |  |  |  | KEY FOR COMMENTS SECTION:
|  |  |  | Dependency: Reliance on just one other area to address requirement |  |  |  | Question about whether the workstream has been mapped correctly
|  |  |  | Interdependency: Reliance across multiple areas to address requirement |  |  |  | Remaining interdependencies that I cannot map / unsure about mapping to existing workstreams
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency (what is required from elsewhere in the programme?) | Interdependency (numerous interdependencies from elsewhere in the programme) | With | Comment | Date needed by | Approved?
Place |  | Waste | WASTE-REQ1 | Staff able to do the job, these will need contracts | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ2 | Be able to dispose of waste | Must have | developed together with |  | Fleet
Place |  | Waste | WASTE-REQ3 | Have appropriate vehicles that are under an O’Licence, insured | Must have | has a connection with |  | Transport
Place |  | Waste | WASTE-REQ4 | Have access to fuel | Must have | has a connection with |  | Finance
Place |  | Waste | WASTE-REQ5 | Be able to access routes and in cab data exchange | Must have | requires support from |  | ICT | Requires support from ICT - Service Continuity and ICT - Infrastructure
Place |  | Waste | WASTE-REQ6 | Customer interface in the way residents are used to contacting us now, this may require access to each-others’ systems | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ6 | Customer interface in the way residents are used to contacting us now, this may require access to each-others’ systems | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ7 | Essential outputs for householders (i.e. Collection calendars) | Must have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ8 | Clear lines of management / accountability and ability to redirect resources to support priority services eg from other operational services | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ9 | Priority access to fleet maintenance and support | Must have | requires support from |  | Fleet
Place |  | Waste | WASTE-REQ10 | Officers authorised to place orders etc | Must have | developed together with |  | Finance
Place |  | Waste | WASTE-REQ11 | Team of staff empowered and confident to make decisions | Must have | developed together with |  | HR & OD
Place |  | Waste | WASTE-REQ12 | Hosted arrangement - Clear transfer of the services which would sit within Host Authority. Staffing, communication routes, Officer/Member governance confirmed. | Must have | requires support from |  | All services - all employees
Place |  | Waste | WASTE-REQ13 | Waste data collection and submission resourcing and arrangements confirmed (ie. WasteDataFlow). | Must have | developed together with |  | ICT
Place |  | Waste | WASTE-REQ14 | Governance Model | Must have | developed together with |  | All services - all employees
Place |  | Waste | WASTE-REQ15 | Duly appointed Shareholder Group for AWSL (Governance) and Partnering Board – a contractual requirement | Must have | developed together with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ16 | Methodology for valuing fuel stock for example as at 31/3/23 | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ17 | IT must work e.g. VPN, in-cab devices, | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ18 | DVLA to be advised of vehicle responsibility – Road Fund licence V5 – who will be responsible for taxing the vehicles 1/4/23 | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ19 | LOLER – bin lifts/tail lifts - are we using one supplier for Cumberland | Must have | requires further discussion with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ20 | Ability to check licences - internal or external | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ21 | Tachograph analysis – RHA/FTA | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ22 | Trade Waste Contracts assigned to Cumberland | Must have | developed together with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ23 | Contingency offtakers in Cumberland e.g. bulky waste to Barrow in the past | Must have
Place |  | Waste | WASTE-REQ24 | Decision on AWSL new name if any | Must have
Place |  | Waste | WASTE-REQ25 | Waste Carriers Licence currently in the name of AWSL | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ26 | An understanding about the ownership of CWM | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ27 | Scheme of financial delegation for officers | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ28 | AWSL, CWM and Tivoli (waste element) contracts assigned to Cumberland | Must have | requires further discussion with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ29 | Portfolio Holder in place | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ30 | Alignment on fees and charges | Must have | requires further discussion with |  | Finance
Place |  | Waste | WASTE-REQ31 | Staffing and therefore reporting structure to be in place | Must have | requires further discussion with |  | HR & OD
Place |  | Waste | WASTE-REQ32 | Cumberland branding on RCVs | Must have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ33 | Standardisation of Customer Service roles across Cumberland | Must have |  | requires support from | HR & OD
Place |  | Waste | WASTE-REQ33 | Standardisation of Customer Service roles across Cumberland | Must have |  | developed together with | Customer & Digital
Place |  | Waste | WASTE-REQ34 | Will Cumberland provide H&S advice to AWSL? | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ35 | Will Cumberland provide current SLA services to AWSL? | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ36 | Access to data – ICT systems/Sharepoint | Must have | requires support from |  | ICT | ICT developed with Service Continuity, Applications and Architecture
Place |  | Waste | WASTE-REQ37 | Waste, Green Waste & Recycling collections - Front-line services must happen on day one as they did in March 2022 | Must have | requires support from |  | All services - all employees
Place |  | Waste | WASTE-REQ38 | Vehicles must be legal & safe. Must be insured, serviced & MoT’d. | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ39 | Fuel - Fuel cards or supplies must be available for vehicles | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ40 | Insurance - Vehicles must be insured | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ41 | Vehicle Accident Packs - Must be up-dated with new insurance details etc | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ42 | Bring site emptying - Recycling banks must be emptied. | Must have
Place |  | Waste | WASTE-REQ43 | Waste disposal - Transfer Stations must be open and accepting materials | Must have | developed together with |  | HR & OD
Place |  | Waste | WASTE-REQ44 | Environmental Permits for Ecclerigg & Ulverston Waste Transfer Stations - Must be transferred to WandF. May be covered by the Change Order. Possible joint meeting with CCC, EDC, BBC & EA to resolve. | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ45 | Staff - We must have staff in place, paid, covered by insurance, qualified to do their jobs. | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ46 | Sickness & Holidays - Must be in place for non-desk-based staff. | Must have |  | requires support from | HR & OD
Place |  | Waste | WASTE-REQ46 | Sickness & Holidays - Must be in place for non-desk-based staff. | Must have |  | Requires futher dicussion with | Finance
Place |  | Waste | WASTE-REQ47 | Credit cards - As required, for emergency use. Possibly retain pre-WaF cards. | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ48 | IT systems - Laptops and phone must work. | Must have |  | requires support from | ICT | ICT developed with Service Continuity, Applications and Architecture
Place |  | Waste | WASTE-REQ48 | Software - Core MS Office systems must work. Content must have transferred. Any specific systems must work. | Must have |  | requires support from | ICT | ICT developed with Service Continuity, Applications and Architecture
Place |  | Waste | WASTE-REQ49 | Software - Core MS Office systems must work. Content must have transferred. Any specific systems must work. | Must have |  |  | Finance
Place |  | Waste | WASTE-REQ50 | Utilities - All depots & buildings must have gas, electric, water etc. | Must have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ50 | Utilities - All depots & buildings must have gas, electric, water etc. | Must have |  | requires support from | Finance
Place |  | Waste | WASTE-REQ51 | Payroll - Processes in place to pay staff and process overtime or other claims. | Must have |  | requires support from | HR & OD
Place |  | Waste | WASTE-REQ51 | Payroll - Processes in place to pay staff and process overtime or other claims. | Must have |  | developed together with | Finance
Place |  | Waste | WASTE-REQ52 | Communications - Staff and the public must know what is going on. May require access to each other's systems | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ52 | Communications - Staff and the public must know what is going on. May require access to each other's systems | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ53 | Website - Website content must be transferred & checked. Collection information (calendars) must be available. | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ53 | Website - Website content must be transferred & checked. Collection information (calendars) must be available. | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ54 | Processes - Systems must be in place to log missed collections, bin requests and queries; and allocate to the correct operational area. | Must have | requires support from |  | ICT | ICT developed with Service Continuity, Applications and Architecture
Place |  | Waste | WASTE-REQ55 | Bulky waste - Requests must be received and forwarded to the correct contractor. | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ55 | Bulky waste - Requests must be received and forwarded to the correct contractor. | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ56 | Clinical waste - Requests must be received and forwarded to the correct contractor. | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ56 | Clinical waste - Requests must be received and forwarded to the correct contractor. | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ57 | Hosted arrangement - Clear transfer of the services which would sit within Host Authority. Staffing, communication routes, Officer/Member governance confirmed. | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ58 | Waste data collection and submission resourcing and arrangements confirmed (ie. WasteDataFlow). | Must have | developed together with |  | ICT
Place |  | Waste | WASTE-REQ59 | Branded Calendars are essential from day one | Must have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ60 | Clear lines of Management and accountability – to be able to redirect resources if needed | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ61 | Waste Carrier License's | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ62 | Understanding ownership of CWM | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ63 | Contract assigned to a correct legal entity – mechanism to be agreed (legal advice required) | Must have |  | requires support from | Strategic Commissioning
Place |  | Waste | WASTE-REQ63 | Contract assigned to a correct legal entity – mechanism to be agreed (legal advice required) | Must have |  | developed together with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ64 | Authority representative to be agreed and Governance between Contractor and Authorities | Must have |  | requires support from | Legal & Democratic Services
Place |  | Waste | WASTE-REQ64 | Authority representative to be agreed and Governance between Contractor and Authorities | Must have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ65 | Up to date Authorised Vehicle List for new authorities – AVL to ensure no end dates of 31 March/April 2023 | Must have |  | requires support from | Fleet
Place |  | Waste | WASTE-REQ65 | Up to date Authorised Vehicle List for new authorities – AVL to ensure no end dates of 31 March/April 2024 | Must have |  | developed together with | Transport
Place |  | Waste | WASTE-REQ65 | Up to date Authorised Vehicle List for new authorities – AVL to ensure no end dates of 31 March/April 2025 | Must have |  | developed together with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ66 | New authorities to understand AVL procedure | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ67 | Agreed process for updating and issuing AVL (currently CCC Service Centre) | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ68 | Waste transfer notes for the 2 authorities | Must have | developed together with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ69 | Agreement on HWRC permit system – is it run by one authority or 2? | Must have |  | requires further discussion with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ70 | Agreement on use of HWRCs – can all residents use all sites in Cumberland and Westmorland and Furness? | Must have |  | requires support from |  | Assets
Place |  | Waste | WASTE-REQ70 | Agreement on use of HWRCs – can all residents use all sites in Cumberland and Westmorland and Furness? | Must have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ71 | Agree scope of Helpline and contact arrangements – confirm telephone number, training for helpline team. | Must have |  | requires support from | Strategic Commissioning
Place |  | Waste | WASTE-REQ71 | Agree scope of Helpline and contact arrangements – confirm telephone number, training for helpline team. | Must have |  | developed together with | Customer & Digital
Place |  | Waste | WASTE-REQ72 | Reporting lines to be communicated to RCL | Must have
Place |  | Waste | WASTE-REQ73 | Agreement to pay CCC invoices for the period to 31 March 2023 and new authorities from 01 April 2023 | Must have |  | requires further discussion with | Finance
Place |  | Waste | WASTE-REQ74 | Inter Authority Agreement in place to process payments | Must have |  | requires support from | Finance
Place |  | Waste | WASTE-REQ74 | Inter Authority Agreement in place to process payments | Must have |  | requires support from | Strategic Commissioning
Place |  | Waste | WASTE-REQ75 | How to deal with CCC legacy issues: Accrual/provision | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ76 | Responsibilities for Waste Data Flow to be agreed between new authorities (currently districts for recycling/bring sites and CCC for residua) | Must have |  | requires support from | ICT
Place |  | Waste | WASTE-REQ76 | Responsibilities for Waste Data Flow to be agreed between new authorities (currently districts for recycling/bring sites and CCC for residua) | Must have |  | developed together with | All services - all employees
Place |  | Waste | WASTE-REQ77 | Budgets to be set | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ78 | Access to data – ICT systems/Sharepoint | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ79 | Bulky waste collection | Should have
Place |  | Waste | WASTE-REQ80 | Charges for replacement receptacles | Should have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ80 | Charges for replacement receptacles |  |  | requires support from | Communications and Engagement
Place |  | Waste | WASTE-REQ81 | Consistency in uniform / PPE / badging etc | Should have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ82 | Vehicle livery | Should have | requires support from |  | Fleet
Place |  | Waste | WASTE-REQ83 | Single approach to recruitment, selection and training of new staff starting from 01 April 2023 on common T+Cs, salaries etc | Should have | requires support from |  | Legal & Democratic Services
|  | Waste | WASTE-REQ84 | Consistency in policies and procedures i.e. assisted collections, collection of side waste, missed collections | Should have |  | requires support from | Legal & Democratic Services
Place |  | Waste | WASTE-REQ84 | Consistency in policies and procedures i.e. assisted collections, collection of side waste, missed collections | Should have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ85 | Combined service budgets – clear lines of responsibility | Should have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ86 | Office locations agreed | Should have | requires support from |  | HR & OD | Assets
Place |  | Waste | WASTE-REQ87 | Agreed trade tipping rates | Should have | developed together with |  | Finance
Place |  | Waste | WASTE-REQ88 | Better understanding of Renewi policies that effect the waste collection element of Cumberland | Should have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ89 | Agreement on how to handle complaints and FOIs | Should have | requires further discussion with |  | Customer & Digital
Place |  | Waste | WASTE-REQ90 | Data - Systems should be in place to record data for the new authority. Must happen by end 1st month. | Should have | developed together with |  | ICT | Requires support from ICT - Service Continuity and ICT - Infrastructure, ICT applications
Place |  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | requires support from | Legal & Democratic Services
|  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | developed together with | HR & OD
|  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | developed together with | Strategic Commissioning
|  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | developed together with | Communications and Engagement
Place |  | Waste | WASTE-REQ92 | A better understanding of the contract for the Disposal element of the work | Should have | requires further discussion with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ93 | Consistency in salaries for operational staff – supervisors / loaders / drivers etc | Could have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ94 | Potential to share resources eg at management / supervisory level | Could have | requires further discussion with |  | HR & OD
Place |  | Waste | WASTE-REQ95 | Potential to share vehicles and other resources | Could have |  | requires further discussion with | Fleet
Place |  | Waste | WASTE-REQ95 | Potential to share vehicles and other resources | Could have |  | has a connection with | Transport
Place |  | Waste | WASTE-REQ96 | Agreed position towards membership of national sector organisations and agreement on first point of contact (ie. LARAC, NAWDO, etc) | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ97 | A move towards consistency of IT use | Could have | requires further discussion with |  | ICT
Place |  | Waste | WASTE-REQ98 | An understanding about how current trade waste contracts could possibly be transferred to CWM | Could have |  | requires further discussion with | Strategic Commissioning
Place |  | Waste | WASTE-REQ98 | An understanding about how current trade waste contracts could possibly be transferred to CWM | Could have |  | requires support from | Legal & Democratic Services
Place |  | Waste | WASTE-REQ99 | Standardised H&S procedures e.g. near misses, gate checks, seat belt checks, crew engagement, safety reps | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ100 | ICT – access to Scada system for closed landfill | Could have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ101 | What will permit scheme look like? Pedestrian and Annual Permits? | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ102 | Policies - Existing policies transfer by area. Some policies could have been aligned (closed lid, side waste, lane end). | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ103 | Processes - Some processes could be aligned (assisted collections, requests for larger bins). | Could have |  |  |  | No detail provided
Place |  | Waste | WASTE-REQ104 | National Waste Strategy - Depends on timing of announcement and required actions. | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ105 | Re-branding of PPE - Some could have been done. Potential for hybrid clothing (SLDC fleece, WaF coat etc). | Could have | requires further discussion with |  | Communications and Engagement
Place |  | Waste | WASTE-REQ106 | Agreed position towards membership of national sector organisations and agreement on first point of contact (ie. LARAC, NAWDO, etc) | Could have |  |  |  | No detail provided
Place |  | Waste | WASTE-REQ107 | H&S and Performance, how that is monitored within Westmorland and Furness | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ108 | Awareness training for all waste service employees | Could have | requires support from |  | HR & OD | Assets
Place |  | Waste | WASTE-REQ109 | Environment Agency Permit transfer/UU discharge consents to legal entity (is there a requirement to apply or is this covered by the SCO?) | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ110 | Ability to pay EA subsistence fees for closed landfill from 01 April 2023 | Could have |  | requires support from | Finance
Place |  | Waste | WASTE-REQ110 | Ability to pay EA subsistence fees for closed landfill from 01 April 2023 | Could have |  | requires further discussion with | Strategic Commissioning
Place |  | Waste | WASTE-REQ111 | DCF registration – currently CWM | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ112 | Approach to branding strategy to be agreed and position on Performance Framework to be set out (eg how long CCC branding can remain in place before deductions apply) signs and PPE for site operatives | Could have |  | requires further discussion with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ112 | Approach to branding strategy to be agreed and position on Performance Framework to be set out (eg how long CCC branding can remain in place before deductions apply) signs and PPE for site operatives | Could have |  | developed together with | Customer & Digital
Place |  | Waste | WASTE-REQ113 | Agreement on paying royalty/rents – currently sitting with waste team | Could have | requires further discussion with |  | Finance
Place |  | Waste | WASTE-REQ114 | New authorities to brief CWM site operatives – clear and unambiguous message about what the changes mean for the HWRC sites and customers | Could have |  | requires further discussion with | HR & OD
Place |  | Waste | WASTE-REQ114 | New authorities to brief CWM site operatives – clear and unambiguous message about what the changes mean for the HWRC sites and customers | Could have |  | developed together with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ115 | Commercial gate fees to be agreed with new authorities (currently only Copeland and Allerdale) | Could have | requires further discussion with |  | Finance
Place |  | Waste | WASTE-REQ116 | Agreement on policies eg charities, side waste | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ117 | Schedule of assets for the new authorities (MBT, HWRC, closed landfill) | Could have | requires support from |  | Workstream - Assets | Assets
Place |  | Waste | WASTE-REQ118 | ICT – access to Scada system for closed landfill | Could have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ119 | What will permit scheme look like? Pedestrian and Annual Permits? | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ119 | What will permit scheme look like? Pedestrian and Annual Permits? | Could have |  | has a connection with | Customer & Digital
Place |  | Waste | WASTE-REQ120 | Consistency in service standards | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ121 | Consistency in service design | Won't have | requires further discussion with |  | Waste | Assets
Place |  | Waste | WASTE-REQ122 | Consistency towards commercial waste collections | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ123 | Waste and Recycling policy alignment | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ124 | Consistency in collection frequency | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ125 | Consistency in container type and size | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ126 | Depot rationalisation/location | Won't have |  | requires support from | Workstream - Assets | Assets
Place |  | Waste | WASTE-REQ126 | Depot rationalisation/location | Won't have |  | developed together with | Waste | Assets
Place |  | Waste | WASTE-REQ127 | Re-routing and re-rounding following removal of boundaries | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ128 | Efficient direct delivery from the North of Allerdale to Hespin Wood but could have! | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ129 | Decision on in-house v LATCo model | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ130 | Opportunity to rationalise/standardise Bring Banks | Won't have | requires support from |  | Waste
Place |  | Waste | WASTE-REQ131 | Consistency in service standards | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ132 | Consistency in service design | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ133 | Consistency towards commercial waste collections | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ134 | Re-branding of bins & boxes - Not urgent, can be done as new items, bins etc are ordered. | Won't have | requires support from |  | Communications & Engagement
Place |  | Waste | WASTE-REQ134 | Re-branding of vehicles - Not urgent, can be done as new vehicles are ordered or as prioritised. | Won't have | requires support from |  | Communications & Engagement
Place |  | Waste | WASTE-REQ135 | In-cab systems - Too complex to introduce by day 1. | Won't have | requires further discussion with |  | ICT
Place |  | Waste | WASTE-REQ136 | Round changes - Any round or route changes must be embedded by December 2022. | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ137 | Waste and Recycling Policy alignment and Consistency in collection frequency and containers | Won't have | requires further discussion with |  | Waste | Assets
Place |  | Waste | WASTE-REQ138 | Reviewed Bring Sites within Westmorland and Furness | Won't have | requires further discussion with |  |  | Assets
Place |  | Waste | WASTE-REQ139 | Agreement on enforcement powers, eg suspected trade waste abuse at HWRCs | Won't have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ140 | New HWRC permit scheme | Won't have | requires further discussion with |  | Strategic Commissioning
Place |  | Climate Change/Net Zero | CLIMATE-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have | developed together with | developed together with | Planning and Building Control |  |  | Summer 2022
Place |  | Climate Change/Net Zero | CLIMATE-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have |  |  | Street Scene and Open Spaces |  |  | Summer 2022
Place |  | Climate Change/Net Zero | CLIMATE-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have |  |  | Community/Localism
Place |  | Climate Change/Net Zero | CLIMATE-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have |  |  | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ2 | Officer to work on Annual Status Report (Due to be submitted to DEFRA by June) | Must have | requires support from | requires support from | Legal & Democratic Services |  |  | By June 2023
Place |  | Climate Change/Net Zero | CLIMATE-REQ2 | Officer to work on Annual Status Report (Due to be submitted to DEFRA by June) | Must have | requires support from | requires support from | Street Scene and Open Spaces
Place |  | Climate Change/Net Zero | CLIMATE-REQ2 | Officer to work on Annual Status Report (Due to be submitted to DEFRA by June) | Must have | requires support from | requires support from | Public Health
Place |  | Climate Change/Net Zero | CLIMATE-REQ2 | Officer to work on Annual Status Report (Due to be submitted to DEFRA by June) | Must have | requires support from | requires support from | Public Protection
Place |  | Climate Change/Net Zero | CLIMATE-REQ3 | ACB Arrangements for existing projects and supporting resources - check acronym | Must have | [5 empty] | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ4 | Formal Grant Agreement and funding arrangements have been transferred eg Account Body Status | Must have | requires further discussion with | Legal & Democratic Services | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ4 | Formal Grant Agreement and funding arrangements have been transferred eg Account Body Status | Must have | requires further discussion with |  | Finance |  |  | 2023-04-02
Place |  | Climate Change/Net Zero | CLIMATE-REQ4 | Formal Grant Agreement and funding arrangements have been transferred eg Account Body Status | Must have | requires further discussion with |  | Grants Portfolio |  |  | 2023-04-03
Place |  | Climate Change/Net Zero | CLIMATE-REQ4 | Formal Grant Agreement and funding arrangements have been transferred eg Account Body Status | Must have | requires further discussion with |  | Contract Management/Monitoring |  |  | 2023-04-04
Place |  | Climate Change/Net Zero | CLIMATE-REQ5 | Policy in place to ensure compliance with current legislation eg Environment Act 2021 Requirements - incl Biodiversity Net Gain | Must have |  | requires support from | Policy Framework |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ5 | Policy in place to ensure compliance with current legislation eg Environment Act 2021 Requirements - incl Biodiversity Net Gain | Must have |  | requires support from | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ6 | Staffing and financial resource to ensure requirements can be met | Must have |  | is dependant on as a precursor | HR & OD |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ6 | Staffing and financial resource to ensure requirements can be met | Must have |  | is dependant on as a precursor | Finance
Place |  | Climate Change/Net Zero | CLIMATE-REQ7 | Flood and Water Management Act - Lead Local Flood Authority | Must have | requires further discussion with |  | Highways |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ8 | Robust Climate Risk Assessment | Must have |  | developed together with | Risk Management & Business Continuity |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ8 | Robust Climate Risk Assessment | Must have |  | developed together with | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ9 | Procurement policy covering social value incl Environmental Stability (PPN 06/20, 06/21, Social Value Act) | Must have |  | requires further discussion with | Strategic Procurement / Strategy​ |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ9 | Procurement policy covering social value incl Environmental Stability (PPN 06/20, 06/21, Social Value Act) | Must have |  | requires further discussion with | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ10 | Sustainability assessment of planning decisions | Must have |  | developed together with | Planning and Building Control |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ10 | Sustainability assessment of planning decisions | Must have |  | developed together with | Housing
Place |  | Climate Change/Net Zero | CLIMATE-REQ11 | Coast Protection Authorities and Coastal Erosion Risk Management Authorities | Must have | developed together with |  | Highways |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ12 | Civil Contingencies Act 2004 - dealing with emergencies (Community Risk Register) | Must have | is dependant on as a precursor |  | Resilience and Emergency Planning |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ13 | Assurance that LGR Programme interdependencies with cross-cutting themes are managed (eg via climate impact assessment) | Must have | is dependant on as a precursor |  | All services - all line managers |  |  | Now onwards
Place |  | Climate Change/Net Zero | CLIMATE-REQ14 | Net Zero target | Should have |  | requires further discussion with | All services - all line managers |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ14 | Net Zero target | Should have |  | requires further discussion with | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ14 | Net Zero target | Should have |  | requires further discussion with | Transformation & Change Management
Place |  | Climate Change/Net Zero | CLIMATE-REQ15 | Route map for compliance with Climate Change Act - Net Zero by 2037/2049 | Should have |  | requires further discussion with | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ15 | Route map for compliance with Climate Change Act - Net Zero by 2037/2050 | Should have |  | requires further discussion with | Transformation & Change Management |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ16 | Clear links with partnerships | Should have |  | developed together with | Community/Localism |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ16 | Clear links with partnerships | Should have |  | developed together with | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ17 | Strategy: Action Plan for Climate Change, Environment and Biodiversity | Should have |  | requires further discussion with | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ17 | Strategy: Action Plan for Climate Change, Environment and Biodiversity | Should have |  | requires further discussion with | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ18 | Adaptation strategy and plan | Should have |  | requires support from | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ18 | Adaptation strategy and plan | Should have |  | requires support from | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ19 | Procurement policy that priorities Climate/Sustainability above mandatory levels | Should have | is dependant on as a precursor |  | Strategic Procurement / Strategy​ |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ20 | Climate Data monitoring | Should have | requires further discussion with |  | Performance & Business Intelligence |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ20 | Climate Governance - Board, Steering Group | Should have | is dependant on as a precursor |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ20 | Climate Governance - Board, Steering Group | Should have | is dependant on as a precursor |  | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ21 | Local Energy strategy | Should have |  | requires further discussion with | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ21 | Local Energy strategy | Should have |  | requires further discussion with | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ21 | Local Energy strategy | Should have |  | requires further discussion with | Capital Programme
Place |  | Climate Change/Net Zero | CLIMATE-REQ21 | Local Energy strategy | Should have |  | requires further discussion with | Economic Development
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Long term financial plan for mitigation and adaptation | Should have | is dependant on as a precursor |  | Finance |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Internal climate change action plan (emissions reduction etc) linked to Corporate KPIs | Should have |  | requires further discussion with | Policy Framework |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Internal climate change action plan (emissions reduction etc) linked to Corporate KPIs | Should have |  | requires further discussion with | All services - all line managers |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Biodiversity to be integrated to work stream and corporate priorities | Should have | developed together with |  | All services - all line managers |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Key expert staff in place around climate change, biodiversity, decarbonisation | Should have | requires support from |  | HR & OD |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ23 | Assessment of climate and ecological implications of key decisions | Should have |  | requires further discussion with | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ23 | Assessment of climate and ecological implications of key decisions | Should have |  |  | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ23 | Website - information for public on climate change, links to strategies, carbon footprint etc | Should have | requires further discussion with |  | Communications and Engagement |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ24 | Stakeholder Engagement Plan | Should have | requires further discussion with |  | Communications and Engagement |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ24 | Stakeholder Engagement Plan | Should have | requires further discussion with |  | Community/Localism
Place |  | Climate Change/Net Zero | CLIMATE-REQ25 | Budget (for Climate Communication, projects community engagement) | Should have | is dependant on as a precursor |  | Finance |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ26 | Climate Comms Strategy | Should have | requires further discussion with |  | Communications and Engagement |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ27 | HR Policies (eg recruitment, performance training) linked to sustainability | Should have | requires further discussion with |  | HR & OD |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ28 | Declaration of Climate Emergency | Could have | has a connection with |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ29 | Climate Champions in all different services within new authorities | Could have | requires further discussion with |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ30 | Retain successful council partnerships | Could have | requires further discussion with |  | Community/Localism |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ31 | Carbon literacy training to be implemented in induction for staff | Could have | requires further discussion with |  | Learning & Development |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ32 | Nominations to existing external partnerships (eg ZCCP) | Could have | developed together with |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ33 | Carbon accounting methodology and mechanisms | Could have | developed together with |  | Performance & Business Intelligence
Place |  | Climate Change/Net Zero | CLIMATE-REQ34 | Adaptation strategy and plan - duplication (also down as Should Have) | Could have |  |  | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ35 | Net Zero Operational target (also down as Should Have) | Could have |  |  | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ36 | Net Zero geographical target (does this differ from above?) | Could have |  |  | Policy Framework |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ37 | Memberships (APSE etc) | Could have | developed together with |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ38 | Net Zero software / tool | Could have | developed together with |  | Performance & Business Intelligence |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ39 | Clear roles and responsibilities to ensure delivery | Could have | is dependant on as a precursor |  | HR & OD |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ40 | Net Zero Skills audits | Could have | is dependant on as a precursor |  | Learning & Development |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ41 | Budgets for consultants | Could have |  | is dependant on as a precursor | Finance |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ41 | Budgets for consultants | Could have |  | is dependant on as a precursor | Highways
Place |  | Climate Change/Net Zero | CLIMATE-REQ41 | Budgets for consultants | Could have |  | is dependant on as a precursor | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ42 | Electric Vehicle transition / infrastructure plan | Could have |  | developed together with | Fleet
Place |  | Climate Change/Net Zero | CLIMATE-REQ42 | Electric Vehicle transition / infrastructure plan | Could have |  | developed together with | Transport
Place |  | Climate Change/Net Zero | CLIMATE-REQ43 | Net Zero operational emissions | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ44 | Council-owned energy company | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ45 | Community energy ownership schemes | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ46 | Mechanisms for non-financial climate and nature related disclosures | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ47 | Ability to achieve Net Zero by 2037 (ie budget, resources, policies etc) | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ48 | Sufficient resources or budget to address climate and nature crises urgently enough | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ49 | Low carbon affordable mobility strategy | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ50 | Robust and funded active travel infrastructure | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ51 | Internal biodiversity net gain principle for council projects | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ52 | Carbon Accounting (duplication - also down as Could Have) | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ53 | Tree Planting target | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ54 | Updated Local Plan - sustainability embedded into policies | Won't have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ1 | Budgets & managing performance within departments, approval limits established, performance reporting in place | Must Have | is reliant upon decisions being made by and requires support from |  | Finance
Place |  | Housing | HOUSE-REQ2 | Out Of Hours Service | Must Have |  | Place Theme - Housing | requires support from
Place |  | Housing | HOUSE-REQ2 | Out Of Hours Service | Must Have |  | is reliant upon decisions being made by and requires support from | Housing
Place |  | Housing | HOUSE-REQ3 | Out Of Hours Service | Must Have |  | is reliant upon decisions being made by and requires support from | HR & OD
Place |  | Housing | HOUSE-REQ4 | Out Of Hours Service | Must Have |  | is reliant upon decisions being made by and requires support from | ICT
Place |  | Housing | HOUSE-REQ5 | Out Of Hours Service | Must Have |  | is reliant upon decisions being made by and requires support from | Customer & Digital
Place |  | Housing | HOUSE-REQ6 | Branded Website with links and Duty to Refer emails | Must Have |  | Requires support from | ICT
Place |  | Housing | HOUSE-REQ6 | Branded Website with links and Duty to Refer emails | Must Have |  | developed together with | Customer & Digital
Place |  | Housing | HOUSE-REQ6 | Branded Website with links and Duty to Refer emails | Must Have |  | developed together with | Communications and Engagement
Place |  | Housing | HOUSE-REQ7 | Fees & Charges should align | Must Have | is reliant upon decisions being made by |  | Finance
Place |  | Housing | HOUSE-REQ7 | Essential standard policies for statutory services, e.g. DFG | Must Have | is reliant upon decisions being made by |  | Strategic Commissioning
Place |  | Housing | HOUSE-REQ8 | Essential standard policies for statutory services, e.g. DFG | Must Have |  | developed together with | Finance
Place |  | Housing | HOUSE-REQ9 | Essential standard policies for statutory services, e.g. DFG | Must Have |  | developed together with | Public Protection
Place |  | Housing | HOUSE-REQ10 | Essential standard policies for statutory services, e.g. DFG | Must Have |  | developed together with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ11 | IT relevant to service - Locata. Flare, Civica CBL, Northgate, Idox, Anite, Info at work, Civicare, HIA foundations case manager, Abavus my council services, Ferret, Case management systems. Flare is needed but may not be fuctioning by vesting day. | Must have |  | developed together with | ICT
Place |  | Housing | HOUSE-REQ11 | IT relevant to service - Locata. Flare, Civica CBL, Northgate, Idox, Anite, Info at work, Civicare, HIA foundations case manager, Abavus my council services, Ferret, Case management systems. Flare is needed but may not be fuctioning by vesting day. | Must have |  | requires support from | Customer & Digital
Place |  | Housing | HOUSE-REQ12 | IT relevant to service - Locata. Flare, Civica CBL, Northgate, Idox, Anite, Info at work, Civicare, HIA foundations case manager, Abavus my council services, Ferret, Case management systems. Flare is needed but may not be fuctioning by vesting day. | Must have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ13 | Branding, name badges and ID for stat visits | Must Have | requires support from |  | Communications and Engagement
Place |  | Housing | HOUSE-REQ14 | Core Support Services such as: Finance, Business Support, Legal, HR & IT. Able to recruit. | Must Have | requires support from |  | All services - all employees
Place |  | Housing | HOUSE-REQ14 | Core Support Services such as: Finance, Business Support, Legal, HR & IT. Able to recruit. | Must Have |  | developed together with | Finance
Place |  | Housing | HOUSE-REQ14 | Core Support Services such as: Finance, Business Support, Legal, HR & IT. Able to recruit. | Must Have |  | developed together with | ICT
Place |  | Housing | HOUSE-REQ14 | Core Support Services such as: Finance, Business Support, Legal, HR & IT. Able to recruit. | Must Have |  | developed together with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ15 | Supported Accomodation Contract/Grant Agreements | Must Have | requires support from |  | Strategic Commissioning
Place |  | Housing | HOUSE-REQ15 | Supported Accomodation Contract/Grant Agreements | Must Have |  | developed together with | HR & OD
Place |  | Housing | HOUSE-REQ15 | Supported Accomodation Contract/Grant Agreements | Must Have |  | developed together with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ16 | Contractor relationships and processes need to continue for day one. | Must Have | is reliant upon decisions being made by |  | Strategic Commissioning
Place |  | Housing | HOUSE-REQ16 | Contractor relationships and processes need to continue for day one. | Must Have | is reliant upon decisions being made by | is reliant upon decisions being made by |  | People -Adults
Place |  | Housing | HOUSE-REQ17 | DA Crisis contact numbers | Must Have | requires further discussion with | Communications & Engagement | developed together with
|  | Housing | HOUSE-REQ18 | CBL Fully operational | Must Have |  | requires support from | Strategic Commissioning
|  | Housing | HOUSE-REQ18 | CBL Fully operational | Must Have |  | requires support from | ICT
Place |  | Housing | HOUSE-REQ18 | CBL Fully operational | Must Have |  | requires support from | developed together with
Place |  | Housing | HOUSE-REQ19 | Consitution for Officers delegations | Must Have |  | is reliant upon decisions being made by | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ19 | Consitution for Officers delegations | Must Have |  | is reliant upon decisions being made by | ICT
Place |  | Housing | HOUSE-REQ19 | Consitution for Officers delegations | Must Have |  | is reliant upon decisions being made by | Customer & Digital
Place |  | Housing | HOUSE-REQ20 | Customers can dial in and email, self serve on day 1 - different legacy council has different triage proesses and that needs to be maintained for day 1 | Must Have | requires support from |  | Communications & Engagement
Place |  | Housing | HOUSE-REQ21 | Executive functions to take reports | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ21 | Executive functions to take reports | Must Have |  | is interdependent with | Finance - Benefit Realisation
Place |  | Housing | HOUSE-REQ21 | Executive functions to take reports | Must Have |  | is interdependent with | ICT
Place |  | Housing | HOUSE-REQ22 | DFG funding payments, approvals, financial delegations. | Must Have | requires support from |  | Finance
Place |  | Housing | HOUSE-REQ22 | DFG funding payments, approvals, financial delegations. | Must Have |  | is interdependent with | Communications and Engagement
Place |  | Housing | HOUSE-REQ22 | DFG funding payments, approvals, financial delegations. | Must Have |  | is interdependent with | Community/Localism
Place |  | Housing | HOUSE-REQ22 | DFG funding payments, approvals, financial delegations. | Must Have |  | is interdependent with | Public Protection
Place |  | Housing | HOUSE-REQ23 | Process for dealing with homeless appeals / approvals | Must Have |  | is reliant upon decisions being made by | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ24 | Process for dealing with homeless appeals / approvals | Must Have |  | is interdependent with | Finance
Place |  | Housing | HOUSE-REQ25 | Green homes grant structures / team | Must Have | is reliant upon decisions being made by |  | Finance
Place |  | Housing | HOUSE-REQ25 | Green homes grant structures / team | Must Have | is reliant upon decisions being made by | is interdependent with | ICT
Place |  | Housing | HOUSE-REQ26 | Government delta returns & HCLIC need to be possible. (Flag discussion around aggregation of returns for new council). | Must Have | requires support from | ICT - Service Continuity | ICT - Service Continuity
Place |  | Housing | HOUSE-REQ26 | Government delta returns & HCLIC need to be possible. (Flag discussion around aggregation of returns for new council). | Must Have | requires support from |  | Adults
Place |  | Housing | HOUSE-REQ26 | Government delta returns & HCLIC need to be possible. (Flag discussion around aggregation of returns for new council). | Must Have |  |  | ICT
Place |  | Housing | HOUSE-REQ26 | Government delta returns & HCLIC need to be possible. (Flag discussion around aggregation of returns for new council). | Must Have |  |  |  | Children
Place |  | Housing | HOUSE-REQ27 | procedure for referrals from OTs and Health absed childrens OT need to be agreed and tested | Must Have | is reliant upon decisions being made by |  | Public Health
Place |  | Housing | HOUSE-REQ27 | procedure for referrals from OTs and Health absed childrens OT need to be agreed and tested | Must Have |  | is interdependent with | Communications and Engagement
Place |  | Housing | HOUSE-REQ27 | procedure for referrals from OTs and Health absed childrens OT need to be agreed and tested | Must Have |  | is interdependent with | ICT
Place |  | Housing | HOUSE-REQ28 | Training on day 1 changes for the teams | Must Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ40 | Training on day 1 changes for the teams |  |  | is interdependent with | Public Health
Place |  | Housing | HOUSE-REQ40 | Training on day 1 changes for the teams |  |  | is interdependent with | Public Protection
Place |  | Housing | HOUSE-REQ40 | Training on day 1 changes for the teams |  |  | is interdependent with | Community/Localism
Place |  | Housing | HOUSE-REQ41 | Service for homeless families to assess applications and be able to provide temp accomodation and wider support for children/safeguarding process | Must Have | requires support from |  |  | People Theme - Childrens and Families
Place |  | Housing | HOUSE-REQ41 | Service for homeless families to assess applications and be able to provide temp accomodation and wider support for children/safeguarding process | Must Have | requires support from |  | Customer & Digital
Place |  | Housing | HOUSE-REQ42 | Landlord functions and Urgent response for Council tenants (e.g. repairs). Where there are districts providing Landlord services, standards and policies need to be aligned for Day 1. | Must Have | requires support from |  | Communications and Engagement
Place |  | Housing | HOUSE-REQ43 | Procedures, hand off points between teams etc | Should Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ43 | Procedures, hand off points between teams etc | Should Have |  | is interdependent with | Finance
Place |  | Housing | HOUSE-REQ44 | Procedures, hand off points between teams etc | Should Have |  | is interdependent with |  | Workstream - Assets
Place |  | Housing | HOUSE-REQ45 | Procedures, hand off points between teams etc | Should Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ46 | Procedures, hand off points between teams etc | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ47 | Premises to operate from and teams in place in each service area to meet service demand. | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ47 | Premises to operate from and teams in place in each service area to meet service demand. | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ48 | Plans to identify existing contracts and how to align, novate etc | Should Have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ54 | Plans to identify existing contracts and how to align, novate etc | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ54 | Plans to identify existing contracts and how to align, novate etc | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ55 | Identifying non priority Policies and plan to review these and timescale | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ56 | Revised Constitution | Should Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ57 | Identify areas that may need new procurement | Should Have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ57 | Identify areas that may need new procurement | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ58 | A plan to align relevant Strategies, e.g. Housing Strategy - what will the priorities be? | Should Have | Requires discussion with |  | Strategic Commissioning
Place |  | Housing | HOUSE-REQ59 | Plan to review partnerships | Should Have |  | requires support from | Communications and Engagement
Place |  | Housing | HOUSE-REQ59 | Plan to review partnerships | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ60 | Effective policies for DFGs, HHSRS and HMOs | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ61 | Local Plan policies in place | Should Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ62 | Identitly of new teams and processes to manage them effectively | Should Have |  | developed together with | HR & OD
Place |  | Housing | HOUSE-REQ62 | Identitly of new teams and processes to manage them effectively | Should Have |  | requires support from | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ63 | review HIA, options going forward. :better homes agency" | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ64 | funding agreements, LAD, domestic abuse | Should Have | requires support from |  | Finance | Cross cutting theme - Financial Sustainability and Benefits Realisation
Place |  | Housing | HOUSE-REQ65 | Direcction of travel for aligning Planning Policies | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ66 | internal procedures, reviewed. process based. | Should Have |  | requires support from | Finance
Place |  | Housing | HOUSE-REQ66 | internal procedures, reviewed. process based. | Should Have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ67 | updated letterheads,licence docs, offcial paperwork to the customer | Should Have |  | requires further discussion with | ICT
Place |  | Housing | HOUSE-REQ67 | updated letterheads,licence docs, offcial paperwork to the customer | Should Have |  | developed together with | Communications and Engagement
Place |  | Housing | HOUSE-REQ68 | started to review staffing and roles, Job Descriptions | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ69 | Analysis of which partnerships are still required and new partnershps needed | Should Have |  | requires further discussion with | Communications and Engagement
Place |  | Housing | HOUSE-REQ70 | Clear guidelines and timelines for staff on emerging structures still not in place | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ71 | identify policies that are required and considered to approval at new Executive | Should Have |  | requires support from | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ71 | identify policies that are required and considered to approval at new Executive | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ72 | review IT systems, not common accross and consider options. | Should Have | requires support from |  | ICT
Place |  | Housing | HOUSE-REQ73 | consolidation of some policy. updated to improve services | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ74 | Common Quality Standards | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ75 | Staff training programme in place and rolling out to embedd new culture, policies changes, new IT, workarounds etc | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ75 | Staff training programme in place and rolling out to embedd new culture, policies changes, new IT, workarounds etc | Should Have |  | requires support from | ICT
Place |  | Housing | HOUSE-REQ76 | Clear decision making and escalation routes | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ76 | Clear decision making and escalation routes | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ77 | streamine none day 1 critical policy and process for discretionary activity so no postcode lottery | Should Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ78 | Plans around HIA development and timeline | Should Have | requires support from |  | ICT
Place |  | Housing | HOUSE-REQ79 | Streamlined Homelessness and Housing Strategies Private sector Housing Grants policies | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ80 | review of policies and procedures, KPI's/monitoring frameworks partner agencies arrangements | Should Have |  | requires further discussion with | Communications and Engagement
Place |  | Housing | HOUSE-REQ80 | review of policies and procedures, KPI's/monitoring frameworks partner agencies arrangements | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ81 | team management lines for comms, 1-1s, team meetings in place | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ82 | Staff training programmes, appraisal processes agreed | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ83 | full team | Should Have | is reliant upon decisions being made by |  | HR & OD
Place |  | Housing | HOUSE-REQ84 | internal policies/training for colleagues ie GDPR, safeguarding, E&D, new LA priorities | Should Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ85 | Partnerships reviewed and resstrucutred eg Cumbria Housing Group (and subgroups) and the Social Landlord/LA group plus agree what is happening with local partnerships | Should Have |  | requires further discussion with | Communications and Engagement
Place |  | Housing | HOUSE-REQ85 | Partnerships reviewed and resstrucutred eg Cumbria Housing Group (and subgroups) and the Social Landlord/LA group plus agree what is happening with local partnerships | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ86 | team know who to report to if different to current arrangments | Should Have | requires further discussion with |  | HR & OD
Place |  | Housing | HOUSE-REQ87 | appraisals and training plans & priorities of the new council, to aid delivery | Should Have |  |  | HR & OD
Place |  | Housing | HOUSE-REQ88 | Strategic partnerships | Could Have |  | requires support from | Communications and Engagement
Place |  | Housing | HOUSE-REQ88 | Strategic partnerships | Could Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ89 | Strategic housing priorities | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ102 | Integrated DFG team with OTs, etc | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ103 | Alignment of contracts - Locata | Could Have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ103 | Alignment of contracts - Locata | Could Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ104 | Consistent template agreements, e.g. grants etc | Could Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ105 | Some alignment of key policies | Could Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ106 | One service team across the whole LA, ie homelessness | Could Have | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ107 | MDT of colleagues dealing with DFG's - OT's, Asc, HIA | Could Have
Place |  | Housing | HOUSE-REQ108 | Working partnership groups with Rp,s developers, Vol sector, | Could Have |  | requires support from | Communications & Engagement
Place |  | Housing | HOUSE-REQ108 | Working partnership groups with Rp,s developers, Vol sector, | Could Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ109 | Align the HoC properties with BBC housing stock to be managed inhouse | Could Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ110 | Model for delivering Green Homes/sustainable warnth & bididng for new fundign opportunities | Could Have | requires further discussion with |  | Finance
Place |  | Housing | HOUSE-REQ111 | Domestic Abuse strategy | Could Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ112 | settled teams who all know their own roles/responsibilities | Could Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ113 | Local Housing Company | Could Have | requires support from |  | Communications & Engagement
Place |  | Housing | HOUSE-REQ114 | Shared contracts in place for DFGs, ECO | Could Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ115 | A model for a new HIA or Better Homes Agency | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ116 | Started work around joint working polcies, practices | Could Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ116 | Started work around joint working polcies, practices | Could Have |  | requires support from | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ117 | Rebranding of Officer equipment, letters, communication | Could Have |  | requires support from | Communications & Engagement
Place |  | Housing | HOUSE-REQ117 | Rebranding of Officer equipment, letters, communication | Could Have |  | developed together with | ICT
Place |  | Housing | HOUSE-REQ118 | Started to look at Intergration of DFG within ASC | Could Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ119 | Uniformed Services for Homeless Services, Housing Asssitance, tenancy advocacy | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ120 | empty homes strategy in plae for each unitary | Could Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ121 | Integrated needs assessment for complex cases ASC/Homelessness/DFGs etc | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ122 | acess to data within east and west so staff can cover all areas not jsut legalcy footprint and provide OOH effectively | Could Have | requires support from |  | ICT
Place |  | Housing | HOUSE-REQ123 | Integrated OT/DFG teams | Could Have | is reliant upon decisions being made by |  | HR & OD
Place |  | Housing | HOUSE-REQ124 | HIA for each new Unitary | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ125 | one OOH shared system integrated with Social Care duty teams | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ126 | shared budgets for homeless prevention | Could Have |  | requires support from | Finance
Place |  | Housing | HOUSE-REQ126 | shared budgets for homeless prevention | Could Have |  | developed together with |  | Cross cutting theme - Financial Sustainability and Benefits Realisation
Place |  | Housing | HOUSE-REQ127 | LHC registered and linking with econmic regen plans | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ128 | Social Care white paper delivery/transition plan | Could Have | requires further discussion with |  | Public Health
Place |  | Housing | HOUSE-REQ129 | One DFG service/meanstesting/ top ups etc | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ130 | Every strategy related not likely to be in place. | Won't Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ131 | All contracts aligned. | Won't Have |  | requires support from | Strategic Commisssioning
Place |  | Housing | HOUSE-REQ131 | All contracts aligned. | Won't Have |  | developed together with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ132 | Aligned evidence base, e.g. stock condition survey or other evidence supporting strategic development - homeless reviews | Won't Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ133 | Consistent approach/funding opportunities in some areas, e.g. empty homes | Won't Have | requires support from |  | Finance
Place |  | Housing | HOUSE-REQ134 | Definitive operating model | Won't Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ135 | new team/structure in place, forums/working groups/partnerships | Won't Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ135 | new team/structure in place, forums/working groups/partnerships | Won't Have |  | requires further discussion with | Communications and Engagement
Place |  | Housing | HOUSE-REQ136 | One Team - all speaking with one voice | Won't Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ137 | all the necessary policies/procedures in place and/or aligned | Won't Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ138 | same team structure across the LA | Won't Have | requires further discussion with |  | HR & OD
Place |  | Housing | HOUSE-REQ139 | budgets | Won't Have | requires support from |  | Finance
Place |  | Housing | HOUSE-REQ140 | a new vision/culture - YET | Won't Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ141 | aligned pay/conditions | Won't Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ142 | aligned pay/conditions | Won't Have |  | developed together with | Finance
Place |  | Housing | HOUSE-REQ143 | settled teams/colleagues | Won't Have | developed together with |  | HR & OD
Place |  | Housing | HOUSE-REQ144 | job descriptions/role profiles consistent | Won't Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ145 | All new teams and systems in place | Won't Have |  | requires support from | HR & OD
|  | Housing | HOUSE-REQ145 | All new teams and systems in place | Won't Have |  | developed together with | ICT
|  | Housing | HOUSE-REQ145 | All new teams and systems in place | Won't Have |  | developed together with | Finance
Place |  | Housing | HOUSE-REQ146 | Consistent approach to Officers decisions, autonomy | Won't Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ147 | Shared IT systems for areas of work, specific to work area. FLARE, CASE MANAGER | Won't Have | requires support from |  | ICT |  |  |  | ICT - Infrastructure
Place |  | Housing | HOUSE-REQ148 | Culture change, Carlisle works on three C's | Won't Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ149 | Shared department budgets, equipment, training, resources | Won't Have |  | developed together with | Finance
Place |  | Housing | HOUSE-REQ149 | Shared department budgets, equipment, training, resources | Won't Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ149 | Shared department budgets, equipment, training, resources | Won't Have |  | requires support from | ICT
Place |  | Housing | HOUSE-REQ150 | VR on the table around staffing | Won't Have | is reliant upon decisions being made by |  | HR & OD
Place |  | Housing | HOUSE-REQ151 | Full commonality in response across the new area | Won't Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ152 | Fully intergated teams and structures | Won't Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ153 | Common contractual arrangements | Won't Have | requires support from |  | Strategic Commisssioning | No detail provided
Place |  | Planning and Building Control | PBC-REQ1 | Recurit and retain staff that will be situated within deliverable geographies across the new authorities | Must Have |  |  |  | No detail provided
Place |  | Planning and Building Control | PBC-REQ2 | New workable schemes of delegation adopted by the new authorities | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ3 | All local plans and supplementary planning documents to be adopted by new authorities | Must Have | has a connection with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ4 | LDS (Local Development Scheme) to be adopted by new authoirities | Must Have | has a connection with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ5 | Shadow authorities to decide committee structure in new authorities | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ6 | Shadow Authority Planning Committee Elections to take place and new chair appointed for both authorities | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ7 | Member training for Planning Committee for-both authorities | Must Have | developed together with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ8 | Street Naming and Numbering - Committee approval of SNN policy in both authorities | Must Have | has a connection with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ9 | Enforcement policies to be adopted by new authorities | Must Have | has a connection with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ10 | Agreed policy in regards to CIL / section 106 (South Lakeland has a CIL but no other authority has one) | Must Have |  | has a connection with | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ10 | Agreed policy in regards to CIL / section 106 (South Lakeland has a CIL but no other authority has one) |  |  | has a connection with | Finance
Place |  | Planning and Building Control | PBC-REQ11 | Pre-app policy to be adopted by the new authorities | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ12 | Functional IT systems for Building Control & Development Management | Must Have | is reliant upon decisions being made by |  | ICT
Place |  | Planning and Building Control | PBC-REQ13 | Access to historic planning records for buiding control, development management and minerals and waste | Must Have | is reliant upon decisions being made by |  | ICT
Place |  | Planning and Building Control | PBC-REQ14 | GIS systems | Must Have | has a connection with |  | ICT
Place |  | Planning and Building Control | PBC-REQ15 | New MoU for joint committees such as partnership boards | Must Have |  |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ16 | Appoint partnership members to AONB boards (Solway Coast, North Pennines & Arnside and Silverdale | Must Have | has a connection with
Place |  | Planning and Building Control | PBC-REQ17 | Statutory Planning Noties Policy needs to be cordinated | Should Have |  |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ18 | Approach to site notices needs to be cordinated | Should Have
Place |  | Planning and Building Control | PBC-REQ19 | Harmonised standard conditions for both authorities | Should Have
Place |  | Planning and Building Control | PBC-REQ20 | Harmonised validation procedures for both authorities | Should Have
Place |  | Planning and Building Control | PBC-REQ21 | Corporate Templates for notices, decisions, delgated reports & committee reports | Should Have | has a connection with
Place |  | Planning and Building Control | PBC-REQ22 | Committee Policy to be agreed (i.e. site visit policy) | Should Have | developed together with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ23 | A new centralised admin protocal for development management and building control in both authorities. These include inboxes and addresses for plannning and building control applications in the new authorities. | Could Have |  |  | ICT
Place |  | Planning and Building Control | PBC-REQ24 | Harmonised local plans for the new authorities | Won't Have | is reliant upon decisions being made by
Place |  | Planning and Building Control | PBC-REQ25 | A harmonised IT system for Development Management and Building Control in the new authorities | Won't Have | is reliant upon decisions being made by |  | ICT
Place |  | Planning and Building Control | PBC-REQ26 | A Harmonised GIS system for the new authorities | Won't Have | ICT - Infrastructure |  | ICT

## Day1 Reqs&Depends (Place) Old (hidden)
Day1 Requirements & Inter/Dependencies (Place)
|  |  |  | DEFINITIONS: |  |  |  | KEY FOR COMMENTS SECTION:
|  |  |  | Dependency: Reliance on just one other area to address requirement |  |  |  | Question about whether the workstream has been mapped correctly
|  |  |  | Interdependency: Reliance across multiple areas to address requirement |  |  |  | Remaining interdependencies that I cannot map / unsure about mapping to existing workstreams
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency (what is required from elsewhere in the programme?) | Interdependency (numerous interdependencies from elsewhere in the programme) | With | Comment | Date needed by | Approved?
Place |  | Waste | WASTE-REQ1 | Staff able to do the job, these will need contracts | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ2 | Be able to dispose of waste | Must have | developed together with |  | Fleet
Place |  | Waste | WASTE-REQ3 | Have appropriate vehicles that are under an O’Licence, insured | Must have | has a connection with |  | Transport
Place |  | Waste | WASTE-REQ4 | Have access to fuel | Must have | has a connection with |  | Finance
Place |  | Waste | WASTE-REQ5 | Be able to access routes and in cab data exchange | Must have | requires support from |  | ICT | Requires support from ICT - Service Continuity and ICT - Infrastructure
Place |  | Waste | WASTE-REQ6 | Customer interface in the way residents are used to contacting us now, this may require access to each-others’ systems | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ6 | Customer interface in the way residents are used to contacting us now, this may require access to each-others’ systems | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ7 | Essential outputs for householders (i.e. Collection calendars) | Must have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ8 | Clear lines of management / accountability and ability to redirect resources to support priority services eg from other operational services | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ9 | #NAME? | Must have | requires support from |  | Fleet
Place |  | Waste | WASTE-REQ10 | Officers authorised to place orders etc | Must have | developed together with |  | Finance
Place |  | Waste | WASTE-REQ11 | Team of staff empowered and confident to make decisions | Must have | developed together with |  | HR & OD
Place |  | Waste | WASTE-REQ12 | Hosted arrangement - Clear transfer of the services which would sit within Host Authority. Staffing, communication routes, Officer/Member governance confirmed. | Must have | requires support from |  | All services - all employees
Place |  | Waste | WASTE-REQ13 | Waste data collection and submission resourcing and arrangements confirmed (ie. WasteDataFlow). | Must have | developed together with |  | ICT
Place |  | Waste | WASTE-REQ14 | Governance Model | Must have | developed together with |  | All services - all employees
Place |  | Waste | WASTE-REQ15 | Duly appointed Shareholder Group for AWSL (Governance) and Partnering Board – a contractual requirement | Must have | developed together with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ16 | Methodology for valuing fuel stock for example as at 31/3/23 | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ17 | IT must work e.g. VPN, in-cab devices, | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ18 | DVLA to be advised of vehicle responsibility – Road Fund licence V5 – who will be responsible for taxing the vehicles 1/4/23 | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ19 | LOLER – bin lifts/tail lifts - are we using one supplier for Cumberland | Must have | requires further discussion with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ20 | Ability to check licences - internal or external | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ21 | Tachograph analysis – RHA/FTA | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ22 | Trade Waste Contracts assigned to Cumberland | Must have | developed together with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ23 | Contingency offtakers in Cumberland e.g. bulky waste to Barrow in the past | Must have
Place |  | Waste | WASTE-REQ24 | Decision on AWSL new name if any | Must have
Place |  | Waste | WASTE-REQ25 | Waste Carriers Licence currently in the name of AWSL | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ26 | An understanding about the ownership of CWM | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ27 | Scheme of financial delegation for officers | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ28 | AWSL, CWM and Tivoli (waste element) contracts assigned to Cumberland | Must have | requires further discussion with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ29 | Portfolio Holder in place | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ30 | Alignment on fees and charges | Must have | requires further discussion with |  | Finance
Place |  | Waste | WASTE-REQ31 | Staffing and therefore reporting structure to be in place | Must have | requires further discussion with |  | HR & OD
Place |  | Waste | WASTE-REQ32 | Cumberland branding on RCVs | Must have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ33 | Standardisation of Customer Service roles across Cumberland | Must have |  | requires support from | HR & OD
Place |  | Waste | WASTE-REQ33 | Standardisation of Customer Service roles across Cumberland | Must have |  | developed together with | Customer & Digital
Place |  | Waste | WASTE-REQ34 | Will Cumberland provide H&S advice to AWSL? | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ35 | Will Cumberland provide current SLA services to AWSL? | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ36 | Access to data – ICT systems/Sharepoint | Must have | requires support from |  | ICT | ICT developed with Service Continuity, Applications and Architecture
Place |  | Waste | WASTE-REQ37 | Waste, Green Waste & Recycling collections - Front-line services must happen on day one as they did in March 2022 | Must have | requires support from |  | All services - all employees
Place |  | Waste | WASTE-REQ38 | Vehicles must be legal & safe. Must be insured, serviced & MoT’d. | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ39 | Fuel - Fuel cards or supplies must be available for vehicles | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ40 | Insurance - Vehicles must be insured | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ41 | Vehicle Accident Packs - Must be up-dated with new insurance details etc | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ42 | Bring site emptying - Recycling banks must be emptied. | Must have
Place |  | Waste | WASTE-REQ43 | Waste disposal - Transfer Stations must be open and accepting materials | Must have | developed together with |  | HR & OD
Place |  | Waste | WASTE-REQ44 | Environmental Permits for Ecclerigg & Ulverston Waste Transfer Stations - Must be transferred to WandF. May be covered by the Change Order. Possible joint meeting with CCC, EDC, BBC & EA to resolve. | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ45 | Staff - We must have staff in place, paid, covered by insurance, qualified to do their jobs. | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ46 | Sickness & Holidays - Must be in place for non-desk-based staff. | Must have |  | requires support from | HR & OD
Place |  | Waste | WASTE-REQ46 | Sickness & Holidays - Must be in place for non-desk-based staff. | Must have |  | Requires futher dicussion with | Finance
Place |  | Waste | WASTE-REQ47 | Credit cards - As required, for emergency use. Possibly retain pre-WaF cards. | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ48 | IT systems - Laptops and phone must work. | Must have |  | requires support from | ICT | ICT developed with Service Continuity, Applications and Architecture
Place |  | Waste | WASTE-REQ48 | Software - Core MS Office systems must work. Content must have transferred. Any specific systems must work. | Must have |  | requires support from | ICT | ICT developed with Service Continuity, Applications and Architecture
Place |  | Waste | WASTE-REQ49 | Software - Core MS Office systems must work. Content must have transferred. Any specific systems must work. | Must have |  |  | Finance
Place |  | Waste | WASTE-REQ50 | Utilities - All depots & buildings must have gas, electric, water etc. | Must have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ50 | Utilities - All depots & buildings must have gas, electric, water etc. | Must have |  | requires support from | Finance
Place |  | Waste | WASTE-REQ51 | Payroll - Processes in place to pay staff and process overtime or other claims. | Must have |  | requires support from | HR & OD
Place |  | Waste | WASTE-REQ51 | Payroll - Processes in place to pay staff and process overtime or other claims. | Must have |  | developed together with | Finance
Place |  | Waste | WASTE-REQ52 | Communications - Staff and the public must know what is going on. May require access to each other's systems | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ52 | Communications - Staff and the public must know what is going on. May require access to each other's systems | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ53 | Website - Website content must be transferred & checked. Collection information (calendars) must be available. | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ53 | Website - Website content must be transferred & checked. Collection information (calendars) must be available. | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ54 | Processes - Systems must be in place to log missed collections, bin requests and queries; and allocate to the correct operational area. | Must have | requires support from |  | ICT | ICT developed with Service Continuity, Applications and Architecture
Place |  | Waste | WASTE-REQ55 | Bulky waste - Requests must be received and forwarded to the correct contractor. | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ55 | Bulky waste - Requests must be received and forwarded to the correct contractor. | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ56 | Clinical waste - Requests must be received and forwarded to the correct contractor. | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ56 | Clinical waste - Requests must be received and forwarded to the correct contractor. | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ57 | Hosted arrangement - Clear transfer of the services which would sit within Host Authority. Staffing, communication routes, Officer/Member governance confirmed. | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ58 | Waste data collection and submission resourcing and arrangements confirmed (ie. WasteDataFlow). | Must have | developed together with |  | ICT
Place |  | Waste | WASTE-REQ59 | Branded Calendars are essential from day one | Must have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ60 | Clear lines of Management and accountability – to be able to redirect resources if needed | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ61 | Waste Carrier License's | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ62 | Understanding ownership of CWM | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ63 | Contract assigned to a correct legal entity – mechanism to be agreed (legal advice required) | Must have |  | requires support from | Strategic Commissioning
Place |  | Waste | WASTE-REQ63 | Contract assigned to a correct legal entity – mechanism to be agreed (legal advice required) | Must have |  | developed together with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ64 | Authority representative to be agreed and Governance between Contractor and Authorities | Must have |  | requires support from | Legal & Democratic Services
Place |  | Waste | WASTE-REQ64 | Authority representative to be agreed and Governance between Contractor and Authorities | Must have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ65 | Up to date Authorised Vehicle List for new authorities – AVL to ensure no end dates of 31 March/April 2023 | Must have |  | requires support from | Fleet
Place |  | Waste | WASTE-REQ65 | Up to date Authorised Vehicle List for new authorities – AVL to ensure no end dates of 31 March/April 2024 | Must have |  | developed together with | Transport
Place |  | Waste | WASTE-REQ65 | Up to date Authorised Vehicle List for new authorities – AVL to ensure no end dates of 31 March/April 2025 | Must have |  | developed together with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ66 | New authorities to understand AVL procedure | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ67 | Agreed process for updating and issuing AVL (currently CCC Service Centre) | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ68 | Waste transfer notes for the 2 authorities | Must have | developed together with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ69 | Agreement on HWRC permit system – is it run by one authority or 2? | Must have |  | requires further discussion with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ70 | Agreement on use of HWRCs – can all residents use all sites in Cumberland and Westmorland and Furness? | Must have |  | requires support from |  | Assets
Place |  | Waste | WASTE-REQ70 | Agreement on use of HWRCs – can all residents use all sites in Cumberland and Westmorland and Furness? | Must have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ71 | Agree scope of Helpline and contact arrangements – confirm telephone number, training for helpline team. | Must have |  | requires support from | Strategic Commissioning
Place |  | Waste | WASTE-REQ71 | Agree scope of Helpline and contact arrangements – confirm telephone number, training for helpline team. | Must have |  | developed together with | Customer & Digital
Place |  | Waste | WASTE-REQ72 | Reporting lines to be communicated to RCL | Must have
Place |  | Waste | WASTE-REQ73 | Agreement to pay CCC invoices for the period to 31 March 2023 and new authorities from 01 April 2023 | Must have |  | requires further discussion with | Finance
Place |  | Waste | WASTE-REQ74 | Inter Authority Agreement in place to process payments | Must have |  | requires support from | Finance
Place |  | Waste | WASTE-REQ74 | Inter Authority Agreement in place to process payments | Must have |  | requires support from | Strategic Commissioning
Place |  | Waste | WASTE-REQ75 | How to deal with CCC legacy issues: Accrual/provision | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ76 | Responsibilities for Waste Data Flow to be agreed between new authorities (currently districts for recycling/bring sites and CCC for residua) | Must have |  | requires support from | ICT
Place |  | Waste | WASTE-REQ76 | Responsibilities for Waste Data Flow to be agreed between new authorities (currently districts for recycling/bring sites and CCC for residua) | Must have |  | developed together with | All services - all employees
Place |  | Waste | WASTE-REQ77 | Budgets to be set | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ78 | Access to data – ICT systems/Sharepoint | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ79 | Bulky waste collection | Should have
Place |  | Waste | WASTE-REQ80 | Charges for replacement receptacles | Should have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ80 | Charges for replacement receptacles |  |  | requires support from | Communications and Engagement
Place |  | Waste | WASTE-REQ81 | Consistency in uniform / PPE / badging etc | Should have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ82 | Vehicle livery | Should have | requires support from |  | Fleet
Place |  | Waste | WASTE-REQ83 | Single approach to recruitment, selection and training of new staff starting from 01 April 2023 on common T+Cs, salaries etc | Should have | requires support from |  | Legal & Democratic Services
|  | Waste | WASTE-REQ84 | Consistency in policies and procedures i.e. assisted collections, collection of side waste, missed collections | Should have |  | requires support from | Legal & Democratic Services
Place |  | Waste | WASTE-REQ84 | Consistency in policies and procedures i.e. assisted collections, collection of side waste, missed collections | Should have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ85 | Combined service budgets – clear lines of responsibility | Should have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ86 | Office locations agreed | Should have | requires support from |  | HR & OD | Assets
Place |  | Waste | WASTE-REQ87 | Agreed trade tipping rates | Should have | developed together with |  | Finance
Place |  | Waste | WASTE-REQ88 | Better understanding of Renewi policies that effect the waste collection element of Cumberland | Should have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ89 | Agreement on how to handle complaints and FOIs | Should have | requires further discussion with |  | Customer & Digital
Place |  | Waste | WASTE-REQ90 | Data - Systems should be in place to record data for the new authority. Must happen by end 1st month. | Should have | developed together with |  | ICT | Requires support from ICT - Service Continuity and ICT - Infrastructure, ICT applications
Place |  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | requires support from | Legal & Democratic Services
|  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | developed together with | HR & OD
|  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | developed together with | Strategic Commissioning
|  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | developed together with | Communications and Engagement
Place |  | Waste | WASTE-REQ92 | A better understanding of the contract for the Disposal element of the work | Should have | requires further discussion with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ93 | Consistency in salaries for operational staff – supervisors / loaders / drivers etc | Could have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ94 | Potential to share resources eg at management / supervisory level | Could have | requires further discussion with |  | HR & OD
Place |  | Waste | WASTE-REQ95 | Potential to share vehicles and other resources | Could have |  | requires further discussion with | Fleet
Place |  | Waste | WASTE-REQ95 | Potential to share vehicles and other resources | Could have |  | has a connection with | Transport
Place |  | Waste | WASTE-REQ96 | Agreed position towards membership of national sector organisations and agreement on first point of contact (ie. LARAC, NAWDO, etc) | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ97 | A move towards consistency of IT use | Could have | requires further discussion with |  | ICT
Place |  | Waste | WASTE-REQ98 | An understanding about how current trade waste contracts could possibly be transferred to CWM | Could have |  | requires further discussion with | Strategic Commissioning
Place |  | Waste | WASTE-REQ98 | An understanding about how current trade waste contracts could possibly be transferred to CWM | Could have |  | requires support from | Legal & Democratic Services
Place |  | Waste | WASTE-REQ99 | Standardised H&S procedures e.g. near misses, gate checks, seat belt checks, crew engagement, safety reps | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ100 | ICT – access to Scada system for closed landfill | Could have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ101 | What will permit scheme look like? Pedestrian and Annual Permits? | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ102 | Policies - Existing policies transfer by area. Some policies could have been aligned (closed lid, side waste, lane end). | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ103 | Processes - Some processes could be aligned (assisted collections, requests for larger bins). | Could have |  |  |  | No detail provided
Place |  | Waste | WASTE-REQ104 | National Waste Strategy - Depends on timing of announcement and required actions. | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ105 | Re-branding of PPE - Some could have been done. Potential for hybrid clothing (SLDC fleece, WaF coat etc). | Could have | requires further discussion with |  | Communications and Engagement
Place |  | Waste | WASTE-REQ106 | Agreed position towards membership of national sector organisations and agreement on first point of contact (ie. LARAC, NAWDO, etc) | Could have |  |  |  | No detail provided
Place |  | Waste | WASTE-REQ107 | H&S and Performance, how that is monitored within Westmorland and Furness | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ108 | Awareness training for all waste service employees | Could have | requires support from |  | HR & OD | Assets
Place |  | Waste | WASTE-REQ109 | Environment Agency Permit transfer/UU discharge consents to legal entity (is there a requirement to apply or is this covered by the SCO?) | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ110 | Ability to pay EA subsistence fees for closed landfill from 01 April 2023 | Could have |  | requires support from | Finance
Place |  | Waste | WASTE-REQ110 | Ability to pay EA subsistence fees for closed landfill from 01 April 2023 | Could have |  | requires further discussion with | Strategic Commissioning
Place |  | Waste | WASTE-REQ111 | DCF registration – currently CWM | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ112 | Approach to branding strategy to be agreed and position on Performance Framework to be set out (eg how long CCC branding can remain in place before deductions apply) signs and PPE for site operatives | Could have |  | requires further discussion with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ112 | Approach to branding strategy to be agreed and position on Performance Framework to be set out (eg how long CCC branding can remain in place before deductions apply) signs and PPE for site operatives | Could have |  | developed together with | Customer & Digital
Place |  | Waste | WASTE-REQ113 | Agreement on paying royalty/rents – currently sitting with waste team | Could have | requires further discussion with |  | Finance
Place |  | Waste | WASTE-REQ114 | New authorities to brief CWM site operatives – clear and unambiguous message about what the changes mean for the HWRC sites and customers | Could have |  | requires further discussion with | HR & OD
Place |  | Waste | WASTE-REQ114 | New authorities to brief CWM site operatives – clear and unambiguous message about what the changes mean for the HWRC sites and customers | Could have |  | developed together with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ115 | Commercial gate fees to be agreed with new authorities (currently only Copeland and Allerdale) | Could have | requires further discussion with |  | Finance
Place |  | Waste | WASTE-REQ116 | Agreement on policies eg charities, side waste | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ117 | Schedule of assets for the new authorities (MBT, HWRC, closed landfill) | Could have | requires support from |  | Workstream - Assets | Assets
Place |  | Waste | WASTE-REQ118 | ICT – access to Scada system for closed landfill | Could have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ119 | What will permit scheme look like? Pedestrian and Annual Permits? | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ119 | What will permit scheme look like? Pedestrian and Annual Permits? | Could have |  | has a connection with | Customer & Digital
Place |  | Waste | WASTE-REQ120 | Consistency in service standards | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ121 | Consistency in service design | Won't have | requires further discussion with |  | Waste | Assets
Place |  | Waste | WASTE-REQ122 | Consistency towards commercial waste collections | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ123 | Waste and Recycling policy alignment | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ124 | Consistency in collection frequency | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ125 | Consistency in container type and size | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ126 | Depot rationalisation/location | Won't have |  | requires support from | Workstream - Assets | Assets
Place |  | Waste | WASTE-REQ126 | Depot rationalisation/location | Won't have |  | developed together with | Waste | Assets
Place |  | Waste | WASTE-REQ127 | Re-routing and re-rounding following removal of boundaries | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ128 | Efficient direct delivery from the North of Allerdale to Hespin Wood but could have! | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ129 | Decision on in-house v LATCo model | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ130 | Opportunity to rationalise/standardise Bring Banks | Won't have | requires support from |  | Waste
Place |  | Waste | WASTE-REQ131 | Consistency in service standards | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ132 | Consistency in service design | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ133 | Consistency towards commercial waste collections | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ134 | Re-branding of bins & boxes - Not urgent, can be done as new items, bins etc are ordered. | Won't have | requires support from |  | Communications & Engagement
Place |  | Waste | WASTE-REQ134 | Re-branding of vehicles - Not urgent, can be done as new vehicles are ordered or as prioritised. | Won't have | requires support from |  | Communications & Engagement
Place |  | Waste | WASTE-REQ135 | In-cab systems - Too complex to introduce by day 1. | Won't have | requires further discussion with |  | ICT
Place |  | Waste | WASTE-REQ136 | Round changes - Any round or route changes must be embedded by December 2022. | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ137 | Waste and Recycling Policy alignment and Consistency in collection frequency and containers | Won't have | requires further discussion with |  | Waste | Assets
Place |  | Waste | WASTE-REQ138 | Reviewed Bring Sites within Westmorland and Furness | Won't have | requires further discussion with |  |  | Assets
Place |  | Waste | WASTE-REQ139 | Agreement on enforcement powers, eg suspected trade waste abuse at HWRCs | Won't have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ140 | New HWRC permit scheme | Won't have | requires further discussion with |  | Strategic Commissioning
Place |  | Climate Change/Net Zero | CLIMATE-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have | developed together with | developed together with | Planning and Building Control |  |  | Summer 2022
Place |  | Climate Change/Net Zero | CLIMATE-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have |  |  | Street Scene and Open Spaces |  |  | Summer 2022
Place |  | Climate Change/Net Zero | CLIMATE-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have |  |  | Community/Localism
Place |  | Climate Change/Net Zero | CLIMATE-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have |  |  | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ2 | Officer to work on Annual Status Report (Due to be submitted to DEFRA by June) | Must have | requires support from | requires support from | Legal & Democratic Services |  |  | By June 2023
Place |  | Climate Change/Net Zero | CLIMATE-REQ2 | Officer to work on Annual Status Report (Due to be submitted to DEFRA by June) | Must have | requires support from | requires support from | Street Scene and Open Spaces
Place |  | Climate Change/Net Zero | CLIMATE-REQ2 | Officer to work on Annual Status Report (Due to be submitted to DEFRA by June) | Must have | requires support from | requires support from | Public Health
Place |  | Climate Change/Net Zero | CLIMATE-REQ2 | Officer to work on Annual Status Report (Due to be submitted to DEFRA by June) | Must have | requires support from | requires support from | Public Protection
Place |  | Climate Change/Net Zero | CLIMATE-REQ3 | ACB Arrangements for existing projects and supporting resources - check acronym | Must have | [5 empty] | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ4 | Formal Grant Agreement and funding arrangements have been transferred eg Account Body Status | Must have | requires further discussion with | Legal & Democratic Services | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ4 | Formal Grant Agreement and funding arrangements have been transferred eg Account Body Status | Must have | requires further discussion with |  | Finance |  |  | 2023-04-02
Place |  | Climate Change/Net Zero | CLIMATE-REQ4 | Formal Grant Agreement and funding arrangements have been transferred eg Account Body Status | Must have | requires further discussion with |  | Grants Portfolio |  |  | 2023-04-03
Place |  | Climate Change/Net Zero | CLIMATE-REQ4 | Formal Grant Agreement and funding arrangements have been transferred eg Account Body Status | Must have | requires further discussion with |  | Contract Management/Monitoring |  |  | 2023-04-04
Place |  | Climate Change/Net Zero | CLIMATE-REQ5 | Policy in place to ensure compliance with current legislation eg Environment Act 2021 Requirements - incl Biodiversity Net Gain | Must have |  | requires support from | Policy Framework |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ5 | Policy in place to ensure compliance with current legislation eg Environment Act 2021 Requirements - incl Biodiversity Net Gain | Must have |  | requires support from | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ6 | Staffing and financial resource to ensure requirements can be met | Must have |  | is dependant on as a precursor | HR & OD |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ6 | Staffing and financial resource to ensure requirements can be met | Must have |  | is dependant on as a precursor | Finance
Place |  | Climate Change/Net Zero | CLIMATE-REQ7 | Flood and Water Management Act - Lead Local Flood Authority | Must have | requires further discussion with |  | Highways |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ8 | Robust Climate Risk Assessment | Must have |  | developed together with | Risk Management & Business Continuity |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ8 | Robust Climate Risk Assessment | Must have |  | developed together with | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ9 | Procurement policy covering social value incl Environmental Stability (PPN 06/20, 06/21, Social Value Act) | Must have |  | requires further discussion with | Strategic Procurement / Strategy​ |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ9 | Procurement policy covering social value incl Environmental Stability (PPN 06/20, 06/21, Social Value Act) | Must have |  | requires further discussion with | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ10 | Sustainability assessment of planning decisions | Must have |  | developed together with | Planning and Building Control |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ10 | Sustainability assessment of planning decisions | Must have |  | developed together with | Housing
Place |  | Climate Change/Net Zero | CLIMATE-REQ11 | Coast Protection Authorities and Coastal Erosion Risk Management Authorities | Must have | developed together with |  | Highways |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ12 | Civil Contingencies Act 2004 - dealing with emergencies (Community Risk Register) | Must have | is dependant on as a precursor |  | Resilience and Emergency Planning |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ13 | Assurance that LGR Programme interdependencies with cross-cutting themes are managed (eg via climate impact assessment) | Must have | is dependant on as a precursor |  | All services - all line managers |  |  | Now onwards
Place |  | Climate Change/Net Zero | CLIMATE-REQ14 | Net Zero target | Should have |  | requires further discussion with | All services - all line managers |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ14 | Net Zero target | Should have |  | requires further discussion with | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ14 | Net Zero target | Should have |  | requires further discussion with | Transformation & Change Management
Place |  | Climate Change/Net Zero | CLIMATE-REQ15 | Route map for compliance with Climate Change Act - Net Zero by 2037/2049 | Should have |  | requires further discussion with | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ15 | Route map for compliance with Climate Change Act - Net Zero by 2037/2050 | Should have |  | requires further discussion with | Transformation & Change Management |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ16 | Clear links with partnerships | Should have |  | developed together with | Community/Localism |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ16 | Clear links with partnerships | Should have |  | developed together with | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ17 | Strategy: Action Plan for Climate Change, Environment and Biodiversity | Should have |  | requires further discussion with | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ17 | Strategy: Action Plan for Climate Change, Environment and Biodiversity | Should have |  | requires further discussion with | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ18 | Adaptation strategy and plan | Should have |  | requires support from | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ18 | Adaptation strategy and plan | Should have |  | requires support from | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ19 | Procurement policy that priorities Climate/Sustainability above mandatory levels | Should have | is dependant on as a precursor |  | Strategic Procurement / Strategy​ |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ20 | Climate Data monitoring | Should have | requires further discussion with |  | Performance & Business Intelligence |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ20 | Climate Governance - Board, Steering Group | Should have | is dependant on as a precursor |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ20 | Climate Governance - Board, Steering Group | Should have | is dependant on as a precursor |  | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ21 | Local Energy strategy | Should have |  | requires further discussion with | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ21 | Local Energy strategy | Should have |  | requires further discussion with | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ21 | Local Energy strategy | Should have |  | requires further discussion with | Capital Programme
Place |  | Climate Change/Net Zero | CLIMATE-REQ21 | Local Energy strategy | Should have |  | requires further discussion with | Economic Development
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Long term financial plan for mitigation and adaptation | Should have | is dependant on as a precursor |  | Finance |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Internal climate change action plan (emissions reduction etc) linked to Corporate KPIs | Should have |  | requires further discussion with | Policy Framework |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Internal climate change action plan (emissions reduction etc) linked to Corporate KPIs | Should have |  | requires further discussion with | All services - all line managers |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Biodiversity to be integrated to work stream and corporate priorities | Should have | developed together with |  | All services - all line managers |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ22 | Key expert staff in place around climate change, biodiversity, decarbonisation | Should have | requires support from |  | HR & OD |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ23 | Assessment of climate and ecological implications of key decisions | Should have |  | requires further discussion with | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ23 | Assessment of climate and ecological implications of key decisions | Should have |  |  | All services - all line managers
Place |  | Climate Change/Net Zero | CLIMATE-REQ23 | Website - information for public on climate change, links to strategies, carbon footprint etc | Should have | requires further discussion with |  | Communications and Engagement |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ24 | Stakeholder Engagement Plan | Should have | requires further discussion with |  | Communications and Engagement |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ24 | Stakeholder Engagement Plan | Should have | requires further discussion with |  | Community/Localism
Place |  | Climate Change/Net Zero | CLIMATE-REQ25 | Budget (for Climate Communication, projects community engagement) | Should have | is dependant on as a precursor |  | Finance |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ26 | Climate Comms Strategy | Should have | requires further discussion with |  | Communications and Engagement |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ27 | HR Policies (eg recruitment, performance training) linked to sustainability | Should have | requires further discussion with |  | HR & OD |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ28 | Declaration of Climate Emergency | Could have | has a connection with |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ29 | Climate Champions in all different services within new authorities | Could have | requires further discussion with |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ30 | Retain successful council partnerships | Could have | requires further discussion with |  | Community/Localism |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ31 | Carbon literacy training to be implemented in induction for staff | Could have | requires further discussion with |  | Learning & Development |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ32 | Nominations to existing external partnerships (eg ZCCP) | Could have | developed together with |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ33 | Carbon accounting methodology and mechanisms | Could have | developed together with |  | Performance & Business Intelligence
Place |  | Climate Change/Net Zero | CLIMATE-REQ34 | Adaptation strategy and plan - duplication (also down as Should Have) | Could have |  |  | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ35 | Net Zero Operational target (also down as Should Have) | Could have |  |  | Policy Framework
Place |  | Climate Change/Net Zero | CLIMATE-REQ36 | Net Zero geographical target (does this differ from above?) | Could have |  |  | Policy Framework |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ37 | Memberships (APSE etc) | Could have | developed together with |  | Legal & Democratic Services |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ38 | Net Zero software / tool | Could have | developed together with |  | Performance & Business Intelligence |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ39 | Clear roles and responsibilities to ensure delivery | Could have | is dependant on as a precursor |  | HR & OD |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ40 | Net Zero Skills audits | Could have | is dependant on as a precursor |  | Learning & Development |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ41 | Budgets for consultants | Could have |  | is dependant on as a precursor | Finance |  |  | 2023-04-01
Place |  | Climate Change/Net Zero | CLIMATE-REQ41 | Budgets for consultants | Could have |  | is dependant on as a precursor | Highways
Place |  | Climate Change/Net Zero | CLIMATE-REQ41 | Budgets for consultants | Could have |  | is dependant on as a precursor | Legal & Democratic Services
Place |  | Climate Change/Net Zero | CLIMATE-REQ42 | Electric Vehicle transition / infrastructure plan | Could have |  | developed together with | Fleet
Place |  | Climate Change/Net Zero | CLIMATE-REQ42 | Electric Vehicle transition / infrastructure plan | Could have |  | developed together with | Transport
Place |  | Climate Change/Net Zero | CLIMATE-REQ43 | Net Zero operational emissions | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ44 | Council-owned energy company | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ45 | Community energy ownership schemes | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ46 | Mechanisms for non-financial climate and nature related disclosures | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ47 | Ability to achieve Net Zero by 2037 (ie budget, resources, policies etc) | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ48 | Sufficient resources or budget to address climate and nature crises urgently enough | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ49 | Low carbon affordable mobility strategy | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ50 | Robust and funded active travel infrastructure | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ51 | Internal biodiversity net gain principle for council projects | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ52 | Carbon Accounting (duplication - also down as Could Have) | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ53 | Tree Planting target | Won't have |  |  |  | No detail provided
Place |  | Climate Change/Net Zero | CLIMATE-REQ54 | Updated Local Plan - sustainability embedded into policies | Won't have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ1 | Budgets & managing performance within departments, approval limits established, performance reporting in place | Must Have | is reliant upon decisions being made by and requires support from |  | Finance
Place |  | Housing | HOUSE-REQ2 | Out Of Hours Service | Must Have |  | Place Theme - Housing | requires support from
Place |  | Housing | HOUSE-REQ2 | Out Of Hours Service | Must Have |  | is reliant upon decisions being made by and requires support from | Housing
Place |  | Housing | HOUSE-REQ3 | Out Of Hours Service | Must Have |  | is reliant upon decisions being made by and requires support from | HR & OD
Place |  | Housing | HOUSE-REQ4 | Out Of Hours Service | Must Have |  | is reliant upon decisions being made by and requires support from | ICT
Place |  | Housing | HOUSE-REQ5 | Out Of Hours Service | Must Have |  | is reliant upon decisions being made by and requires support from | Customer & Digital
Place |  | Housing | HOUSE-REQ6 | Branded Website with links and Duty to Refer emails | Must Have |  | Requires support from | ICT
Place |  | Housing | HOUSE-REQ6 | Branded Website with links and Duty to Refer emails | Must Have |  | developed together with | Customer & Digital
Place |  | Housing | HOUSE-REQ6 | Branded Website with links and Duty to Refer emails | Must Have |  | developed together with | Communications and Engagement
Place |  | Housing | HOUSE-REQ7 | Fees & Charges should align | Must Have | is reliant upon decisions being made by |  | Finance
Place |  | Housing | HOUSE-REQ7 | Essential standard policies for statutory services, e.g. DFG | Must Have | is reliant upon decisions being made by |  | Strategic Commissioning
Place |  | Housing | HOUSE-REQ8 | Essential standard policies for statutory services, e.g. DFG | Must Have |  | developed together with | Finance
Place |  | Housing | HOUSE-REQ9 | Essential standard policies for statutory services, e.g. DFG | Must Have |  | developed together with | Public Protection
Place |  | Housing | HOUSE-REQ10 | Essential standard policies for statutory services, e.g. DFG | Must Have |  | developed together with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ11 | IT relevant to service - Locata. Flare, Civica CBL, Northgate, Idox, Anite, Info at work, Civicare, HIA foundations case manager, Abavus my council services, Ferret, Case management systems. Flare is needed but may not be fuctioning by vesting day. | Must have |  | developed together with | ICT
Place |  | Housing | HOUSE-REQ11 | IT relevant to service - Locata. Flare, Civica CBL, Northgate, Idox, Anite, Info at work, Civicare, HIA foundations case manager, Abavus my council services, Ferret, Case management systems. Flare is needed but may not be fuctioning by vesting day. | Must have |  | requires support from | Customer & Digital
Place |  | Housing | HOUSE-REQ12 | IT relevant to service - Locata. Flare, Civica CBL, Northgate, Idox, Anite, Info at work, Civicare, HIA foundations case manager, Abavus my council services, Ferret, Case management systems. Flare is needed but may not be fuctioning by vesting day. | Must have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ13 | Branding, name badges and ID for stat visits | Must Have | requires support from |  | Communications and Engagement
Place |  | Housing | HOUSE-REQ14 | Core Support Services such as: Finance, Business Support, Legal, HR & IT. Able to recruit. | Must Have | requires support from |  | All services - all employees
Place |  | Housing | HOUSE-REQ14 | Core Support Services such as: Finance, Business Support, Legal, HR & IT. Able to recruit. | Must Have |  | developed together with | Finance
Place |  | Housing | HOUSE-REQ14 | Core Support Services such as: Finance, Business Support, Legal, HR & IT. Able to recruit. | Must Have |  | developed together with | ICT
Place |  | Housing | HOUSE-REQ14 | Core Support Services such as: Finance, Business Support, Legal, HR & IT. Able to recruit. | Must Have |  | developed together with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ15 | Supported Accomodation Contract/Grant Agreements | Must Have | requires support from |  | Strategic Commissioning
Place |  | Housing | HOUSE-REQ15 | Supported Accomodation Contract/Grant Agreements | Must Have |  | developed together with | HR & OD
Place |  | Housing | HOUSE-REQ15 | Supported Accomodation Contract/Grant Agreements | Must Have |  | developed together with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ16 | Contractor relationships and processes need to continue for day one. | Must Have | is reliant upon decisions being made by |  | Strategic Commissioning
Place |  | Housing | HOUSE-REQ16 | Contractor relationships and processes need to continue for day one. | Must Have | is reliant upon decisions being made by | is reliant upon decisions being made by |  | People -Adults
Place |  | Housing | HOUSE-REQ17 | DA Crisis contact numbers | Must Have | requires further discussion with | Communications & Engagement | developed together with
|  | Housing | HOUSE-REQ18 | CBL Fully operational | Must Have |  | requires support from | Strategic Commissioning
|  | Housing | HOUSE-REQ18 | CBL Fully operational | Must Have |  | requires support from | ICT
Place |  | Housing | HOUSE-REQ18 | CBL Fully operational | Must Have |  | requires support from | developed together with
Place |  | Housing | HOUSE-REQ19 | Consitution for Officers delegations | Must Have |  | is reliant upon decisions being made by | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ19 | Consitution for Officers delegations | Must Have |  | is reliant upon decisions being made by | ICT
Place |  | Housing | HOUSE-REQ19 | Consitution for Officers delegations | Must Have |  | is reliant upon decisions being made by | Customer & Digital
Place |  | Housing | HOUSE-REQ20 | Customers can dial in and email, self serve on day 1 - different legacy council has different triage proesses and that needs to be maintained for day 1 | Must Have | requires support from |  | Communications & Engagement
Place |  | Housing | HOUSE-REQ21 | Executive functions to take reports | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ21 | Executive functions to take reports | Must Have |  | is interdependent with | Finance - Benefit Realisation
Place |  | Housing | HOUSE-REQ21 | Executive functions to take reports | Must Have |  | is interdependent with | ICT
Place |  | Housing | HOUSE-REQ22 | DFG funding payments, approvals, financial delegations. | Must Have | requires support from |  | Finance
Place |  | Housing | HOUSE-REQ22 | DFG funding payments, approvals, financial delegations. | Must Have |  | is interdependent with | Communications and Engagement
Place |  | Housing | HOUSE-REQ22 | DFG funding payments, approvals, financial delegations. | Must Have |  | is interdependent with | Community/Localism
Place |  | Housing | HOUSE-REQ22 | DFG funding payments, approvals, financial delegations. | Must Have |  | is interdependent with | Public Protection
Place |  | Housing | HOUSE-REQ23 | Process for dealing with homeless appeals / approvals | Must Have |  | is reliant upon decisions being made by | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ24 | Process for dealing with homeless appeals / approvals | Must Have |  | is interdependent with | Finance
Place |  | Housing | HOUSE-REQ25 | Green homes grant structures / team | Must Have | is reliant upon decisions being made by |  | Finance
Place |  | Housing | HOUSE-REQ25 | Green homes grant structures / team | Must Have | is reliant upon decisions being made by | is interdependent with | ICT
Place |  | Housing | HOUSE-REQ26 | Government delta returns & HCLIC need to be possible. (Flag discussion around aggregation of returns for new council). | Must Have | requires support from | ICT - Service Continuity | ICT - Service Continuity
Place |  | Housing | HOUSE-REQ26 | Government delta returns & HCLIC need to be possible. (Flag discussion around aggregation of returns for new council). | Must Have | requires support from |  | Adults
Place |  | Housing | HOUSE-REQ26 | Government delta returns & HCLIC need to be possible. (Flag discussion around aggregation of returns for new council). | Must Have |  |  | ICT
Place |  | Housing | HOUSE-REQ26 | Government delta returns & HCLIC need to be possible. (Flag discussion around aggregation of returns for new council). | Must Have |  |  |  | Children
Place |  | Housing | HOUSE-REQ27 | procedure for referrals from OTs and Health absed childrens OT need to be agreed and tested | Must Have | is reliant upon decisions being made by |  | Public Health
Place |  | Housing | HOUSE-REQ27 | procedure for referrals from OTs and Health absed childrens OT need to be agreed and tested | Must Have |  | is interdependent with | Communications and Engagement
Place |  | Housing | HOUSE-REQ27 | procedure for referrals from OTs and Health absed childrens OT need to be agreed and tested | Must Have |  | is interdependent with | ICT
Place |  | Housing | HOUSE-REQ28 | Training on day 1 changes for the teams | Must Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ40 | Training on day 1 changes for the teams |  |  | is interdependent with | Public Health
Place |  | Housing | HOUSE-REQ40 | Training on day 1 changes for the teams |  |  | is interdependent with | Public Protection
Place |  | Housing | HOUSE-REQ40 | Training on day 1 changes for the teams |  |  | is interdependent with | Community/Localism
Place |  | Housing | HOUSE-REQ41 | Service for homeless families to assess applications and be able to provide temp accomodation and wider support for children/safeguarding process | Must Have | requires support from |  |  | People Theme - Childrens and Families
Place |  | Housing | HOUSE-REQ41 | Service for homeless families to assess applications and be able to provide temp accomodation and wider support for children/safeguarding process | Must Have | requires support from |  | Customer & Digital
Place |  | Housing | HOUSE-REQ42 | Landlord functions and Urgent response for Council tenants (e.g. repairs). Where there are districts providing Landlord services, standards and policies need to be aligned for Day 1. | Must Have | requires support from |  | Communications and Engagement
Place |  | Housing | HOUSE-REQ43 | Procedures, hand off points between teams etc | Should Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ43 | Procedures, hand off points between teams etc | Should Have |  | is interdependent with | Finance
Place |  | Housing | HOUSE-REQ44 | Procedures, hand off points between teams etc | Should Have |  | is interdependent with |  | Workstream - Assets
Place |  | Housing | HOUSE-REQ45 | Procedures, hand off points between teams etc | Should Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ46 | Procedures, hand off points between teams etc | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ47 | Premises to operate from and teams in place in each service area to meet service demand. | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ47 | Premises to operate from and teams in place in each service area to meet service demand. | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ48 | Plans to identify existing contracts and how to align, novate etc | Should Have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ54 | Plans to identify existing contracts and how to align, novate etc | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ54 | Plans to identify existing contracts and how to align, novate etc | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ55 | Identifying non priority Policies and plan to review these and timescale | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ56 | Revised Constitution | Should Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ57 | Identify areas that may need new procurement | Should Have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ57 | Identify areas that may need new procurement | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ58 | A plan to align relevant Strategies, e.g. Housing Strategy - what will the priorities be? | Should Have | Requires discussion with |  | Strategic Commissioning
Place |  | Housing | HOUSE-REQ59 | Plan to review partnerships | Should Have |  | requires support from | Communications and Engagement
Place |  | Housing | HOUSE-REQ59 | Plan to review partnerships | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ60 | Effective policies for DFGs, HHSRS and HMOs | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ61 | Local Plan policies in place | Should Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ62 | Identitly of new teams and processes to manage them effectively | Should Have |  | developed together with | HR & OD
Place |  | Housing | HOUSE-REQ62 | Identitly of new teams and processes to manage them effectively | Should Have |  | requires support from | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ63 | review HIA, options going forward. :better homes agency" | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ64 | funding agreements, LAD, domestic abuse | Should Have | requires support from |  | Finance | Cross cutting theme - Financial Sustainability and Benefits Realisation
Place |  | Housing | HOUSE-REQ65 | Direcction of travel for aligning Planning Policies | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ66 | internal procedures, reviewed. process based. | Should Have |  | requires support from | Finance
Place |  | Housing | HOUSE-REQ66 | internal procedures, reviewed. process based. | Should Have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ67 | updated letterheads,licence docs, offcial paperwork to the customer | Should Have |  | requires further discussion with | ICT
Place |  | Housing | HOUSE-REQ67 | updated letterheads,licence docs, offcial paperwork to the customer | Should Have |  | developed together with | Communications and Engagement
Place |  | Housing | HOUSE-REQ68 | started to review staffing and roles, Job Descriptions | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ69 | Analysis of which partnerships are still required and new partnershps needed | Should Have |  | requires further discussion with | Communications and Engagement
Place |  | Housing | HOUSE-REQ70 | Clear guidelines and timelines for staff on emerging structures still not in place | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ71 | identify policies that are required and considered to approval at new Executive | Should Have |  | requires support from | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ71 | identify policies that are required and considered to approval at new Executive | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ72 | review IT systems, not common accross and consider options. | Should Have | requires support from |  | ICT
Place |  | Housing | HOUSE-REQ73 | consolidation of some policy. updated to improve services | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ74 | Common Quality Standards | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ75 | Staff training programme in place and rolling out to embedd new culture, policies changes, new IT, workarounds etc | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ75 | Staff training programme in place and rolling out to embedd new culture, policies changes, new IT, workarounds etc | Should Have |  | requires support from | ICT
Place |  | Housing | HOUSE-REQ76 | Clear decision making and escalation routes | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ76 | Clear decision making and escalation routes | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ77 | streamine none day 1 critical policy and process for discretionary activity so no postcode lottery | Should Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ78 | Plans around HIA development and timeline | Should Have | requires support from |  | ICT
Place |  | Housing | HOUSE-REQ79 | Streamlined Homelessness and Housing Strategies Private sector Housing Grants policies | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ80 | review of policies and procedures, KPI's/monitoring frameworks partner agencies arrangements | Should Have |  | requires further discussion with | Communications and Engagement
Place |  | Housing | HOUSE-REQ80 | review of policies and procedures, KPI's/monitoring frameworks partner agencies arrangements | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ81 | team management lines for comms, 1-1s, team meetings in place | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ82 | Staff training programmes, appraisal processes agreed | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ83 | full team | Should Have | is reliant upon decisions being made by |  | HR & OD
Place |  | Housing | HOUSE-REQ84 | internal policies/training for colleagues ie GDPR, safeguarding, E&D, new LA priorities | Should Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ85 | Partnerships reviewed and resstrucutred eg Cumbria Housing Group (and subgroups) and the Social Landlord/LA group plus agree what is happening with local partnerships | Should Have |  | requires further discussion with | Communications and Engagement
Place |  | Housing | HOUSE-REQ85 | Partnerships reviewed and resstrucutred eg Cumbria Housing Group (and subgroups) and the Social Landlord/LA group plus agree what is happening with local partnerships | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ86 | team know who to report to if different to current arrangments | Should Have | requires further discussion with |  | HR & OD
Place |  | Housing | HOUSE-REQ87 | appraisals and training plans & priorities of the new council, to aid delivery | Should Have |  |  | HR & OD
Place |  | Housing | HOUSE-REQ88 | Strategic partnerships | Could Have |  | requires support from | Communications and Engagement
Place |  | Housing | HOUSE-REQ88 | Strategic partnerships | Could Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ89 | Strategic housing priorities | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ102 | Integrated DFG team with OTs, etc | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ103 | Alignment of contracts - Locata | Could Have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ103 | Alignment of contracts - Locata | Could Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ104 | Consistent template agreements, e.g. grants etc | Could Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ105 | Some alignment of key policies | Could Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ106 | One service team across the whole LA, ie homelessness | Could Have | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ107 | MDT of colleagues dealing with DFG's - OT's, Asc, HIA | Could Have
Place |  | Housing | HOUSE-REQ108 | Working partnership groups with Rp,s developers, Vol sector, | Could Have |  | requires support from | Communications & Engagement
Place |  | Housing | HOUSE-REQ108 | Working partnership groups with Rp,s developers, Vol sector, | Could Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ109 | Align the HoC properties with BBC housing stock to be managed inhouse | Could Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ110 | Model for delivering Green Homes/sustainable warnth & bididng for new fundign opportunities | Could Have | requires further discussion with |  | Finance
Place |  | Housing | HOUSE-REQ111 | Domestic Abuse strategy | Could Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ112 | settled teams who all know their own roles/responsibilities | Could Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ113 | Local Housing Company | Could Have | requires support from |  | Communications & Engagement
Place |  | Housing | HOUSE-REQ114 | Shared contracts in place for DFGs, ECO | Could Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ115 | A model for a new HIA or Better Homes Agency | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ116 | Started work around joint working polcies, practices | Could Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ116 | Started work around joint working polcies, practices | Could Have |  | requires support from | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ117 | Rebranding of Officer equipment, letters, communication | Could Have |  | requires support from | Communications & Engagement
Place |  | Housing | HOUSE-REQ117 | Rebranding of Officer equipment, letters, communication | Could Have |  | developed together with | ICT
Place |  | Housing | HOUSE-REQ118 | Started to look at Intergration of DFG within ASC | Could Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ119 | Uniformed Services for Homeless Services, Housing Asssitance, tenancy advocacy | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ120 | empty homes strategy in plae for each unitary | Could Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ121 | Integrated needs assessment for complex cases ASC/Homelessness/DFGs etc | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ122 | acess to data within east and west so staff can cover all areas not jsut legalcy footprint and provide OOH effectively | Could Have | requires support from |  | ICT
Place |  | Housing | HOUSE-REQ123 | Integrated OT/DFG teams | Could Have | is reliant upon decisions being made by |  | HR & OD
Place |  | Housing | HOUSE-REQ124 | HIA for each new Unitary | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ125 | one OOH shared system integrated with Social Care duty teams | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ126 | shared budgets for homeless prevention | Could Have |  | requires support from | Finance
Place |  | Housing | HOUSE-REQ126 | shared budgets for homeless prevention | Could Have |  | developed together with |  | Cross cutting theme - Financial Sustainability and Benefits Realisation
Place |  | Housing | HOUSE-REQ127 | LHC registered and linking with econmic regen plans | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ128 | Social Care white paper delivery/transition plan | Could Have | requires further discussion with |  | Public Health
Place |  | Housing | HOUSE-REQ129 | One DFG service/meanstesting/ top ups etc | Could Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ130 | Every strategy related not likely to be in place. | Won't Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ131 | All contracts aligned. | Won't Have |  | requires support from | Strategic Commisssioning
Place |  | Housing | HOUSE-REQ131 | All contracts aligned. | Won't Have |  | developed together with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ132 | Aligned evidence base, e.g. stock condition survey or other evidence supporting strategic development - homeless reviews | Won't Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ133 | Consistent approach/funding opportunities in some areas, e.g. empty homes | Won't Have | requires support from |  | Finance
Place |  | Housing | HOUSE-REQ134 | Definitive operating model | Won't Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ135 | new team/structure in place, forums/working groups/partnerships | Won't Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ135 | new team/structure in place, forums/working groups/partnerships | Won't Have |  | requires further discussion with | Communications and Engagement
Place |  | Housing | HOUSE-REQ136 | One Team - all speaking with one voice | Won't Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ137 | all the necessary policies/procedures in place and/or aligned | Won't Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ138 | same team structure across the LA | Won't Have | requires further discussion with |  | HR & OD
Place |  | Housing | HOUSE-REQ139 | budgets | Won't Have | requires support from |  | Finance
Place |  | Housing | HOUSE-REQ140 | a new vision/culture - YET | Won't Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ141 | aligned pay/conditions | Won't Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ142 | aligned pay/conditions | Won't Have |  | developed together with | Finance - Financial & Commercial Stability
Place |  | Housing | HOUSE-REQ143 | settled teams/colleagues | Won't Have | developed together with |  | HR & OD
Place |  | Housing | HOUSE-REQ144 | job descriptions/role profiles consistent | Won't Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ145 | All new teams and systems in place | Won't Have |  | requires support from | HR & OD
|  | Housing | HOUSE-REQ145 | All new teams and systems in place | Won't Have |  | developed together with | ICT
|  | Housing | HOUSE-REQ145 | All new teams and systems in place | Won't Have |  | developed together with | Finance
Place |  | Housing | HOUSE-REQ146 | Consistent approach to Officers decisions, autonomy | Won't Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ147 | Shared IT systems for areas of work, specific to work area. FLARE, CASE MANAGER | Won't Have | requires support from |  | ICT |  |  |  | ICT - Infrastructure
Place |  | Housing | HOUSE-REQ148 | Culture change, Carlisle works on three C's | Won't Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ149 | Shared department budgets, equipment, training, resources | Won't Have |  | developed together with | Finance
Place |  | Housing | HOUSE-REQ149 | Shared department budgets, equipment, training, resources | Won't Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ149 | Shared department budgets, equipment, training, resources | Won't Have |  | requires support from | ICT
Place |  | Housing | HOUSE-REQ150 | VR on the table around staffing | Won't Have | is reliant upon decisions being made by |  | HR & OD
Place |  | Housing | HOUSE-REQ151 | Full commonality in response across the new area | Won't Have |  |  |  | No detail provided
Place |  | Housing | HOUSE-REQ152 | Fully intergated teams and structures | Won't Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ153 | Common contractual arrangements | Won't Have | requires support from |  | Strategic Commisssioning | No detail provided
Place |  | Planning and Building Control | PBC-REQ1 | Recurit and retain staff that will be situated within deliverable geographies across the new authorities | Must Have |  |  |  | No detail provided
Place |  | Planning and Building Control | PBC-REQ2 | New workable schemes of delegation adopted by the new authorities | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ3 | All local plans and supplementary planning documents to be adopted by new authorities | Must Have | has a connection with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ4 | LDS (Local Development Scheme) to be adopted by new authoirities | Must Have | has a connection with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ5 | Shadow authorities to decide committee structure in new authorities | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ6 | Shadow Authority Planning Committee Elections to take place and new chair appointed for both authorities | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ7 | Member training for Planning Committee for-both authorities | Must Have | developed together with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ8 | Street Naming and Numbering - Committee approval of SNN policy in both authorities | Must Have | has a connection with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ9 | Enforcement policies to be adopted by new authorities | Must Have | has a connection with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ10 | Agreed policy in regards to CIL / section 106 (South Lakeland has a CIL but no other authority has one) | Must Have |  | has a connection with | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ10 | Agreed policy in regards to CIL / section 106 (South Lakeland has a CIL but no other authority has one) | Must Have |  | has a connection with | Finance
Place |  | Planning and Building Control | PBC-REQ11 | Pre-app policy to be adopted by the new authorities | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ12 | Functional IT systems for Building Control & Development Management | Must Have | is reliant upon decisions being made by |  | ICT
Place |  | Planning and Building Control | PBC-REQ13 | Access to historic planning records for buiding control, development management and minerals and waste | Must Have | is reliant upon decisions being made by |  | ICT
Place |  | Planning and Building Control | PBC-REQ14 | GIS systems | Must Have | has a connection with |  | ICT
Place |  | Planning and Building Control | PBC-REQ15 | New MoU for joint committees such as partnership boards | Must Have |  |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ16 | Appoint partnership members to AONB boards (Solway Coast, North Pennines & Arnside and Silverdale | Must Have | has a connection with
Place |  | Planning and Building Control | PBC-REQ17 | Statutory Planning Noties Policy needs to be cordinated | Should Have |  |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ18 | Approach to site notices needs to be cordinated | Should Have
Place |  | Planning and Building Control | PBC-REQ19 | Harmonised standard conditions for both authorities | Should Have
Place |  | Planning and Building Control | PBC-REQ20 | Harmonised validation procedures for both authorities | Should Have
Place |  | Planning and Building Control | PBC-REQ21 | Corporate Templates for notices, decisions, delgated reports & committee reports | Should Have | has a connection with
Place |  | Planning and Building Control | PBC-REQ22 | Committee Policy to be agreed (i.e. site visit policy) | Should Have | developed together with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ23 | A new centralised admin protocal for development management and building control in both authorities. These include inboxes and addresses for plannning and building control applications in the new authorities. | Could Have |  |  | ICT
Place |  | Planning and Building Control | PBC-REQ24 | Harmonised local plans for the new authorities | Won't Have | is reliant upon decisions being made by
Place |  | Planning and Building Control | PBC-REQ25 | A harmonised IT system for Development Management and Building Control in the new authorities | Won't Have | is reliant upon decisions being made by |  | ICT
Place |  | Planning and Building Control | PBC-REQ26 | A Harmonised GIS system for the new authorities | Won't Have | ICT - Infrastructure |  | ICT

## Day1 Reqs&Depends (C&D) (hidden)
Day1 Requirements & Inter/Dependencies (Customer and Digital)
|  |  |  | DEFINITIONS: |  |  |  | KEY FOR COMMENTS SECTION:
|  |  |  | Dependency: Reliance on just one other area to address requirement |  |  |  | Question about whether the workstream has been mapped correctly
|  |  |  | Interdependency: Reliance across multiple areas to address requirement |  |  |  | Remaining interdependencies that I cannot map / unsure about mapping to existing workstreams
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency (what is required from elsewhere in the programme?) | Interdependency (numerous interdependencies from elsewhere in the programme) | With | Comment | Date needed by | Approved?
Customer and Digital
Customer and Digital
Customer and Digital
Customer and Digital
Customer and Digital
Customer and Digital
Customer and Digital

## Day1 Requirements (C Enablers) (hidden)
Day 1 Requirements - Corporate Enablers
THEME | WORKSTREAM | REQUIREMENT ID | DAY 1 REQUIREMENTS ( A checklist to ensure the organisation functions both safe&legal and provides the same services as it currently does) | Agreed with dependent workstream? | MOSCOW
CORPORATE ENABLERS | Accountancy and financial planning |  | All info TBC | (Yes/No) | Must have (safe & legal)/ Should have/ could have
| Audit |  | Baselining/as-is complete - day 1 requirements TBC
| Admin & Business Support |  | Baselining/as-is complete - day 1 requirements TBC Business support is the backbone of a lot of the services, interdependencies are high between this service and most others
| Capital Programme |  | Baselining/as-is complete - day 1 requirements TBC
| Comms & Engagement |  | Baselining/as-is complete - day 1 requirements TBC
| Change Mngt & Transformation |  | Baselining/as-is complete - day 1 requirements TBC
| Digital, Service centre & Customer interf. |  | Further on than other workstreams - EY aiding this work
| FOI/SAR Comments, Compliment & Complaints | FOI-REQ1 | Statutory compliance with: FOIA 2000/ EIR 2004/ DPA 2018/ UK GDPR - Data Protection Reform/ Public Records Act 58/67. INSPIRE Regulations / the Re-use of Public Sector Information Regulations 2015 (RPSI). NHS & Local Authority 2009 Care Act. Mental Capacity Consent '3ps' | No | Must have
|  | FOI-REQ2 | Data Protection Officer as SPOC for Information Commissioner Office | No | Must have
|  | FOI-REQ3 | Ensuring registration with Information Commissioner | No | Must have
|  | FOI-REQ4 | Dealing directly with the Local Government and Social Care Ombudsman | No | Must have
|  | FOI-REQ5 | Publishing information and data sets under a Publication Scheme/INSPIRE/RPS | No | Must have
|  | FOI-REQ6 | Ensuring the Complaints Policies and Information Governance Framework are complied with | No | Must have
|  | FOI-REQ7 | Advising on Data Protection | No | Must have
|  | FOI-REQ8 | Responding to complaints and requests | No | Must have
|  | FOI-REQ9 | Ability to make a request for rectification, erasure, restriction, portability of your data under the General Data Protection Regulations (GDPR) // Ability to make requests for CCTV footage //Ability to report data breaches | No | Must have
|  | FOI-REQ10 | FOI request form | No | Must have
|  | FOI-REQ11 | Disclosure Log | No | Must have
|  | FOI-REQ12 | Access to digital and hard records | No | Must have
|  | FOI-REQ13 | SAR Process | No | Must have
|  | FOI-REQ14 | Agree a complaints process. Define scope, stages, escalation, timescales and limitations | No | Must have
| Health & Safety | H&S-REQ1 (Policy) | Corporate H&S Policy. Need to be brought to the attention of all the employees as per the H&S at work act | No | Must have
|  | H&S-REQ2 (The Team) | Access to sufficient resources for competent health and safety advice both general and “industry specific competence” depending on service or service areas | No | Must have
|  | H&S-REQ3 (The Team) | Review of health and safety resources (in terms of current workforce) | No | Must have
|  | H&S-REQ4 (Reporting/ Recording) | Agreed mechanisms for accident and incident reporting, recording and investigation | No | Must have
|  | H&S-REQ5 (Assessing Hazards) | Agreed arrangements for the provisions of suitable and sufficient risk assessment, risk controls and PPE | No | Must have
|  | H&S-REQ6 (Training and Development) | Ensuring the provisions of suitable and sufficient information, Instruction, training and supervision for employees specific to their area of work / working environment | No | Must have
|  | H&S-REQ7 (The Team) | First Aid / Fire Safety Provisions – Equipment, training, appointed First Aid Persons | No | Must have
|  | H&S-REQ8 (Governance) | Compliant workplace and welfare facilities | No | Must have
|  | H&S-REQ9 (The Team) | Agreed consultation mechanisms in place (workers and their TU H&S representatives) | No | Must have
|  | H&S-REQ10 (Delivery Model) | Statutory Health Surveillance for employees – Requirement specific to nature of work | No | Must have
|  | H&S-REQ11 (Delivery Model) | Robust contractor procurement and safety management systems | No | Must have
|  | H&S-REQ12 (Assessing Risk) | Arrangements for Statutory Inspections / Compliance | No | Must have
|  | H&S-REQ13 (The Team) | Provision of specifically assigned Competent Persons | No | Must have
|  | H&S-REQ14 (Assessing Risk) | Approval and notification service for Educational Visits | No | Must have
|  | H&S-REQ15 (Assessing Risk) | Basic statutory compliance | No | Must have
|  | H&S-REQ16 (Governance) | Corporate Insurance | No | Must have
|  | H&S-REQ17 (Governance) | Outline plan for accountability and lead for H&S Governance for the new authorities and establishment of management structures (e.g. H&S Management Board/Group) | No | Should have
|  | H&S-REQ18 (The Team) | Portfolio holder for H & S - Council Members H & S understanding of their roles with regards to H&S | No | Should have
|  | H&S-REQ19 (The Team) | Structural knowledge by Senior Team, Council Members, Manage | No | Should have
|  | H&S-REQ20 (Governance) | Clear longer term understanding of “who” in terms of H&S provisions and monitoring compliance is doing what in new authority | No | Should have
|  | H&S-REQ21 (The Team) | Dedicated H & S Administrative support | No | Should have
|  | H&S-REQ22 (Finance) | Health and Safety budgets for team and for the wider H & S requirements | No | Should have
|  | H&S-REQ23 (Assessing Risk) | Corporate Risk Register and H&S Action plans to identify “higher risk” areas and priority H&S Objectives | No | Should have
|  | H&S-REQ24 (Assessing Risk) | Agreed procedures for ongoing H&S audits, inspection and proactive monitoring | No | Should have
|  | H&S-REQ25 (Comms) | ICT infrastructure to support H&S systems and relevant communications | No | Should have
|  | H&S-REQ26 (Governance) | Mechanisms in place for production of annual H&S report | No | Should have
|  | H&S-REQ27 (Comms) | Appropriate branding | No | Should have
|  | H&S-REQ28 (Training & Development) | Clear H&S champions as part of working groups | No | Could have
|  | H&S-REQ29 (Governance) | Unified H&S Unions working parties | No | Could have
|  | H&S-REQ30 (The Team) | Agreed and recognised competence of H&S specialist list | No | Could have
|  | H&S-REQ31 (Governance) | Audits undertaken by those currently within different authorities | No | Could have
|  | H&S-REQ32 (Finance) | Shared Budgets for better purchasing power | No | Could have
|  | H&S-REQ33 (Finance) | Agreed protocols between merging authorities | No | Could have
|  | H&S-REQ34 (The Team) | Action plan to review current H & S team structures and corporate OH&S arrangements | No | Could have
|  | H&S-REQ35 (Delivery Model) | Review of tasks currently undertaken by H & S Services | No | Could have
|  | H&S-REQ36 (Learning & Development) | Health and Safety Competence Development Framework for employees and managers | No | Could have
|  | H&S-REQ37 (Assessing Risk) | Day one unification of risk assessments and safe working practices for common areas of work | No | Won't have
|  | H&S-REQ38 (Governance) | Unification of Corporate Risk Registers and agreed committee structures / formats | No | Won't have
|  | H&S-REQ39 (Delivery Model) | Universal / shared “Service Providers / external | No | Won't have
|  | H&S-REQ40 (Governance) | Universal providers of facilities contracts | No | Won't have
|  | H&S-REQ41 (Comms) | Electronic Health and Safety management and audit systems | No | Won't have
|  | H&S-REQ42 (The Team) | Risk that current H&S resources, staffing and personnel will be insufficient to cover both unitary authorities | No | Won't have
|  | H&S-REQ43 (Governance) | Long term compliance contracts signed off | No | Won't have
| HR & OD |  | Baselining/as-is complete. Day 1 requirements TBC
| ICT |  | Baselining/as-is complete. Day 1 requirements TBC
| Income Collection |  | Baselining/as-is complete. Day 1 requirements TBC
| Info governance |  | Baselining/as-is complete. Day 1 requirements TBC
| Legal & Democratic |  | Baselining/as-is complete. Day 1 requirements TBC
| Local tax collection & Benefits |  | Baselining/as-is complete. Day 1 requirements TBC
| Pension fund |  | Baselining/as-is complete. Day 1 requirements TBC
| Performance & Intelligence |  | Baselining/as-is complete. Day 1 requirements TBC
| Policy Framework |  | Baselining/as-is complete. Day 1 requirements TBC
| Property, asset strategy & property maint. |  | Baselining/as-is complete. Day 1 requirements TBC
| Risk Managem. & Business Continuity |  | Baselining/as-is complete. Day 1 requirements TBC
| Records Management |  | To populate with day 1 requirements
| Strategic Commiss., procurement & Contract |  | Baselining/as-is complete. Day 1 requirements TBC
| Treasury Managem. & Insurance |  | Baselining/as-is complete. Day 1 requirements TBC

## Day 1 Customer & Digital (hidden)
Day 1 Customer & digital
|  | Service offer | Key metrics | IT systems | Customer and channels | Key partners/suppliers | Day 1 service delivery model | Budget/Staffing/Assets Dis/aggregation | Transition following Day 1 | Transformation ambitions | Exceptions | Other notes | Service Delivery | Organisational Capabilities | People / Organisation | Processes | Tech | Estates / Location | Governance | Users and Stakeholders
|  | e.g. 1. what are the statutory services you will deliver 2. what are the discretionary services you will deliver | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. where does the work get done and who delivers it | e.g. 1. how will the work get done on day 1? 2. The new approach will be defined and implemented… 3. Where is the line drawn between services/themes (hand-offs?)? | e.g. 1. Required Regional structures in place 2. There will be vacancies across the model with a plan for filling these? 3. What is the accepted risk level for vetting? | e.g. 1. Payroll and finance processes updated 2. Inductions to be undertaken for new staff 3. Payment systems in place | e.g. 1. MVP Digital tools aligned to new regions (M) 2. MVP tools developed, tested and deployed (M) 3. Data migration is ready | e.g. 1. Transfer from x to y in place 2. Security of buildings meets security specifications 3. Physical layout of buildings meet security specifications | e.g. 1. Required level of Performance reporting implemented 2. Performance management framework defined and approved 3.Government framework in line with RACI | e.g. All users and staff will be aware of changes and some will relocate on Day 1
CUSTOMER & DIGITAL | Workstream 1
Workstream 2
Workstream 3

## Day1 Requirements & Depen (C&D) (hidden)
Day1 Requirements & Inter/Dependencies (Customer & Digital)
Dependency: Reliance on just one other area to address requirement
Interdependency: Reliance across multiple areas to address requirement
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency | Interdependency | With | Comment | Date needed by | Approved?
|  |  | e.g. AUDIT-REQ1 | e.g. Out Of Hours Service | e.g. Must have/Should have |  |  | e.g. Workstream - Organisational Development & Human Resources |  | e.g. 01/08/2022 | (Yes/No)

## Day 1 - Finance (hidden)
Day 1 Customer & digital
|  | Service offer | Key metrics | IT systems | Customer and channels | Key partners/suppliers | Day 1 service delivery model | Budget/Staffing/Assets Dis/aggregation | Transition following Day 1 | Transformation ambitions | Exceptions | Other notes | Service Delivery | Organisational Capabilities | People / Organisation | Processes | Tech | Estates / Location | Governance | Users and Stakeholders
|  | e.g. 1. what are the statutory services you will deliver 2. what are the discretionary services you will deliver | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. | e.g. where does the work get done and who delivers it | e.g. 1. how will the work get done on day 1? 2. The new approach will be defined and implemented… 3. Where is the line drawn between services/themes (hand-offs?)? | e.g. 1. Required Regional structures in place 2. There will be vacancies across the model with a plan for filling these? 3. What is the accepted risk level for vetting? | e.g. 1. Payroll and finance processes updated 2. Inductions to be undertaken for new staff 3. Payment systems in place | e.g. 1. MVP Digital tools aligned to new regions (M) 2. MVP tools developed, tested and deployed (M) 3. Data migration is ready | e.g. 1. Transfer from x to y in place 2. Security of buildings meets security specifications 3. Physical layout of buildings meet security specifications | e.g. 1. Required level of Performance reporting implemented 2. Performance management framework defined and approved 3.Government framework in line with RACI | e.g. All users and staff will be aware of changes and some will relocate on Day 1
CUSTOMER & DIGITAL | Workstream 1
Workstream 2
Workstream 3

## Day1 Reqs & Depen. (Finance) (hidden)
Day1 Requirements & Inter/Dependencies (Finance)
Dependency: Reliance on just one other area to address requirement
Interdependency: Reliance across multiple areas to address requirement
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency | Interdependency | With | Comment | Date needed by | Approved?
|  |  | e.g. AUDIT-REQ1 | e.g. Out Of Hours Service | e.g. Must have/Should have |  |  | e.g. Workstream - Organisational Development & Human Resources |  | e.g. 01/08/2022 | (Yes/No)

## Day1 Reqs & Depen. (People) (hidden)
Day1 Requirements & Inter/Dependencies (People)
Dependency: Reliance on just one other area to address requirement
Interdependency: Reliance across multiple areas to address requirement
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency | Interdependency | With | Comment | Date needed by | Approved?
|  |  | e.g. AUDIT-REQ1 | e.g. Out Of Hours Service | e.g. Must have/Should have |  |  | e.g. Workstream - Organisational Development & Human Resources |  | e.g. 01/08/2022 | (Yes/No)

## Day1 Reqs & Depen. (Place) (hidden)
Day1 Requirements & Inter/Dependencies (Place)
Dependency: Reliance on just one other area to address requirement
Interdependency: Reliance across multiple areas to address requirement
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency | Interdependency | With | Comment | Date needed by | Approved?
|  |  | e.g. AUDIT-REQ1 | e.g. Out Of Hours Service | e.g. Must have/Should have |  |  | e.g. Workstream - Organisational Development & Human Resources |  | e.g. 01/08/2022 | (Yes/No)

## Day1 Reqs & Depen. (ICT) (hidden)
Day1 Requirements & Inter/Dependencies (ICT)
Dependency: Reliance on just one other area to address requirement
Interdependency: Reliance across multiple areas to address requirement
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency | Interdependency | With | Comment | Date needed by | Approved?
|  |  | e.g. AUDIT-REQ1 | e.g. Out Of Hours Service | e.g. Must have/Should have |  |  | e.g. Workstream - Organisational Development & Human Resources |  | e.g. 01/08/2022 | (Yes/No)

## Risk Register (hidden)
PROJECT RISK REGISTER |  |  | Current overall Project Risk RAG Rating: | Amber | Some concerns with one or more risk controls but confident that actions taken will address problem.
Target Score Assessment
Project Name: LGR Place Theme |  |  |  |  | Risk Register | [6 empty] | Red | Significant concerns
[12 empty] | Amber | Some concerns but confident that actions taken will address problem.
Version No: 2 | [11 empty] | Green | On schedule to meet target score by target date.
[12 empty] | Met Target | The target risk score has been reached.
Risk No. | Author | Date Identified | Risk Description | Likelihood | Impact | Risk Score (LxI) | Risk Level | Risk Treatments | Progress with mitigation | Target Risk Score | Target Date | Prospect of hitting target score | Risk Owner | Date Reviewed | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
Overall Project Risk RAG Rating Key: |  |  |  |  | Risk Matrix
Red | Significant concerns with one or more risk controls. Requires Board consideration / immediate action |  |  |  |  | 1 | 2 | 3 | 4 | 5
Amber | Some concerns with one or more risk controls but confident that actions taken will address problem. |  |  |  | 5 | 5 | 10 | 15 | 20 | 25
Green | On schedule to meet target score by target date. |  |  |  | 4 | 4 | 8 | 12 | 16 | 20
[5 empty] | 3 | 3 | 6 | 9 | 12 | 15
[5 empty] | 2 | 2 | 4 | 6 | 8 | 10
[5 empty] | 1 | 1 | 2 | 3 | 4 | 5
Risk Level Tolerances
[5 empty] | Band |  |  | Risk Treatment
[5 empty] | High 15-25 (Red Risks) |  |  | Risks at this level are so significant that risk treatment is mandatory
[5 empty] | Medium 6-12 (Amber Risks) |  |  | Risks at this level require a cost/benefit analysis to take place to determine the most appropriate risk treatment
[5 empty] | Low 1-5 (Green Risks) |  |  | Risks at this level can be regarded as negligible, or so small that no risk treatment is required
Note on F1: Grainger-Barnes, Helen D: Key to rating included at the bottom of the spreadsheet
Note on B7: Insert Initials of person identifying the risk
Note on C7: Insert the date you first identified the risk
Note on D7: It is important that the risk is clearly described, this will include what the event or situation may be, what has caused the risk and what the impact will be to the project objectives.
Note on E7: Choose a score from one to five from the Risk Assessment Methodology, located on the Methodology sheet. You should consider all existing controls whilst estimating this score.
Note on F7: Choose a score from one to five from the Risk Assessment Methodology, in the Methodology sheet. You should consider all existing controls whilst estimating this score.
Note on G7: This represents the current likelihood score multiplied by the impact score.
Note on I7: Contains details of the mitigation treatments that you intend to put in place to reduce the risk to the target score in the future. These are new controls in addition to any existing measures
Note on J7: Gives details of progress with the mitigation treatments that have taken place or are taking place to reduce the risk to the target score.
Note on K7: This shows the levels of risk that you would consider to be acceptable and when reached would require no further action other than monitoring.
Note on L7: The date that you consider you will have completed the mitigation treatments and the risk will reach its target score
Note on M7: Provides an indication of how well or otherwise the mitigation treatments are progressing to reduce the risk to the target score by the target date. This box is a visual indicator using the key guide above.
Note on N7: This is the person who will be ultimately responsible for ensuring that the risk gets to the target score. This should preferably be one person who takes overall responsibility for the risk. However there may be other individuals that mitigation treatments will be delegated to.
Note on O7: The date when the risk last underwent a full review to determine whether the risk scores should remain the same, the treatments are working and the prospects of reaching the target score are correct.
Note on P7: Whether the risk is open or closed

## Issues (hidden)
PROJECT ISSUES |  |  | Current overall Project Issue RAG Rating: | Amber | Some concerns with one or more issue controls but confident that actions taken will address problem.
Target Score Assessment
Project Name: |  |  |  |  | Issues | [6 empty] | Red | Significant concerns
Prepared by: | [11 empty] | Amber | Some concerns but confident that actions taken will address problem.
Version No: | [11 empty] | Green | On schedule to meet target score by target date.
[12 empty] | Met Target | The target issue score has been reached.
Issue No. | Author | Date Identified | Issue Description | Likelihood | Impact | Issue Score (LxI) | Issue Level | Issue Treatments | Progress with mitigation | Target Issue Score | Target Date | Prospect of hitting target score | Issue Owner | Date Reviewed | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
Overall Project Issue RAG Rating Key: |  |  |  |  | Issue Matrix
Red | Significant concerns with one or more issue controls. Requires Board consideration / immediate action |  |  |  |  | 1 | 2 | 3 | 4 | 5
Amber | Some concerns with one or more issue controls but confident that actions taken will address problem. |  |  |  | 5 | 5 | 10 | 15 | 20 | 25
Green | On schedule to meet target score by target date. |  |  |  | 4 | 4 | 8 | 12 | 16 | 20
[5 empty] | 3 | 3 | 6 | 9 | 12 | 15
[5 empty] | 2 | 2 | 4 | 6 | 8 | 10
[5 empty] | 1 | 1 | 2 | 3 | 4 | 5
Issue Level Tolerances
[5 empty] | Band |  |  | Issue Treatment
[5 empty] | High 15-25 (Red Risks) |  |  | Issues at this level are so significant that issue treatment is mandatory
[5 empty] | Medium 6-12 (Amber Risks) |  |  | Issues at this level require a cost/benefit analysis to take place to determine the most appropriate risk treatment
[5 empty] | Low 1-5 (Green Risks) |  |  | Issues at this level can be regarded as negligible, or so small that no issue treatment is required
Note on F1: Grainger-Barnes, Helen D: Key to rating included at the bottom of the spreadsheet
Note on B7: Insert Initials of person identifying the risk
Note on C7: Insert the date you first identified the risk
Note on D7: It is important that the risk is clearly described, this will include what the event or situation may be, what has caused the risk and what the impact will be to the project objectives.
Note on E7: Choose a score from one to five from the Risk Assessment Methodology, located on the Methodology sheet. You should consider all existing controls whilst estimating this score.
Note on F7: Choose a score from one to five from the Risk Assessment Methodology, in the Methodology sheet. You should consider all existing controls whilst estimating this score.
Note on G7: This represents the current likelihood score multiplied by the impact score.
Note on I7: Contains details of the mitigation treatments that you intend to put in place to reduce the risk to the target score in the future. These are new controls in addition to any existing measures
Note on J7: Gives details of progress with the mitigation treatments that have taken place or are taking place to reduce the risk to the target score.
Note on K7: This shows the levels of risk that you would consider to be acceptable and when reached would require no further action other than monitoring.
Note on L7: The date that you consider you will have completed the mitigation treatments and the risk will reach its target score
Note on M7: Provides an indication of how well or otherwise the mitigation treatments are progressing to reduce the risk to the target score by the target date. This box is a visual indicator using the key guide above.
Note on N7: This is the person who will be ultimately responsible for ensuring that the risk gets to the target score. This should preferably be one person who takes overall responsibility for the risk. However there may be other individuals that mitigation treatments will be delegated to.
Note on O7: The date when the risk last underwent a full review to determine whether the risk scores should remain the same, the treatments are working and the prospects of reaching the target score are correct.
Note on P7: Whether the risk is open or closed

## Day1 Reqs&Depends (Place )
Day1 Requirements & Inter/Dependencies (Place)
|  |  |  | DEFINITIONS: |  |  |  | KEY FOR COMMENTS SECTION:
|  |  |  | Dependency: Reliance on just one other area to address requirement |  |  |  | Question about whether the workstream has been mapped correctly
|  |  |  | Interdependency: Reliance across multiple areas to address requirement |  |  |  | Remaining interdependencies that I cannot map / unsure about mapping to existing workstreams
Theme | Cluster | Service / Work Package | Requirement ID | Day 1 Requirement | Priority/ MoSCoW | Dependency (what is required from elsewhere in the programme?) | Interdependency (numerous interdependencies from elsewhere in the programme) | With | Comment | Date needed by | Approved?
Place |  | Waste | WASTE-REQ1 | Staff able to do the job, these will need contracts | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ2 | Be able to dispose of waste | Must have | developed together with |  | Fleet
Place |  | Waste | WASTE-REQ3 | Have appropriate vehicles that are under an O’Licence, insured | Must have | has a connection with |  | Transport
Place |  | Waste | WASTE-REQ4 | Have access to fuel | Must have | has a connection with |  | Finance
Place |  | Waste | WASTE-REQ5 | Be able to access routes and in cab data exchange | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ6 | Customer interface in the way residents are used to contacting us now, this may require access to each-others’ systems | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ6 | Customer interface in the way residents are used to contacting us now, this may require access to each-others’ systems | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ7 | Essential outputs for householders (i.e. Collection calendars) | Must have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ8 | Clear lines of management / accountability and ability to redirect resources to support priority services eg from other operational services | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ9 | Priority access to fleet maintenance and support | Must have | requires support from |  | Fleet
Place |  | Waste | WASTE-REQ10 | Officers authorised to place orders etc | Must have | developed together with |  | Finance
Place |  | Waste | WASTE-REQ11 | Team of staff empowered and confident to make decisions | Must have | developed together with |  | HR & OD
Place |  | Waste | WASTE-REQ12 | Hosted arrangement - Clear transfer of the services which would sit within Host Authority. Staffing, communication routes, Officer/Member governance confirmed. | Must have | requires support from |  | All services - all employees
Place |  | Waste | WASTE-REQ13 | Waste data collection and submission resourcing and arrangements confirmed (ie. WasteDataFlow). | Must have | developed together with |  | ICT
Place |  | Waste | WASTE-REQ14 | Governance Model | Must have | developed together with |  | All services - all employees
Place |  | Waste | WASTE-REQ15 | Duly appointed Shareholder Group for AWSL (Governance) and Partnering Board – a contractual requirement | Must have | developed together with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ16 | Methodology for valuing fuel stock for example as at 31/3/23 | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ17 | IT must work e.g. VPN, in-cab devices, | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ18 | DVLA to be advised of vehicle responsibility – Road Fund licence V5 – who will be responsible for taxing the vehicles 1/4/23 | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ19 | LOLER – bin lifts/tail lifts - are we using one supplier for Cumberland | Must have | requires further discussion with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ20 | Ability to check licences - internal or external | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ21 | Tachograph analysis – RHA/FTA | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ22 | Trade Waste Contracts assigned to Cumberland | Must have | developed together with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ23 | Contingency offtakers in Cumberland e.g. bulky waste to Barrow in the past | Must have
Place |  | Waste | WASTE-REQ24 | Decision on AWSL new name if any | Must have
Place |  | Waste | WASTE-REQ25 | Waste Carriers Licence currently in the name of AWSL | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ26 | An understanding about the ownership of CWM | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ27 | Scheme of financial delegation for officers | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ28 | AWSL, CWM and Tivoli (waste element) contracts assigned to Cumberland | Must have | requires further discussion with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ29 | Portfolio Holder in place | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ30 | Alignment on fees and charges | Must have | requires further discussion with |  | Finance
Place |  | Waste | WASTE-REQ31 | Staffing and therefore reporting structure to be in place | Must have | requires further discussion with |  | HR & OD
Place |  | Waste | WASTE-REQ32 | Cumberland branding on RCVs | Must have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ33 | Standardisation of Customer Service roles across Cumberland | Must have |  | requires support from | HR & OD
Place |  | Waste | WASTE-REQ33 | Standardisation of Customer Service roles across Cumberland | Must have |  | developed together with | Customer & Digital
Place |  | Waste | WASTE-REQ34 | Will Cumberland provide H&S advice to AWSL? | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ35 | Will Cumberland provide current SLA services to AWSL? | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ36 | Access to data – ICT systems/Sharepoint | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ37 | Waste, Green Waste & Recycling collections - Front-line services must happen on day one as they did in March 2022 | Must have | requires support from |  | All services - all employees
Place |  | Waste | WASTE-REQ38 | Vehicles must be legal & safe. Must be insured, serviced & MoT’d. | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ39 | Fuel - Fuel cards or supplies must be available for vehicles | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ40 | Insurance - Vehicles must be insured | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ41 | Vehicle Accident Packs - Must be up-dated with new insurance details etc | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ42 | Bring site emptying - Recycling banks must be emptied. | Must have
Place |  | Waste | WASTE-REQ43 | Waste disposal - Transfer Stations must be open and accepting materials | Must have | developed together with |  | HR & OD
Place |  | Waste | WASTE-REQ44 | Environmental Permits for Ecclerigg & Ulverston Waste Transfer Stations - Must be transferred to WandF. May be covered by the Change Order. Possible joint meeting with CCC, EDC, BBC & EA to resolve. | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ45 | Staff - We must have staff in place, paid, covered by insurance, qualified to do their jobs. | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ46 | Sickness & Holidays - Must be in place for non-desk-based staff. | Must have |  | requires support from | HR & OD
Place |  | Waste | WASTE-REQ46 | Sickness & Holidays - Must be in place for non-desk-based staff. | Must have |  | Requires futher dicussion with | Finance
Place |  | Waste | WASTE-REQ47 | Credit cards - As required, for emergency use. Possibly retain pre-WaF cards. | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ48 | IT systems - Laptops and phone must work. | Must have |  | requires support from | ICT
Place |  | Waste | WASTE-REQ48 | Software - Core MS Office systems must work. Content must have transferred. Any specific systems must work. | Must have |  | requires support from | ICT
Place |  | Waste | WASTE-REQ49 | Software - Core MS Office systems must work. Content must have transferred. Any specific systems must work. | Must have |  |  | Finance
Place |  | Waste | WASTE-REQ50 | Utilities - All depots & buildings must have gas, electric, water etc. | Must have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ50 | Utilities - All depots & buildings must have gas, electric, water etc. | Must have |  | requires support from | Finance
Place |  | Waste | WASTE-REQ51 | Payroll - Processes in place to pay staff and process overtime or other claims. | Must have |  | requires support from | HR & OD
Place |  | Waste | WASTE-REQ51 | Payroll - Processes in place to pay staff and process overtime or other claims. | Must have |  | developed together with | Finance
Place |  | Waste | WASTE-REQ52 | Communications - Staff and the public must know what is going on. May require access to each other's systems | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ52 | Communications - Staff and the public must know what is going on. May require access to each other's systems | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ53 | Website - Website content must be transferred & checked. Collection information (calendars) must be available. | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ53 | Website - Website content must be transferred & checked. Collection information (calendars) must be available. | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ54 | Processes - Systems must be in place to log missed collections, bin requests and queries; and allocate to the correct operational area. | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ55 | Bulky waste - Requests must be received and forwarded to the correct contractor. | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ55 | Bulky waste - Requests must be received and forwarded to the correct contractor. | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ56 | Clinical waste - Requests must be received and forwarded to the correct contractor. | Must have |  | requires support from | Customer & Digital
Place |  | Waste | WASTE-REQ56 | Clinical waste - Requests must be received and forwarded to the correct contractor. | Must have |  | developed together with | ICT
Place |  | Waste | WASTE-REQ57 | Hosted arrangement - Clear transfer of the services which would sit within Host Authority. Staffing, communication routes, Officer/Member governance confirmed. | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ58 | Waste data collection and submission resourcing and arrangements confirmed (ie. WasteDataFlow). | Must have | developed together with |  | ICT
Place |  | Waste | WASTE-REQ59 | Branded Calendars are essential from day one | Must have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ60 | Clear lines of Management and accountability – to be able to redirect resources if needed | Must have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ61 | Waste Carrier License's | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ62 | Understanding ownership of CWM | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ63 | Contract assigned to a correct legal entity – mechanism to be agreed (legal advice required) | Must have |  | requires support from | Strategic Commissioning
Place |  | Waste | WASTE-REQ63 | Contract assigned to a correct legal entity – mechanism to be agreed (legal advice required) | Must have |  | developed together with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ64 | Authority representative to be agreed and Governance between Contractor and Authorities | Must have |  | requires support from | Legal & Democratic Services
Place |  | Waste | WASTE-REQ64 | Authority representative to be agreed and Governance between Contractor and Authorities | Must have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ65 | Up to date Authorised Vehicle List for new authorities – AVL to ensure no end dates of 31 March/April 2023 | Must have |  | requires support from | Fleet
Place |  | Waste | WASTE-REQ65 | Up to date Authorised Vehicle List for new authorities – AVL to ensure no end dates of 31 March/April 2024 | Must have |  | developed together with | Transport
Place |  | Waste | WASTE-REQ65 | Up to date Authorised Vehicle List for new authorities – AVL to ensure no end dates of 31 March/April 2025 | Must have |  | developed together with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ66 | New authorities to understand AVL procedure | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ67 | Agreed process for updating and issuing AVL (currently CCC Service Centre) | Must have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ68 | Waste transfer notes for the 2 authorities | Must have | developed together with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ69 | Agreement on HWRC permit system – is it run by one authority or 2? | Must have |  | requires further discussion with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ70 | Agreement on use of HWRCs – can all residents use all sites in Cumberland and Westmorland and Furness? | Must have |  | requires support from | Assets
Place |  | Waste | WASTE-REQ70 | Agreement on use of HWRCs – can all residents use all sites in Cumberland and Westmorland and Furness? | Must have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ71 | Agree scope of Helpline and contact arrangements – confirm telephone number, training for helpline team. | Must have |  | requires support from | Strategic Commissioning
Place |  | Waste | WASTE-REQ71 | Agree scope of Helpline and contact arrangements – confirm telephone number, training for helpline team. | Must have |  | developed together with | Customer & Digital
Place |  | Waste | WASTE-REQ72 | Reporting lines to be communicated to RCL | Must have
Place |  | Waste | WASTE-REQ73 | Agreement to pay CCC invoices for the period to 31 March 2023 and new authorities from 01 April 2023 | Must have |  | requires further discussion with | Finance
Place |  | Waste | WASTE-REQ74 | Inter Authority Agreement in place to process payments | Must have |  | requires support from | Finance
Place |  | Waste | WASTE-REQ74 | Inter Authority Agreement in place to process payments | Must have |  | requires support from | Strategic Commissioning
Place |  | Waste | WASTE-REQ75 | How to deal with CCC legacy issues: Accrual/provision | Must have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ76 | Responsibilities for Waste Data Flow to be agreed between new authorities (currently districts for recycling/bring sites and CCC for residua) | Must have |  | requires support from | ICT
Place |  | Waste | WASTE-REQ76 | Responsibilities for Waste Data Flow to be agreed between new authorities (currently districts for recycling/bring sites and CCC for residua) | Must have |  | developed together with | All services - all employees
Place |  | Waste | WASTE-REQ77 | Budgets to be set | Must have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ78 | Access to data – ICT systems/Sharepoint | Must have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ79 | Bulky waste collection | Should have
Place |  | Waste | WASTE-REQ80 | Charges for replacement receptacles | Should have | requires support from |  | Finance
Place |  | Waste | WASTE-REQ80 | Charges for replacement receptacles |  |  | requires support from | Communications and Engagement
Place |  | Waste | WASTE-REQ81 | Consistency in uniform / PPE / badging etc | Should have | requires support from |  | Communications and Engagement
Place |  | Waste | WASTE-REQ82 | Vehicle livery | Should have | requires support from |  | Fleet
Place |  | Waste | WASTE-REQ83 | Single approach to recruitment, selection and training of new staff starting from 01 April 2023 on common T+Cs, salaries etc | Should have | requires support from |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ84 | Consistency in policies and procedures i.e. assisted collections, collection of side waste, missed collections | Should have |  | requires support from | Legal & Democratic Services
Place |  | Waste | WASTE-REQ84 | Consistency in policies and procedures i.e. assisted collections, collection of side waste, missed collections | Should have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ85 | Combined service budgets – clear lines of responsibility | Should have |  | requires support from | Finance
Place |  | Waste | WASTE-REQ86 | Office locations agreed | Should have |  | developed together with | Assets
Place |  | Waste | WASTE-REQ86 | Office locations agreed | Should have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ87 | Agreed trade tipping rates | Should have | developed together with |  | Finance
Place |  | Waste | WASTE-REQ88 | Better understanding of Renewi policies that effect the waste collection element of Cumberland | Should have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ89 | Agreement on how to handle complaints and FOIs | Should have | requires further discussion with |  | Customer & Digital
Place |  | Waste | WASTE-REQ90 | Data - Systems should be in place to record data for the new authority. Must happen by end 1st month. | Should have | developed together with |  | ICT
Place |  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | requires support from | Legal & Democratic Services
Place |  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | developed together with | HR & OD
Place |  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | developed together with | Strategic Commissioning
Place |  | Waste | WASTE-REQ91 | Review Consistency – Fees and Charges/Branding PPE and Vehicles/Staff - recruitment – training – T&Cs salaries / Policies and Procedures | Should have |  | developed together with | Communications and Engagement
Place |  | Waste | WASTE-REQ92 | A better understanding of the contract for the Disposal element of the work | Should have | requires further discussion with |  | Strategic Commissioning
Place |  | Waste | WASTE-REQ93 | Consistency in salaries for operational staff – supervisors / loaders / drivers etc | Could have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ94 | Potential to share resources eg at management / supervisory level | Could have | requires further discussion with |  | HR & OD
Place |  | Waste | WASTE-REQ95 | Potential to share vehicles and other resources | Could have |  | requires further discussion with | Fleet
Place |  | Waste | WASTE-REQ95 | Potential to share vehicles and other resources | Could have |  | has a connection with | Transport
Place |  | Waste | WASTE-REQ96 | Agreed position towards membership of national sector organisations and agreement on first point of contact (ie. LARAC, NAWDO, etc) | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ97 | A move towards consistency of IT use | Could have | requires further discussion with |  | ICT
Place |  | Waste | WASTE-REQ98 | An understanding about how current trade waste contracts could possibly be transferred to CWM | Could have |  | requires further discussion with | Strategic Commissioning
Place |  | Waste | WASTE-REQ98 | An understanding about how current trade waste contracts could possibly be transferred to CWM | Could have |  | requires support from | Legal & Democratic Services
Place |  | Waste | WASTE-REQ99 | Standardised H&S procedures e.g. near misses, gate checks, seat belt checks, crew engagement, safety reps | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ100 | ICT – access to Scada system for closed landfill | Could have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ101 | What will permit scheme look like? Pedestrian and Annual Permits? | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ102 | Policies - Existing policies transfer by area. Some policies could have been aligned (closed lid, side waste, lane end). | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ103 | Processes - Some processes could be aligned (assisted collections, requests for larger bins). | Could have
Place |  | Waste | WASTE-REQ104 | National Waste Strategy - Depends on timing of announcement and required actions. | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ105 | Re-branding of PPE - Some could have been done. Potential for hybrid clothing (SLDC fleece, WaF coat etc). | Could have | requires further discussion with |  | Communications and Engagement
Place |  | Waste | WASTE-REQ106 | Agreed position towards membership of national sector organisations and agreement on first point of contact (ie. LARAC, NAWDO, etc) | Could have
Place |  | Waste | WASTE-REQ107 | H&S and Performance, how that is monitored within Westmorland and Furness | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ108 | Awareness training for all waste service employees | Could have | requires support from |  | HR & OD
Place |  | Waste | WASTE-REQ109 | Environment Agency Permit transfer/UU discharge consents to legal entity (is there a requirement to apply or is this covered by the SCO?) | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ110 | Ability to pay EA subsistence fees for closed landfill from 01 April 2023 | Could have |  | requires support from | Finance
Place |  | Waste | WASTE-REQ110 | Ability to pay EA subsistence fees for closed landfill from 01 April 2023 | Could have |  | requires further discussion with | Strategic Commissioning
Place |  | Waste | WASTE-REQ111 | DCF registration – currently CWM | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ112 | Approach to branding strategy to be agreed and position on Performance Framework to be set out (eg how long CCC branding can remain in place before deductions apply) signs and PPE for site operatives | Could have |  | requires further discussion with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ112 | Approach to branding strategy to be agreed and position on Performance Framework to be set out (eg how long CCC branding can remain in place before deductions apply) signs and PPE for site operatives | Could have |  | developed together with | Customer & Digital
Place |  | Waste | WASTE-REQ113 | Agreement on paying royalty/rents – currently sitting with waste team | Could have | requires further discussion with |  | Finance
Place |  | Waste | WASTE-REQ114 | New authorities to brief CWM site operatives – clear and unambiguous message about what the changes mean for the HWRC sites and customers | Could have |  | requires further discussion with | HR & OD
Place |  | Waste | WASTE-REQ114 | New authorities to brief CWM site operatives – clear and unambiguous message about what the changes mean for the HWRC sites and customers | Could have |  | developed together with | Legal & Democratic Services
Place |  | Waste | WASTE-REQ115 | Commercial gate fees to be agreed with new authorities (currently only Copeland and Allerdale) | Could have | requires further discussion with |  | Finance
Place |  | Waste | WASTE-REQ116 | Agreement on policies eg charities, side waste | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ117 | Schedule of assets for the new authorities (MBT, HWRC, closed landfill) | Could have | requires support from |  | Assets
Place |  | Waste | WASTE-REQ118 | ICT – access to Scada system for closed landfill | Could have | requires support from |  | ICT
Place |  | Waste | WASTE-REQ119 | What will permit scheme look like? Pedestrian and Annual Permits? | Could have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ119 | What will permit scheme look like? Pedestrian and Annual Permits? | Could have |  | has a connection with | Customer & Digital
Place |  | Waste | WASTE-REQ120 | Consistency in service standards | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ121 | Consistency in service design | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ122 | Consistency towards commercial waste collections | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ123 | Waste and Recycling policy alignment | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ124 | Consistency in collection frequency | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ125 | Consistency in container type and size | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ126 | Depot rationalisation/location | Won't have |  | requires support from | Assets
Place |  | Waste | WASTE-REQ126 | Depot rationalisation/location | Won't have |  | developed together with | Waste
Place |  | Waste | WASTE-REQ127 | Re-routing and re-rounding following removal of boundaries | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ128 | Efficient direct delivery from the North of Allerdale to Hespin Wood but could have! | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ129 | Decision on in-house v LATCo model | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ130 | Opportunity to rationalise/standardise Bring Banks | Won't have | requires support from |  | Waste
Place |  | Waste | WASTE-REQ131 | Consistency in service standards | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ132 | Consistency in service design | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ133 | Consistency towards commercial waste collections | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ134 | Re-branding of bins & boxes - Not urgent, can be done as new items, bins etc are ordered. | Won't have | requires support from |  | Communications & Engagement
Place |  | Waste | WASTE-REQ134 | Re-branding of vehicles - Not urgent, can be done as new vehicles are ordered or as prioritised. | Won't have | requires support from |  | Communications & Engagement
Place |  | Waste | WASTE-REQ135 | In-cab systems - Too complex to introduce by day 1. | Won't have | requires further discussion with |  | ICT
Place |  | Waste | WASTE-REQ136 | Round changes - Any round or route changes must be embedded by December 2022. | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ137 | Waste and Recycling Policy alignment and Consistency in collection frequency and containers | Won't have | requires further discussion with |  | Waste
Place |  | Waste | WASTE-REQ138 | Reviewed Bring Sites within Westmorland and Furness | Won't have | requires further discussion with |  | Assets
Place |  | Waste | WASTE-REQ139 | Agreement on enforcement powers, eg suspected trade waste abuse at HWRCs | Won't have | requires further discussion with |  | Legal & Democratic Services
Place |  | Waste | WASTE-REQ140 | New HWRC permit scheme | Won't have | requires further discussion with |  | Strategic Commissioning
Place |  | Housing | HOUSE-REQ1 | Budgets & managing performance within departments, approval limits established, performance reporting in place | Must Have | is reliant upon decisions being made by and requires support from |  | Finance
Place |  | Housing | HOUSE-REQ2 | Out Of Hours Service | Must Have |  | Place Theme - Housing | requires support from
Place |  | Housing | HOUSE-REQ2 | Out Of Hours Service | Must Have |  | is reliant upon decisions being made by and requires support from | Housing
Place |  | Housing | HOUSE-REQ3 | Out Of Hours Service | Must Have |  | is reliant upon decisions being made by and requires support from | HR & OD
Place |  | Housing | HOUSE-REQ4 | Out Of Hours Service | Must Have |  | is reliant upon decisions being made by and requires support from | ICT
Place |  | Housing | HOUSE-REQ5 | Out Of Hours Service | Must Have |  | is reliant upon decisions being made by and requires support from | Customer & Digital
Place |  | Housing | HOUSE-REQ6 | Branded Website with links and Duty to Refer emails | Must Have |  | Requires support from | ICT
Place |  | Housing | HOUSE-REQ6 | Branded Website with links and Duty to Refer emails | Must Have |  | developed together with | Customer & Digital
Place |  | Housing | HOUSE-REQ6 | Branded Website with links and Duty to Refer emails | Must Have |  | developed together with | Communications and Engagement
Place |  | Housing | HOUSE-REQ7 | Fees & Charges should align | Must Have | is reliant upon decisions being made by |  | Finance
Place |  | Housing | HOUSE-REQ7 | Essential standard policies for statutory services, e.g. DFG | Must Have | is reliant upon decisions being made by |  | Strategic Commissioning
Place |  | Housing | HOUSE-REQ8 | Essential standard policies for statutory services, e.g. DFG | Must Have |  | developed together with | Finance
Place |  | Housing | HOUSE-REQ9 | Essential standard policies for statutory services, e.g. DFG | Must Have |  | developed together with | Public Protection
Place |  | Housing | HOUSE-REQ10 | Essential standard policies for statutory services, e.g. DFG | Must Have |  | developed together with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ11 | IT relevant to service - Locata. Flare, Civica CBL, Northgate, Idox, Anite, Info at work, Civicare, HIA foundations case manager, Abavus my council services, Ferret, Case management systems. Flare is needed but may not be fuctioning by vesting day. | Must have |  | developed together with | ICT
Place |  | Housing | HOUSE-REQ11 | IT relevant to service - Locata. Flare, Civica CBL, Northgate, Idox, Anite, Info at work, Civicare, HIA foundations case manager, Abavus my council services, Ferret, Case management systems. Flare is needed but may not be fuctioning by vesting day. | Must have |  | requires support from | Customer & Digital
Place |  | Housing | HOUSE-REQ12 | IT relevant to service - Locata. Flare, Civica CBL, Northgate, Idox, Anite, Info at work, Civicare, HIA foundations case manager, Abavus my council services, Ferret, Case management systems. Flare is needed but may not be fuctioning by vesting day. | Must have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ13 | Branding, name badges and ID for stat visits | Must Have | requires support from |  | Communications and Engagement
Place |  | Housing | HOUSE-REQ14 | Core Support Services such as: Finance, Business Support, Legal, HR & IT. Able to recruit. | Must Have | requires support from |  | All services - all employees
Place |  | Housing | HOUSE-REQ14 | Core Support Services such as: Finance, Business Support, Legal, HR & IT. Able to recruit. | Must Have |  | developed together with | Finance
Place |  | Housing | HOUSE-REQ14 | Core Support Services such as: Finance, Business Support, Legal, HR & IT. Able to recruit. | Must Have |  | developed together with | ICT
Place |  | Housing | HOUSE-REQ14 | Core Support Services such as: Finance, Business Support, Legal, HR & IT. Able to recruit. | Must Have |  | developed together with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ15 | Supported Accomodation Contract/Grant Agreements | Must Have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ15 | Supported Accomodation Contract/Grant Agreements | Must Have |  | developed together with | HR & OD
Place |  | Housing | HOUSE-REQ15 | Supported Accomodation Contract/Grant Agreements | Must Have |  | developed together with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ16 | Contractor relationships and processes need to continue for day one. | Must Have |  | is reliant upon decisions being made by | Strategic Commissioning
Place |  | Housing | HOUSE-REQ16 | Contractor relationships and processes need to continue for day one. | Must Have |  | is reliant upon decisions being made by | Adults
Place |  | Housing | HOUSE-REQ17 | DA Crisis contact numbers | Must Have | requires further discussion with | Communications & Engagement | developed together with
Place |  | Housing | HOUSE-REQ18 | CBL Fully operational | Must Have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ18 | CBL Fully operational | Must Have |  | requires support from | ICT
Place |  | Housing | HOUSE-REQ18 | CBL Fully operational | Must Have |  | requires support from | developed together with
Place |  | Housing | HOUSE-REQ19 | Consitution for Officers delegations | Must Have |  | is reliant upon decisions being made by | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ19 | Consitution for Officers delegations | Must Have |  | is reliant upon decisions being made by | ICT
Place |  | Housing | HOUSE-REQ19 | Consitution for Officers delegations | Must Have |  | is reliant upon decisions being made by | Customer & Digital
Place |  | Housing | HOUSE-REQ20 | Customers can dial in and email, self serve on day 1 - different legacy council has different triage proesses and that needs to be maintained for day 1 | Must Have | requires support from |  | Communications & Engagement
Place |  | Housing | HOUSE-REQ21 | Executive functions to take reports | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ21 | Executive functions to take reports | Must Have |  | is interdependent with | Finance - Benefit Realisation
Place |  | Housing | HOUSE-REQ21 | Executive functions to take reports | Must Have |  | is interdependent with | ICT
Place |  | Housing | HOUSE-REQ22 | DFG funding payments, approvals, financial delegations. | Must Have | requires support from |  | Finance
Place |  | Housing | HOUSE-REQ22 | DFG funding payments, approvals, financial delegations. | Must Have |  | is interdependent with | Communications and Engagement
Place |  | Housing | HOUSE-REQ22 | DFG funding payments, approvals, financial delegations. | Must Have |  | is interdependent with | Community/Localism
Place |  | Housing | HOUSE-REQ22 | DFG funding payments, approvals, financial delegations. | Must Have |  | is interdependent with | Public Protection
Place |  | Housing | HOUSE-REQ23 | Process for dealing with homeless appeals / approvals | Must Have |  | is reliant upon decisions being made by | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ24 | Process for dealing with homeless appeals / approvals | Must Have |  | is interdependent with | Finance
Place |  | Housing | HOUSE-REQ25 | Green homes grant structures / team | Must Have | is reliant upon decisions being made by |  | Finance
Place |  | Housing | HOUSE-REQ25 | Green homes grant structures / team | Must Have | is reliant upon decisions being made by | is interdependent with | ICT
Place |  | Housing | HOUSE-REQ26 | Government delta returns & HCLIC need to be possible. (Flag discussion around aggregation of returns for new council). | Must Have | requires support from | ICT - Service Continuity | ICT - Service Continuity
Place |  | Housing | HOUSE-REQ26 | Government delta returns & HCLIC need to be possible. (Flag discussion around aggregation of returns for new council). | Must Have | requires support from |  | Adults
Place |  | Housing | HOUSE-REQ26 | Government delta returns & HCLIC need to be possible. (Flag discussion around aggregation of returns for new council). | Must Have |  |  | ICT
Place |  | Housing | HOUSE-REQ26 | Government delta returns & HCLIC need to be possible. (Flag discussion around aggregation of returns for new council). | Must Have |  |  | Children's
Place |  | Housing | HOUSE-REQ27 | procedure for referrals from OTs and Health absed childrens OT need to be agreed and tested | Must Have | is reliant upon decisions being made by |  | Public Health
Place |  | Housing | HOUSE-REQ27 | procedure for referrals from OTs and Health absed childrens OT need to be agreed and tested | Must Have |  | is interdependent with | Communications and Engagement
Place |  | Housing | HOUSE-REQ27 | procedure for referrals from OTs and Health absed childrens OT need to be agreed and tested | Must Have |  | is interdependent with | ICT
Place |  | Housing | HOUSE-REQ28 | Training on day 1 changes for the teams | Must Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ40 | Training on day 1 changes for the teams |  |  | is interdependent with | Public Health
Place |  | Housing | HOUSE-REQ40 | Training on day 1 changes for the teams |  |  | is interdependent with | Public Protection
Place |  | Housing | HOUSE-REQ40 | Training on day 1 changes for the teams |  |  | is interdependent with | Community/Localism
Place |  | Housing | HOUSE-REQ41 | Service for homeless families to assess applications and be able to provide temp accomodation and wider support for children/safeguarding process | Must Have | requires support from |  | Children's
Place |  | Housing | HOUSE-REQ41 | Service for homeless families to assess applications and be able to provide temp accomodation and wider support for children/safeguarding process | Must Have | requires support from |  | Customer & Digital
Place |  | Housing | HOUSE-REQ42 | Landlord functions and Urgent response for Council tenants (e.g. repairs). Where there are districts providing Landlord services, standards and policies need to be aligned for Day 1. | Must Have | requires support from |  | Communications and Engagement
Place |  | Housing | HOUSE-REQ43 | Procedures, hand off points between teams etc | Should Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ43 | Procedures, hand off points between teams etc | Should Have |  | is interdependent with | Finance
Place |  | Housing | HOUSE-REQ44 | Procedures, hand off points between teams etc | Should Have |  | is interdependent with | Assets
Place |  | Housing | HOUSE-REQ45 | Procedures, hand off points between teams etc | Should Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ46 | Procedures, hand off points between teams etc | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ47 | Premises to operate from and teams in place in each service area to meet service demand. | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ47 | Premises to operate from and teams in place in each service area to meet service demand. | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ48 | Plans to identify existing contracts and how to align, novate etc | Should Have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ54 | Plans to identify existing contracts and how to align, novate etc | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ54 | Plans to identify existing contracts and how to align, novate etc | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ55 | Identifying non priority Policies and plan to review these and timescale | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ56 | Revised Constitution | Should Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ57 | Identify areas that may need new procurement | Should Have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ57 | Identify areas that may need new procurement | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ58 | A plan to align relevant Strategies, e.g. Housing Strategy - what will the priorities be? | Should Have | Requires discussion with |  | Strategic Commissioning
Place |  | Housing | HOUSE-REQ59 | Plan to review partnerships | Should Have |  | requires support from | Communications and Engagement
Place |  | Housing | HOUSE-REQ59 | Plan to review partnerships | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ60 | Effective policies for DFGs, HHSRS and HMOs | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ61 | Local Plan policies in place | Should Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ62 | Identitly of new teams and processes to manage them effectively | Should Have |  | developed together with | HR & OD
Place |  | Housing | HOUSE-REQ62 | Identitly of new teams and processes to manage them effectively | Should Have |  | requires support from | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ63 | review HIA, options going forward. :better homes agency" | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ64 | funding agreements, LAD, domestic abuse | Should Have | requires support from |  | Finance
Place |  | Housing | HOUSE-REQ65 | Direcction of travel for aligning Planning Policies | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ66 | internal procedures, reviewed. process based. | Should Have |  | requires support from | Finance
Place |  | Housing | HOUSE-REQ66 | internal procedures, reviewed. process based. | Should Have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ67 | updated letterheads,licence docs, offcial paperwork to the customer | Should Have |  | requires further discussion with | ICT
Place |  | Housing | HOUSE-REQ67 | updated letterheads,licence docs, offcial paperwork to the customer | Should Have |  | developed together with | Communications and Engagement
Place |  | Housing | HOUSE-REQ68 | started to review staffing and roles, Job Descriptions | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ69 | Analysis of which partnerships are still required and new partnershps needed | Should Have |  | requires further discussion with | Communications and Engagement
Place |  | Housing | HOUSE-REQ70 | Clear guidelines and timelines for staff on emerging structures still not in place | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ71 | identify policies that are required and considered to approval at new Executive | Should Have |  | requires support from | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ71 | identify policies that are required and considered to approval at new Executive | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ72 | review IT systems, not common accross and consider options. | Should Have | requires support from |  | ICT
Place |  | Housing | HOUSE-REQ73 | consolidation of some policy. updated to improve services | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ74 | Common Quality Standards | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ75 | Staff training programme in place and rolling out to embedd new culture, policies changes, new IT, workarounds etc | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ75 | Staff training programme in place and rolling out to embedd new culture, policies changes, new IT, workarounds etc | Should Have |  | requires support from | ICT
Place |  | Housing | HOUSE-REQ76 | Clear decision making and escalation routes | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ76 | Clear decision making and escalation routes | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ77 | streamine none day 1 critical policy and process for discretionary activity so no postcode lottery | Should Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ78 | Plans around HIA development and timeline | Should Have | requires support from |  | ICT
Place |  | Housing | HOUSE-REQ79 | Streamlined Homelessness and Housing Strategies Private sector Housing Grants policies | Should Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ80 | review of policies and procedures, KPI's/monitoring frameworks partner agencies arrangements | Should Have |  | requires further discussion with | Communications and Engagement
Place |  | Housing | HOUSE-REQ80 | review of policies and procedures, KPI's/monitoring frameworks partner agencies arrangements | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ81 | team management lines for comms, 1-1s, team meetings in place | Should Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ82 | Staff training programmes, appraisal processes agreed | Should Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ83 | full team | Should Have | is reliant upon decisions being made by |  | HR & OD
Place |  | Housing | HOUSE-REQ84 | internal policies/training for colleagues ie GDPR, safeguarding, E&D, new LA priorities | Should Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ85 | Partnerships reviewed and resstrucutred eg Cumbria Housing Group (and subgroups) and the Social Landlord/LA group plus agree what is happening with local partnerships | Should Have |  | requires further discussion with | Communications and Engagement
Place |  | Housing | HOUSE-REQ85 | Partnerships reviewed and resstrucutred eg Cumbria Housing Group (and subgroups) and the Social Landlord/LA group plus agree what is happening with local partnerships | Should Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ86 | team know who to report to if different to current arrangments | Should Have | requires further discussion with |  | HR & OD
Place |  | Housing | HOUSE-REQ87 | appraisals and training plans & priorities of the new council, to aid delivery | Should Have |  |  | HR & OD
Place |  | Housing | HOUSE-REQ88 | Strategic partnerships | Could Have |  | requires support from | Communications and Engagement
Place |  | Housing | HOUSE-REQ88 | Strategic partnerships | Could Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ89 | Strategic housing priorities | Could Have
Place |  | Housing | HOUSE-REQ102 | Integrated DFG team with OTs, etc | Could Have
Place |  | Housing | HOUSE-REQ103 | Alignment of contracts - Locata | Could Have |  | requires support from | Strategic Commissioning
Place |  | Housing | HOUSE-REQ103 | Alignment of contracts - Locata | Could Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ104 | Consistent template agreements, e.g. grants etc | Could Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ105 | Some alignment of key policies | Could Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ106 | One service team across the whole LA, ie homelessness | Could Have | requires further discussion with |  | HR & OD
Place |  | Housing | HOUSE-REQ107 | MDT of colleagues dealing with DFG's - OT's, Asc, HIA | Could Have
Place |  | Housing | HOUSE-REQ108 | Working partnership groups with Rp,s developers, Vol sector, | Could Have |  | requires support from | Communications & Engagement
Place |  | Housing | HOUSE-REQ108 | Working partnership groups with Rp,s developers, Vol sector, | Could Have |  | requires further discussion with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ109 | Align the HoC properties with BBC housing stock to be managed inhouse | Could Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ110 | Model for delivering Green Homes/sustainable warnth & bididng for new fundign opportunities | Could Have | requires further discussion with |  | Finance
Place |  | Housing | HOUSE-REQ111 | Domestic Abuse strategy | Could Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ112 | settled teams who all know their own roles/responsibilities | Could Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ113 | Local Housing Company | Could Have | requires support from |  | Communications & Engagement
Place |  | Housing | HOUSE-REQ114 | Shared contracts in place for DFGs, ECO | Could Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ115 | A model for a new HIA or Better Homes Agency | Could Have
Place |  | Housing | HOUSE-REQ116 | Started work around joint working polcies, practices | Could Have |  | requires further discussion with | HR & OD
Place |  | Housing | HOUSE-REQ116 | Started work around joint working polcies, practices | Could Have |  | requires support from | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ117 | Rebranding of Officer equipment, letters, communication | Could Have |  | requires support from | Communications & Engagement
Place |  | Housing | HOUSE-REQ117 | Rebranding of Officer equipment, letters, communication | Could Have |  | developed together with | ICT
Place |  | Housing | HOUSE-REQ118 | Started to look at Intergration of DFG within ASC | Could Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ119 | Uniformed Services for Homeless Services, Housing Asssitance, tenancy advocacy | Could Have
Place |  | Housing | HOUSE-REQ120 | empty homes strategy in plae for each unitary | Could Have | requires support from |  | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ121 | Integrated needs assessment for complex cases ASC/Homelessness/DFGs etc | Could Have
Place |  | Housing | HOUSE-REQ122 | acess to data within east and west so staff can cover all areas not jsut legalcy footprint and provide OOH effectively | Could Have | requires support from |  | ICT
Place |  | Housing | HOUSE-REQ123 | Integrated OT/DFG teams | Could Have | is reliant upon decisions being made by |  | HR & OD
Place |  | Housing | HOUSE-REQ124 | HIA for each new Unitary | Could Have
Place |  | Housing | HOUSE-REQ125 | one OOH shared system integrated with Social Care duty teams | Could Have
Place |  | Housing | HOUSE-REQ126 | shared budgets for homeless prevention | Could Have |  | requires support from | Finance
Place |  | Housing | HOUSE-REQ126 | shared budgets for homeless prevention | Could Have |  | developed together with | Finance
Place |  | Housing | HOUSE-REQ127 | LHC registered and linking with econmic regen plans | Could Have
Place |  | Housing | HOUSE-REQ128 | Social Care white paper delivery/transition plan | Could Have | requires further discussion with |  | Public Health
Place |  | Housing | HOUSE-REQ129 | One DFG service/meanstesting/ top ups etc | Could Have
Place |  | Housing | HOUSE-REQ130 | Every strategy related not likely to be in place. | Won't Have
Place |  | Housing | HOUSE-REQ131 | All contracts aligned. | Won't Have |  | requires support from | Strategic Commisssioning
Place |  | Housing | HOUSE-REQ131 | All contracts aligned. | Won't Have |  | developed together with | Legal & Democratic Services
Place |  | Housing | HOUSE-REQ132 | Aligned evidence base, e.g. stock condition survey or other evidence supporting strategic development - homeless reviews | Won't Have
Place |  | Housing | HOUSE-REQ133 | Consistent approach/funding opportunities in some areas, e.g. empty homes | Won't Have | requires support from |  | Finance
Place |  | Housing | HOUSE-REQ134 | Definitive operating model | Won't Have
Place |  | Housing | HOUSE-REQ135 | new team/structure in place, forums/working groups/partnerships | Won't Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ135 | new team/structure in place, forums/working groups/partnerships | Won't Have |  | requires further discussion with | Communications and Engagement
Place |  | Housing | HOUSE-REQ136 | One Team - all speaking with one voice | Won't Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ137 | all the necessary policies/procedures in place and/or aligned | Won't Have
Place |  | Housing | HOUSE-REQ138 | same team structure across the LA | Won't Have | requires further discussion with |  | HR & OD
Place |  | Housing | HOUSE-REQ139 | budgets | Won't Have | requires support from |  | Finance
Place |  | Housing | HOUSE-REQ140 | a new vision/culture - YET | Won't Have
Place |  | Housing | HOUSE-REQ141 | aligned pay/conditions | Won't Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ142 | aligned pay/conditions | Won't Have |  | developed together with | Finance - Financial & Commercial Stability
Place |  | Housing | HOUSE-REQ143 | settled teams/colleagues | Won't Have | developed together with |  | HR & OD
Place |  | Housing | HOUSE-REQ144 | job descriptions/role profiles consistent | Won't Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ145 | All new teams and systems in place | Won't Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ145 | All new teams and systems in place | Won't Have |  | developed together with | ICT
Place |  | Housing | HOUSE-REQ145 | All new teams and systems in place | Won't Have |  | developed together with | Finance
Place |  | Housing | HOUSE-REQ146 | Consistent approach to Officers decisions, autonomy | Won't Have
Place |  | Housing | HOUSE-REQ147 | Shared IT systems for areas of work, specific to work area. FLARE, CASE MANAGER | Won't Have | requires support from |  | ICT
Place |  | Housing | HOUSE-REQ148 | Culture change, Carlisle works on three C's | Won't Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ149 | Shared department budgets, equipment, training, resources | Won't Have |  | developed together with | Finance
Place |  | Housing | HOUSE-REQ149 | Shared department budgets, equipment, training, resources | Won't Have |  | requires support from | HR & OD
Place |  | Housing | HOUSE-REQ149 | Shared department budgets, equipment, training, resources | Won't Have |  | requires support from | ICT
Place |  | Housing | HOUSE-REQ150 | VR on the table around staffing | Won't Have | is reliant upon decisions being made by |  | HR & OD
Place |  | Housing | HOUSE-REQ151 | Full commonality in response across the new area | Won't Have
Place |  | Housing | HOUSE-REQ152 | Fully intergated teams and structures | Won't Have | requires support from |  | HR & OD
Place |  | Housing | HOUSE-REQ153 | Common contractual arrangements | Won't Have | requires support from |  | Strategic Commisssioning
Place |  | Planning and Building Control | PBC-REQ1 | Recurit and retain staff that will be situated within deliverable geographies across the new authorities | Must Have
Place |  | Planning and Building Control | PBC-REQ2 | New workable schemes of delegation adopted by the new authorities | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ3 | All local plans and supplementary planning documents to be adopted by new authorities | Must Have | has a connection with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ4 | LDS (Local Development Scheme) to be adopted by new authoirities | Must Have | has a connection with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ5 | Shadow authorities to decide committee structure in new authorities | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ6 | Shadow Authority Planning Committee Elections to take place and new chair appointed for both authorities | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ7 | Member training for Planning Committee for-both authorities | Must Have | developed together with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ8 | Street Naming and Numbering - Committee approval of SNN policy in both authorities | Must Have | has a connection with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ9 | Enforcement policies to be adopted by new authorities | Must Have | has a connection with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ10 | Agreed policy in regards to CIL / section 106 (South Lakeland has a CIL but no other authority has one) | Must Have |  | has a connection with | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ10 | Agreed policy in regards to CIL / section 106 (South Lakeland has a CIL but no other authority has one) | Must Have |  | has a connection with | Finance
Place |  | Planning and Building Control | PBC-REQ11 | Pre-app policy to be adopted by the new authorities | Must Have | is reliant upon decisions being made by |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ12 | Functional IT systems for Building Control & Development Management | Must Have | is reliant upon decisions being made by |  | ICT
Place |  | Planning and Building Control | PBC-REQ13 | Access to historic planning records for buiding control, development management and minerals and waste | Must Have | is reliant upon decisions being made by |  | ICT
Place |  | Planning and Building Control | PBC-REQ14 | GIS systems | Must Have | has a connection with |  | ICT
Place |  | Planning and Building Control | PBC-REQ15 | New MoU for joint committees such as partnership boards | Must Have |  |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ16 | Appoint partnership members to AONB boards (Solway Coast, North Pennines & Arnside and Silverdale | Must Have | has a connection with
Place |  | Planning and Building Control | PBC-REQ17 | Statutory Planning Noties Policy needs to be cordinated | Should Have |  |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ18 | Approach to site notices needs to be cordinated | Should Have
Place |  | Planning and Building Control | PBC-REQ19 | Harmonised standard conditions for both authorities | Should Have
Place |  | Planning and Building Control | PBC-REQ20 | Harmonised validation procedures for both authorities | Should Have
Place |  | Planning and Building Control | PBC-REQ21 | Corporate Templates for notices, decisions, delgated reports & committee reports | Should Have | has a connection with
Place |  | Planning and Building Control | PBC-REQ22 | Committee Policy to be agreed (i.e. site visit policy) | Should Have | developed together with |  | Legal & Democratic Services
Place |  | Planning and Building Control | PBC-REQ23 | A new centralised admin protocal for development management and building control in both authorities. These include inboxes and addresses for plannning and building control applications in the new authorities. | Could Have |  |  | ICT
Place |  | Planning and Building Control | PBC-REQ24 | Harmonised local plans for the new authorities | Won't Have | is reliant upon decisions being made by
Place |  | Planning and Building Control | PBC-REQ25 | A harmonised IT system for Development Management and Building Control in the new authorities | Won't Have | is reliant upon decisions being made by |  | ICT
Place |  | Planning and Building Control | PBC-REQ26 | A Harmonised GIS system for the new authorities | Won't Have | ICT - Infrastructure |  | ICT
Place |  | Economic Development | ED-REQ1 | Grant Funding Agreements & MoU (legacy and current) to be novated (an estimated 1,880 county council GFA contracts require novation) | Must Have |  | is reliant on contributions from | Legal & Democratic Services
Place |  | Economic Development | ED-REQ1 | Grant Funding Agreements & MoU (legacy and current) to be novated (an estimated 1,880 county council GFA contracts require novation) | Must Have |  | is reliant upon decisions being made by | Finance
Place |  | Economic Development | ED-REQ2 | Where accountable bodies and project applicants belong to the same organisation, new MoUs need to be created. | Must Have | is reliant on contributions from |  | Legal & Democratic Services
Place |  | Economic Development | ED-REQ3 | Decision is needed regarding if the CLEP accountable body function is going to be provided by two authorities or one | Must Have | is reliant upon decisions being made by
Place |  | Economic Development | ED-REQ4 | The accountable body function for Cross boundary programmes (both current and legacy) needs to be allocated to either authority | Must Have | is reliant upon decisions being made by |  | Finance
Place |  | Economic Development | ED-REQ5 | Where accountable bodies and project applicants belong to the same organisation, new MoUs need to be drawn up | Must Have | is reliant on contributions from |  | Legal & Democratic Services
Place |  | Economic Development | ED-REQ6 | Agreements to be made regarding how the PMO and accountable body functions will be funded in the new authorities (including administration fees from programmes such as Town Deal) | Must Have | is reliant upon decisions being made by |  | Finance
Place |  | Economic Development | ED-REQ7 | Document retention | Must Have | developed together with |  | Legal & Democratic Services
Place |  | Economic Development | ED-REQ8 | Harmonised governance frameworks | Won't Have | requires further discussion with |  | Legal & Democratic Services
Place |  | Economic Development | ED-REQ9 | Harmonised and consolidated economic strategies for day one | Won't Have
Place |  | Climate Change/Net Zero | NZ-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have | developed together with |  | Planning and Building Control
Place |  | Climate Change/Net Zero | NZ-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have | developed together with |  | Street Scene and Open Spaces
Place |  | Climate Change/Net Zero | NZ-REQ1 | Local Nature Recovery Strategy (becoming mandatory summer 2022) | Must have | developed together with |  | Community/Localism
Place |  | Climate Change/Net Zero | NZ-REQ2 | Officer to work on Annual Status Report (Due to be submitted to DEFRA by June) | Must have | requires support from |  | Legal & Democratic Services
Place |  | Climate Change/Net Zero | NZ-REQ3 | Acountable Body arrangements for existing projects and supporting resources | Must have | requires support from |  | Accountancy & Financial Planning – all other elements
Place |  | Climate Change/Net Zero | NZ-REQ4 | Policy in place to ensure compliance with current legislation eg Environment Act 2021 Requirements - incl Biodiversity Net Gain | Must have |  | developed together with | Policy Framework
Place |  | Climate Change/Net Zero | NZ-REQ4 | Policy in place to ensure compliance with current legislation eg Environment Act 2021 Requirements - incl Biodiversity Net Gain | Must have |  | developed together with | Planning and Building Control
Place |  | Climate Change/Net Zero | NZ-REQ5 | Staffing and financial resource to ensure requirements can be met | Must have |  | is dependant on as a precursor | HR & OD
Place |  | Climate Change/Net Zero | NZ-REQ5 | Staffing and financial resource to ensure requirements can be met | Must have |  | is dependant on as a precursor | Accountancy & Financial Planning – all other elements
Place |  | Climate Change/Net Zero | NZ-REQ6 | Flood and Water Management Act - Lead Local Flood Authority | Must have |  | requires further discussion with | Highways
Place |  | Climate Change/Net Zero | NZ-REQ6 | Flood and Water Management Act - Lead Local Flood Authority | Must have |  | requires further discussion with | Resilience and Emergency Planning
Place |  | Climate Change/Net Zero | NZ-REQ7 | Robust Climate Risk Assessment | Must have |  | developed together with | Risk Management & Business Continuity
Place |  | Climate Change/Net Zero | NZ-REQ7 | Robust Climate Risk Assessment | Must have |  | developed together with | All services - all line managers
Place |  | Climate Change/Net Zero | NZ-REQ7 | Robust Climate Risk Assessment | Must have |  | developed together with | Resilience and Emergency Planning
Place |  | Climate Change/Net Zero | NZ-REQ8 | Procurement policy covering social value incl Environmental Stability (PPN 06/20, 06/21, Social Value Act) | Must have |  | developed together with | Strategic Procurement / Strategy​
Place |  | Climate Change/Net Zero | NZ-REQ8 | Procurement policy covering social value incl Environmental Stability (PPN 06/20, 06/21, Social Value Act) | Must have |  | developed together with | Policy Framework
Place |  | Climate Change/Net Zero | NZ-REQ9 | Sustainability assessment of planning decisions | Must have |  | developed together with | Planning and Building Control
Place |  | Climate Change/Net Zero | NZ-REQ9 | Sustainability assessment of planning decisions | Must have |  | developed together with | Housing
Place |  | Climate Change/Net Zero | NZ-REQ9 | Sustainability assessment of planning decisions | Must have |  | developed together with | Highways
Place |  | Climate Change/Net Zero | NZ-REQ10 | Coast Protection Authorities and Coastal Erosion Risk Management Authorities | Must have | requires further discussion with |  | Resilience and Emergency Planning
Place |  | Climate Change/Net Zero | NZ-REQ11 | Civil Contingencies Act 2004 - dealing with emergencies (Community Risk Register) | Must have | is dependant on as a precursor |  | Resilience and Emergency Planning
Place |  | Climate Change/Net Zero | NZ-REQ12 | Assurance that LGR Programme interdependencies with cross-cutting themes are managed (eg via climate impact assessment) | Must have | requires support from |  | All services - all line managers
Place |  | Climate Change/Net Zero | NZ-REQ13 | Organisational and geographical Net Zero targets | Should have |  | requires further discussion with | Policy Framework
Place |  | Climate Change/Net Zero | NZ-REQ13 | Organisational and geographical Net Zero targets | Should have |  | requires further discussion with | Legal & Democratic Services
Place |  | Climate Change/Net Zero | NZ-REQ13 | Organisational and geographical Net Zero targets | Should have |  | requires further discussion with | Transformation & Change Management
Place |  | Climate Change/Net Zero | NZ-REQ14 | Route map for compliance with ZCCP/Climate Change Act net zero targets 2037/2050 | Should have |  | requires further discussion with | All services - all line managers
Place |  | Climate Change/Net Zero | NZ-REQ14 | Route map for compliance with ZCCP/Climate Change Act net zero targets 2037/2050 | Should have |  | requires further discussion with | Transformation & Change Management
Place |  | Climate Change/Net Zero | NZ-REQ15 | Strategy: Action Plan for Climate Change, Environment and Biodiversity | Should have |  | requires further discussion with | Legal & Democratic Services
Place |  | Climate Change/Net Zero | NZ-REQ15 | Strategy: Action Plan for Climate Change, Environment and Biodiversity | Should have |  | requires further discussion with | Policy Framework
Place |  | Climate Change/Net Zero | NZ-REQ15 | Strategy: Action Plan for Climate Change, Environment and Biodiversity | Should have |  | requires further discussion with | All services - all line managers
Place |  | Climate Change/Net Zero | NZ-REQ16 | Adaptation strategy and plan | Should have |  | requires support from | Resilience and Emergency Planning
|  | Climate Change/Net Zero | NZ-REQ16 | Adaptation strategy and plan | Should have |  | requires support from | Public Protection
|  | Climate Change/Net Zero | NZ-REQ16 | Adaptation strategy and plan | Should have |  | requires support from | Community/Localism
|  | Climate Change/Net Zero | NZ-REQ16 | Adaptation strategy and plan | Should have |  | requires support from | Planning and Building Control
Place |  | Climate Change/Net Zero | NZ-REQ17 | Procurement policy that priorities Climate/Sustainability above mandatory levels | Should have |  | is dependant on as a precursor | Strategic Procurement / Strategy​
|  | Climate Change/Net Zero | NZ-REQ17 | Procurement policy that priorities Climate/Sustainability above mandatory levels | Should have |  | is dependant on as a precursor | Policy Framework
Place |  | Climate Change/Net Zero | NZ-REQ18 | Carbon Data monitoring/accounting systems | Should have | requires further discussion with |  | Performance & Business Intelligence
Place |  | Climate Change/Net Zero | NZ-REQ19 | Climate Governance - Board, Steering Group | Should have | is dependant on as a precursor |  | Legal & Democratic Services
Place |  | Climate Change/Net Zero | NZ-REQ20 | Local Energy strategy | Should have
Place |  | Climate Change/Net Zero | NZ-REQ21 | Long term financial plan for mitigation and adaptation | Should have |  | is dependant on as a precursor | Accountancy & Financial Planning – all other elements
|  | Climate Change/Net Zero | NZ-REQ21 | Long term financial plan for mitigation and adaptation | Should have |  | is dependant on as a precursor | Policy Framework
Place |  | Climate Change/Net Zero | NZ-REQ22 | Internal climate change action plan (emissions reduction etc) linked to Corporate KPIs | Should have |  | requires further discussion with | Policy Framework
|  | Climate Change/Net Zero | NZ-REQ22 | Internal climate change action plan (emissions reduction etc) linked to Corporate KPIs | Should have |  |  | All services - all line managers
Place |  | Climate Change/Net Zero | NZ-REQ23 | Key expert staff in place around climate change, biodiversity, decarbonisation | Should have | requires support from |  | HR & OD
Place |  | Climate Change/Net Zero | NZ-REQ24 | Assessment of climate and ecological implications of key decisions | Should have |  | requires further discussion with | Legal & Democratic Services
Place |  | Climate Change/Net Zero | NZ-REQ24 | Assessment of climate and ecological implications of key decisions | Should have |  | requires further discussion with | Policy Framework
Place |  | Climate Change/Net Zero | NZ-REQ25 | Website - information for businesses and public on climate change, links to strategies, carbon footprint etc | Should have | requires further discussion with |  | Communications and Engagement
Place |  | Climate Change/Net Zero | NZ-REQ26 | Stakeholder Engagement Plan | Should have |  | requires further discussion with | Communications and Engagement
Place |  | Climate Change/Net Zero | NZ-REQ26 | Stakeholder Engagement Plan | Should have |  | requires further discussion with | Community/Localism
Place |  | Climate Change/Net Zero | NZ-REQ27 | Budget (for Climate Communication, projects community engagement) | Should have | is dependant on as a precursor |  | Accountancy & Financial Planning – all other elements
Place |  | Climate Change/Net Zero | NZ-REQ28 | Climate Comms Strategy | Should have | requires further discussion with |  | Communications and Engagement
Place |  | Climate Change/Net Zero | NZ-REQ29 | HR Policies (eg recruitment, performance training) linked to sustainability | Should have | requires further discussion with |  | HR & OD
Place |  | Climate Change/Net Zero | NZ-REQ30 | Declaration of Climate Emergency | Could have | has a connection with |  | Policy Framework
Place |  | Climate Change/Net Zero | NZ-REQ31 | Climate Champions in all different services within new authorities | Could have |  | requires further discussion with | All services - all line managers
Place |  | Climate Change/Net Zero | NZ-REQ31 | Climate Champions in all different services within new authorities | Could have |  | requires further discussion with | All services - all employees
Place |  | Climate Change/Net Zero | NZ-REQ32 | Carbon literacy training to be implemented in induction for staff & offered to all councillors | Should have |  | requires further discussion with | Learning & Development
Place |  | Climate Change/Net Zero | NZ-REQ32 | Carbon literacy training to be implemented in induction for staff & offered to all councillors | Should have |  | requires further discussion with | HR & OD
Place |  | Climate Change/Net Zero | NZ-REQ32 | Carbon literacy training to be implemented in induction for staff & offered to all councillors | Should have |  | requires further discussion with | Legal & Democratic Services
Place |  | Climate Change/Net Zero | NZ-REQ33 | Nominations to existing external partnerships (eg ZCCP) | Could have | developed together with |  | Legal & Democratic Services
Place |  | Climate Change/Net Zero | NZ-REQ34 | Memberships/subscriptions (APSE etc) | Could have | is dependant on as a precursor |  | Accountancy & Financial Planning – all other elements
Place |  | Climate Change/Net Zero | NZ-REQ35 | Net Zero Skills audits | Could have |  | developed together with | Learning & Development
Place |  | Climate Change/Net Zero | NZ-REQ35 | Net Zero Skills audits | Could have |  | developed together with | HR & OD
Place |  | Climate Change/Net Zero | NZ-REQ36 | Budget for consultants | Could have | is dependant on as a precursor |  | Accountancy & Financial Planning – all other elements
Place |  | Climate Change/Net Zero | NZ-REQ37 | Electric Vehicle transition / infrastructure plan | Could have |  | developed together with | Fleet
Place |  | Climate Change/Net Zero | NZ-REQ37 | Electric Vehicle transition / infrastructure plan | Could have |  | developed together with | Transport
Place |  | Climate Change/Net Zero | NZ-REQ37 | Electric Vehicle transition / infrastructure plan | Could have |  | developed together with | Highways
Place |  | Climate Change/Net Zero | NZ-REQ37 | Electric Vehicle transition / infrastructure plan | Could have |  | developed together with | Planning and Building Control
Place |  | Climate Change/Net Zero | NZ-REQ37 | Electric Vehicle transition / infrastructure plan | Could have |  | developed together with | Economic Development
Place |  | Climate Change/Net Zero | NZ-REQ37 | Electric Vehicle transition / infrastructure plan | Could have |  | developed together with | Community/Localism
Place |  | Climate Change/Net Zero | NZ-REQ38 | Tree planting target | Could have |  | developed together with | Street Scene and Open Spaces
Place |  | Climate Change/Net Zero | NZ-REQ38 | Tree planting target | Could have |  | developed together with | Community/Localism
Place |  | Climate Change/Net Zero | NZ-REQ38 | Tree planting target | Could have |  | developed together with | Planning and Building Control
Place |  | Climate Change/Net Zero | NZ-REQ39 | Environmental Credit/Trading Warehousing scheme | Could have |  | developed together with | Accountancy & Financial Planning – all other elements
Place |  | Climate Change/Net Zero | NZ-REQ39 | Environmental Credit/Trading Warehousing scheme | Could have |  | developed together with | Economic Development
Place |  | Climate Change/Net Zero | NZ-REQ39 | Environmental Credit/Trading Warehousing scheme | Could have |  | developed together with | Grants Portfolio
Place |  | Climate Change/Net Zero | NZ-REQ39 | Environmental Credit/Trading Warehousing scheme | Could have |  | developed together with | Income Collection
Place |  | Climate Change/Net Zero | NZ-REQ40 | Net Zero operational emissions | Won't have
Place |  | Climate Change/Net Zero | NZ-REQ41 | Council-owned socially-focused energy company | Won't have
Place |  | Climate Change/Net Zero | NZ-REQ42 | Community energy ownership schemes | Won't have
Place |  | Climate Change/Net Zero | NZ-REQ43 | Mechanisms for non-financial climate and nature related disclosures | Won't have
Place |  | Climate Change/Net Zero | NZ-REQ44 | Ability (ie budget, resources, policies etc) to achieve ZCCP Net Zero by 2037 target | Won't have
Place |  | Climate Change/Net Zero | NZ-REQ45 | Sufficient resources or budget to address climate and nature crises urgently enough | Won't have
Place |  | Climate Change/Net Zero | NZ-REQ46 | Low carbon affordable mobility strategy | Won't have
Place |  | Climate Change/Net Zero | NZ-REQ47 | Robust and funded active travel infrastructure | Won't have
Place |  | Climate Change/Net Zero | NZ-REQ48 | Internal biodiversity net gain principle for council projects | Won't have
Place |  | Climate Change/Net Zero | NZ-REQ49 | Updated Local Plan - sustainability embedded into policies | Won't have

## Assumptions
Assumptions
ID | Theme | Cluster | Service / Work Package | Assumption |  | Work Package Responsible | Agreed? | Priority
e.g A_001 | Corporate Enablers |  |  | e.g. On day 1 all staff will have access to a new intranet site - two will be developed, one for each new unitary authority |  | ICT | Yes | Medium (Impacts Detail of the Blueprint but Not Overall Shape)
ADMIN-ASSUM1 | Corporate and Enabling Services |  | Administration and Business Support | Access to buildings
ADMIN-ASSUM2 | Corporate and Enabling Services |  | Administration and Business Support | Access to basic IT - MS Suite of Products
ADMIN-ASSUM3 | Corporate and Enabling Services |  | Administration and Business Support | Access to shared folders/sharepoint with relevant security access
ADMIN-ASSUM4 | Corporate and Enabling Services |  | Administration and Business Support | Cumbria County Council currently provide Business Support for CFRS - we have not included this due to the current proposals for the new governance options for CFRS
ADMIN-ASSUM5 | Corporate and Enabling Services |  | Administration and Business Support | Access to employee HR data (either your personal data or those in your team so you can record Appraisals/Abences/Approve Annual leave/Expenses etc)
ADMIN-ASSUM6 | Corporate and Enabling Services |  | Administration and Business Support | Budgets for the Admin and Business Support function agreed and set up for Vesting Day
ADMIN-ASSUM7 | Corporate and Enabling Services |  | Administration and Business Support | Access to your new authorities intranet - including policies/procedures relating to the new authority
ADMIN-ASSUM8 | Corporate and Enabling Services |  | Administration and Business Support | Assume the telephony/mobile phones will be up and running for day one (with relevant hunt groups/pickups etc)
ADMIN-ASSUM9 | Corporate and Enabling Services |  | Administration and Business Support | Business Continuity Plans for all Service Areas will be created for day one of the new Authority
ADMIN-ASSUM10 | Corporate and Enabling Services |  | Administration and Business Support | Assume that the new Authorities are regisitered with the relevant Court
ADMIN-ASSUM11 | Corporate and Enabling Services |  | Administration and Business Support | Assume VPN access will be set up to enable remote working |  |  |  |  | Sub Theme | Service / Work Package | Cluster
ADMIN-ASSUM12 | Corporate and Enabling Services |  | Administration and Business Support | Assume access to shared drives within each new authority (do we need to list these now? How do we ensure the ones we use will be mapped across?)
ADMIN-ASSUM13 | Corporate and Enabling Services |  | Administration and Business Support | A full list of staff and job roles so we know who is in what team and how they can be contacted

## List for Drop Down
Missing dependent workstreams (enabling):
Theme | Work Package | Cluster | Priority/ MoSCoW | HR
Place | Accountancy & Financial Planning – Accountable Body & Programme Management Office Function – Economic Programme’s Team | TBC | Must Have | Finance
People | Accountancy & Financial Planning – all other elements |  | Should Have
Corporate and Enabling Services | Administration and Business Support |  | Could Have
ICT | Adults |  | Wont Have
Customer and Digital | Adults - Commissioning
Finance and Commercial | Adults - Commissioned Services
Adults - Cumbria Care
Adults - Non Commissioned Services
Adults - Partnerships
Adults - Social Work
All services - all employees
All services - all line managers
Assets
Audit
Capital Programme
Children’s Statutory Placement Function
Children's
Children's - Integration & Partnerships
Children's - Children & Young People
Children's - Education & Skills
Climate Change/Net Zero
Commissioning & Procurement
Communications and Engagement
Community/Localism
Contract Management/Monitoring
Contracts Portfolio
Coroners Service
Council-wide Purchasing (Category Management)​
Culture, Leisure, Events
Cumbria Local Government Pension Scheme (CLGPS)
Customer & Digital
Economic Development
Finance
Fire & Rescue and Blue Light Integration
Fleet
FOI/SAR, Comments, Compliments & Complaints
Governance & Policy
Grants Portfolio
Health & Safety
Highways
Housing
HR & OD
ICT
Income Collection
Information Governance
Internal Audit
Learning & Development
Legal & Democratic Services
LGR Leadership/Board
LGR PMO
Libraries and Community Services
Local Tax Collection (Council Tax/NNDR) & Benefits
Market Management / Development / Sufficiency
Market Shaping and Market Failure (Care Act Duties)
Nuclear
Ordering and Paying for Goods and Services
Pension Fund
Performance & Business Intelligence
Planning and Building Control
Policy Framework
Property, Asset Strategy and Property Maintenance
Public Health
Public Protection
Records Management work package
Resilience and Emergency Planning
Risk Management & Business Continuity
Social Care Brokerage
Strategic Commissioning
Strategic Planning / Needs Analysis
Strategic Procurement / Strategy​
Street Scene and Open Spaces
Trade Unions
Transformation & Change Management
Transport
Treasury Management and Insurance
Waste
Workforce & Organisational Development
Data Centres
Networks
Back Up and Disaster Recovery
Virtual Private Networks
Active Directory Domains
Information Security
Non Microsoft Cloud
Cumbria County Council Architecture
Solutions Target
Microsoft Enterprise Agreement
End User Computing
ICT Service Support
Telephony
LLPG
GIS
Systems

## Action Log (hidden)
Action Log
Ref | Date Raised | Action | Owner | Target Completion Date | Status | Update / Outcome
1 | xxx | Brief description of Action | e.g. John Doe | xxx | Create drop down: To be escalates In progress On hold Completed No longer needed | Open
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48

## Transformation Opportunities (hidden)
Transformation Opportunities
| Place | People | Corporate Enablers | Customer & Digital | Finance | ICT
Transformational Opportunity Description

## Stakeholders (hidden)
Programme Key Stakeholder Management Plan
| Name | Job Title | Organisation | Stakeholder Status Is this Stakeholder….. Responsible Accountable Consulted Informed | Responsible individual Who is responsible for managing this stakeholder? (Enter name/s) | Potential impact of programme on stakeholder Low Medium High | Importance of stakeholder to success of programme Low (Can watch it happening) Medium (Can help it happen) High (Can make it or stop it happening) | CURRENT Commitment level and change readiness (1) Ownership (2) Participation/Understanding (3) Awareness (4) Dissatisfaction/Denial (5) Sabotage/non-compliance | Key Issues and Concerns (Enter date and key issues/concerns. To add new information, enter date and record changes to issues and concerns) | Interventions - how this stakeholder is being managed (e.g. 1-2-1 meetings; weekly phone calls; focus group invite; routine info circular, occassional email) | Date of last review NOTE: Status of Stakeholder assessment must be updated weekly for HIGH IMPACT stakeholders
Internal Stakeholders
| XXX | YYY | ZZZ | Informed |  | Low | High | (5)Sabotage/non-compliance |  | email circular | N/A
| XXX | YYY | ZZZ | Accountable |  | High | High | (4) Dissatisfaction/Denial |  | one to one | N/A
| XXX | YYY | ZZZ | Consulted |  | Low | High | (3) Awareness |  | weekly phone call | N/A
| XXX | YYY | ZZZ | Responsible |  | Medium | High | (2) Participation/Understanding |  | email circular | N/A
| XXX | YYY | ZZZ | Informed |  | Low | High | (1) Ownership |  | one to one | N/A
| XXX | YYY | ZZZ | Informed |  | Low | High | (2) Participation/Understanding |  | email circular | N/A
| XXX | YYY | ZZZ | Informed |  | Low | High | (2) Participation/Understanding |  | one to one | N/A
| XXX | YYY | ZZZ | Informed |  | Low | High | (2) Participation/Understanding |  | weekly phone call | N/A
External Stakeholders
Group One (e.g. NHS organisations, police, schools, commissioned providers, or established service user representative groups)
Group Two (e.g. MPs, third sector partners, regulators, parish councils, or individual services users)
|  |  |  | Responsible |  | Low | Low | (1) Ownership
|  |  |  | Accountable |  | Medium | Medium | (2) Participation/Understanding
|  |  |  | Consulted |  | High | High | (3) Awareness
|  |  |  | Informed |  |  |  | (4) Dissatisfaction/Denial
(5)Sabotage/non-compliance

## Requirements Tracker (hidden)
Day 1 Requirements Tracker
Work Theme | Work Package | Requirement ID | MoSCoW | Day 1 Requirement | Milestone ID | Risk ID | Decision ID | Dependency ID

## POAP (hidden)
| Year 2021 |  |  |  | Year 2022 | [10 empty] | Year 2023
| Sep-21 | Oct-21 | Nov-21 | Dec-21 | Jan-22 | Feb-22 | Mar-22 | Apr-22 | Jun-22 | July-22 | Aug-22 | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Apr-23 | May-23
| xxx Phase |  | xxx Phase |  |  |  | xxx Phase
Tech
Example text

## Milestone Summary (hidden)
|  |  | Cumbria LGR - Milestone and Activity Summary Sheet | [6 empty] | Data cut-off: xxx
Tech Workstream
| Baseline |  |  |  |  | Previous Reporting Period Forecast |  | Current Reporting Period Forecast |  | Deltas
| Level | Milestone Code | WBS | Baseline Start Date | Baseline Finish Date | Start Date | Finish Date | Start Date | Finish Date | End Date Delta1 - Current forecast vs Baseline | End Date Delta2 - Current forecast vs Previous forecast
[8 empty] | x | x | X | X
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü

## Plan (hidden)
|  |  | Plan Template Tech Workstream | [6 empty] | Updated: 18/03/2022
[10 empty] | 2020 Year | Jan 2020 | January 2020 | [30 empty] | Feb 2020 | February 2020 | [28 empty] | Mar 2020 | March 2020 | [30 empty] | Apr 2020 | April 2020 | [29 empty] | May 2020 | May 2020 | [30 empty] | Jun 2020 | June 2020 | [29 empty] | Jul 2020 | July 2020 | [30 empty] | Aug 2020 | August 2020 | [30 empty] | Sep 2020 | September 2020 | [29 empty] | Oct 2020 | October 2020 | [30 empty] | Nov 2020 | November 2020 | [29 empty] | Dec 2020 | December 2020 | [30 empty] | 2021 Year | Jan 2021 | January 2021 | [30 empty] | Feb 2021 | February 2021 | [27 empty] | Mar 2021 | March 2021 | [30 empty] | Apr 2021 | April 2021 | [29 empty] | May 2021 | May 2021 | [30 empty] | Jun 2021 | June 2021
ID | B/N | Status | Milestone / Activity | Critical | Baseline Start Date | Baseline Finish Date | Forecast Start Date | Forecast Finish Date | Owner |  |  | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F |  | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T |  | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T |  | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T |  | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F |  | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W |  | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T |  |  | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W |  | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F |  | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
[12 empty] | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12 | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-18 | 2020-01-19 | 2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26 | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 |  | 2020-02-01 | 2020-02-02 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16 | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 |  | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29 | 2020-03-30 | 2020-03-31 |  | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 |  | 2020-05-01 | 2020-05-02 | 2020-05-03 | 2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-09 | 2020-05-10 | 2020-05-11 | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-15 | 2020-05-16 | 2020-05-17 | 2020-05-18 | 2020-05-19 | 2020-05-20 | 2020-05-21 | 2020-05-22 | 2020-05-23 | 2020-05-24 | 2020-05-25 | 2020-05-26 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-05-30 | 2020-05-31 |  | 2020-06-01 | 2020-06-02 | 2020-06-03 | 2020-06-04 | 2020-06-05 | 2020-06-06 | 2020-06-07 | 2020-06-08 | 2020-06-09 | 2020-06-10 | 2020-06-11 | 2020-06-12 | 2020-06-13 | 2020-06-14 | 2020-06-15 | 2020-06-16 | 2020-06-17 | 2020-06-18 | 2020-06-19 | 2020-06-20 | 2020-06-21 | 2020-06-22 | 2020-06-23 | 2020-06-24 | 2020-06-25 | 2020-06-26 | 2020-06-27 | 2020-06-28 | 2020-06-29 | 2020-06-30 |  | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-04 | 2020-07-05 | 2020-07-06 | 2020-07-07 | 2020-07-08 | 2020-07-09 | 2020-07-10 | 2020-07-11 | 2020-07-12 | 2020-07-13 | 2020-07-14 | 2020-07-15 | 2020-07-16 | 2020-07-17 | 2020-07-18 | 2020-07-19 | 2020-07-20 | 2020-07-21 | 2020-07-22 | 2020-07-23 | 2020-07-24 | 2020-07-25 | 2020-07-26 | 2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 |  | 2020-08-01 | 2020-08-02 | 2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09 | 2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23 | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30 | 2020-08-31 |  | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30 |  | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 |  | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29 | 2020-11-30 |  | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-05 | 2020-12-06 | 2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-12 | 2020-12-13 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 2020-12-27 | 2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 |  |  | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 |  | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-02-27 | 2021-02-28 |  | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 |  | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 |  | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 |  | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30
Tech Milestones

## Key Decisions (hidden)
Key Decisions
Decision ID | Decision Origin | Decision Raised By (Programme Area / Workstream) | Type of Decision | Decisions Title | Owner (Name of Individual) | Status | Impact | Priority | Required Sign-off Board | Date Decision Raised | Date Decision Required | Date Closed | Impacted Workstreams / Enabling Capabilities | First Key Approval | Second Key Approval | Third Key Approval
xxx | xxx | e.g. Tech/ Place | Programme | e.g. is x a solution for day 1 statutory or blueprint requirements? | e.g. John Doe | Open | High | Monitor | e.g. Programme Delivery Board | dd/mm/yyyy | dd/mm/yyyy | dd/mm/yyyy | x, y, z

## Change Register (hidden)
|  |  | Key Changes Register | [7 empty] | Updated: 18/03/2022
Change ID | Status | Change Title |  | Change Description | Change Author | Date Raised | Change Raised By | Required Sign-off Board | Impacted Areas | Date Change Required | First Key Approval | Second Key Approval

## Data Sheet (hidden)
Risk Status |  | Decision Status | Type of Decision | Decision Impact | Decision Priority | Decision needed |  | MASS Level
Open |  | Open | Programme | High | Criritcal | Yes |  | L2
Ongoing |  | Pending | Workstream | Medium | Required | No |  | L3
Closed |  | Closed |  | Low | Monitor |  |  | L4
Complete
Plan - Critical | Plan - Baseline |  | Dependencies - Critical |  | Change - Status |  | Day1 MoSCoW
C | B |  | C |  | Open |  | Must have
| N |  |  |  | Pending |  | Should have
[5 empty] | Closed |  | Could have
Won't have