## Coversheet
Project Prioritisation Tool
Version | V1.0
Last edited | 2025-05-25
Description | This workbook contains a project prioritisation tool designed for use by local authorities to support infrastructure planning. The criteria included are desinged to align with a range of priorities and objectives. This tool should be adjusted to account for your evolving needs and priorities. The weighting for each criterion can be adjusted in the yellow cells (U4-AC4) in the Matrix sheet. Adjusting these will give more or less improtance to each of the critreria based on the need. Further information is contained in the guidance section.
Criteria | Criteria | Type | Operationalisation | Assessment guide | Additional Information
| Strategic Criteria- Site Allocation Relation | Strategic | Y/N 1 for Y, 0 for N | Does the project support or enable site allocations or strategic growth areas?
| Strategic Criteria- Cross Thematic Benefits | Strategic | Low, Medium, High Range 1-3 (1 low, 3 high) | Does the project offer benefits across multiple service areas? | For projects that improve multiple service areas. For example supporting both active travel and improving green spaces.
| Carbon | Additional | Low, Medium, High Range 1-3 (1 low, 3 high) | Does it contribute to carbon reduction/ net zero?
| Additional Benfits | Additional | Y/N 1 for Y, 0 for N | Is the project in a high-need /deprived area? | If you do not know the level of need or deprivation of an area, consider using deprivation data such as the Index for Multiple Deprivation (IMD) or using the latest data from the ONS census. This data is available is spatial formats so you should be able to assess the deprivation level of the projects’ locations. You may consider a High/Medium/Low based on the level of deprivation or other more detailed approaches.
| Funding | Feasibility | Range 0 - 3: Full funding = 3 points, Partial = 2, Indicative = 1, None = 0 | Is funding fully or partially secured?
| Cost | Feasibility | Low, Medium, High Range 1-3 (1 High, 3 Low) | Project Cost | If more details are available, you may consider a more detailed scoring approach with cost categories (e.g. <£250K, £250K-£1M, >£1M)
| Timescales | Feasibility | Low, Medium, High Range 1-3 Example scoring bands: 0-2 yrs = High = 3, 2-5 yrs = Medium = 2, 5+ yrs = Low = 1 | Project Delivery Timescales | These ranges can be adjusted to better fit your requirements.
| Delivery Partners | Feasibility | Low, Medium, High Range 1-3 (1 low, 3 high) | Are capable delivery partners in place? | Considerations: Delivery mechanism, Solo delivery, or Joint delivery. Score weighted by past track record if available. You can choose to allocate scores based on your preferred delivery approach.
| Maturity | Feasibility | Y/N 1 for Y, 0 for N | Has the project reached a stage where feasibility or design work has begun? | You may also consider a weighted score depending on stage (e.g. feasibility complete = 1 pt, RIBA Stage 2 = 2 pts)

## Matrix
[10 empty] | Strategic Fit and Impact |  |  |  | Deliverability and Feasibility
[10 empty] | Strategic |  | Carbon | Additional Benfits | Funding | Cost | Timescales | Delivery Partners | Maturity | Weighting and Calibration 1 - 10 Importance | [8 empty] | Score
[10 empty] | Is the project related to a devlopment site allocation? | Does the project offer benefits across multiple service areas? | Does it contribute to carbon reduction/ net zero | Is the project in a high-need /deprived area? | Is funding fully or partially secured? | Project Cost | Delivery Timescales | Are capable delivery partners in place? | Has the project reached a stage where feasibility or design work has begun? | Strategic Criteria- Site Allocation Relation | Strategic Criteria- Cross Thematic Benefits | Carbon Benefits | Additional Benefits | Funding | Cost | Timescales | Delivery Partners | Maturity
Project Name | Delivery Partner | Cost | Direct Cost Savings | Indirect Cost Savings | Carbon Capture | Time Required to Deliver | Location | Description | Project Classification | Y/N 1 for Y, 0 for N | Low, Medium, High Range 1-3 (1 low, 3 high) | Low, Medium, High Range 1-3 (1 low, 3 high) | Y/N 1 for Y, 0 for N | Range 0 - 3: Full funding = 3 points, Partial = 2, Indicative = 1, None = 0 | Low, Medium, High Range 1-3 (3 low, 1 high) | Low, Medium, High Range 1-3 Example scoring bands: 0-2 yrs = High = 3, 2-5 yrs = Medium = 2, 5+ yrs = Low = 1 | Low, Medium, High Range 1-3 (1 low, 3 high) | Y/N 1 for Y, 0 for N | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Example 1 | [8 empty] | Local - Point Location | 1 | 3 | 1 | 1 | 3 | 3 | 2 | 3 | 1 | 5 | 5 | 1.6667 | 5 | 5 | 5 | 3.3333 | 5 | 5 | 40
Example 2 | [8 empty] | Local - Point Location | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1.6667 | 1.6667 | 0 | 0 | 1.6667 | 1.6667 | 1.6667 | 0 | 8.3333
Example 3 | [8 empty] | Strategic - Network (Multiple Locations inc. Roads, Paths, Trails) | 1 | 3 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 5 | 5 | 1.6667 | 5 | 0 | 1.6667 | 1.6667 | 1.6667 | 0 | 21.6667
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Presets (hidden)
Project Classification
Strategic - Point Location
Local - Point Location
Strategic - Network (Multiple Locations inc. Roads, Paths, Trails)
Local - Network (Multiple Locations inc. Roads, Paths, Trails)