## 0. Introduction
Planning Advisory Service Local Plan Project Plan Tool Purpose of the Tool This tool is intended to support local planning authorities (LPAs) that are proposing to submit a local plan for Independent Examination under the current system by December 2026. Specifically the tool seeks to support LPAs to: - develop and/or validate existing programmes they have produced; - help LPAs to map out key milestones, activities and interdependencies; - consider how risks that might influence preparation of the plan could affect the plan production timescale; and - inform decision making on the realistic achievability of submitting a local plan by the December 2026 deadline. Having a sufficiently detailed and robust project plan in place is vital in ensuring the timely and efficient progression of Local Plans. Putting in place a robust project plan may require an investment of time now, but it will save significant time and avoid wasted resources further down the line. The tool is informed by the experience PAS has gained over recent years in providing support and advice to LPAs about typical project management risks to Local Plans, and the evolution of best practice to try and mitigate those risks. The tool comprises six tabs: - Tab 1 (this tab) - provides an introduction on what the tool contains and how to use it; - Tab 2 - contains a summary tracker of key milestones for plan preparation, in a format intended to be easy to communicate to Members and senior officers, linked to the worked example in Tab 4. - Tab 3 - comprises a blank project plan template for LPAs to use; - Tab 4 - contains a worked example project plan drawing on the activities, tasks and durations typically expected to produce a legally compliant and sound local plan. For the purposes of illustration it assumes that Regulation 18 consultation has already been completed. Each LPA will be different with regard to its local context, processes, evidence and stage of plan preparation. This tool therefore does not attempt to reflect that complexity and variation, but has been designed to enable LPAs to tailor it to their local circumstances. To do this, it illustrates key elements of plan preparation, provides guidance on how long key activities might take as well as containing hints and tips which can help accelerate and/or streamline the plan production process. - Tab 5 - contains a template for logging and scheduling key meetings with Members, neighbouring authorities, delivery partners, developers/site promoters etc. - Tab 6 - is a template risk register. LPAs can use this tool for their plan making project management or use it to help sense check and inform existing project plans.
How to use the Tool The tool has a section for plan preparation that can be used to add information on the drafting of plan content. In the worked example there is a specific row on the development of site allocations and spatial strategy updates, alongside the drafting of the Regulation 19 version of the plan itself. Further rows can be added for different sections of plan content development if required. The interdependencies column can be used to highlight other relevant activities that are either required for that section of plan content to be developed or other aspects of the project plan that it will be needed for – this could be needed for other evidence to be produced, for stakeholder or Duty to Cooperate engagement or for other chapters of the plan to be drafted. Reviewing the timelines for the development of plan content alongside other key aspects of the programme will help with the setting of key milestones and also risks in achieving these which will need to be considered, for example evidence not being ready. The project plan tool can help with setting milestones for different legal and procedural requirements and identifying interdependencies with other parts of the local plan programme. In the worked example, the legal and procedural requirements are within a number of different sections – including engagement and governance, plan preparation and supporting documents, as well as legal requirements and information required for submission of the plan. You can tailor your own project plan to present the key requirements which are relevant to you and in the way that will be most helpful to manage your programme and keep track of different tasks. For example, you may want to have a more detailed section breaking down the different elements of your Duty to Cooperate engagements, or having multiple lines for different stages of the sustainability appraisal process. The main thing is having the key information with milestones associated with the different tasks in one place.
The worked example project plan is based on a number of assumptions - these should be amended as necessary to reflect local context. 1. This plan is based on the assumption that the LPA is at the start of Regulation 19 preparation and Regulation 18 has concluded. However, it is recognised that LPAs will be at different stages and can adapt the project plan as needed (although authorities that still envisage undertaking further Regulation 18 consultation should critcially examine whether it will still be possible to submit the plan by December 2026). 2. It is assumed that at the Regulation 19 stage, approval will given by the relevant committee/cabinet/ full council to publish for Regulation 19 and to delegate authority to submit the local plan for Independent Examination to the relevant senior officer. This avoids the need for further governance approvals before submission and enables a three month duration between end of Regulation 19 publication and submission of the local plan for Independent Examination. 3. It is assumed that no material changes will be required to the plan after the Regulation 19 publication stage1. 4. Regulation 19 publication is shown as running for six weeks (consistent with the statutory minimum). It is recognised each LPA will need to take their own view on the length of Regulation 19 publication to reflect local circumstances, including Statements of Community Involvement, but if more than six weeks is considered necessary this needs to be reflected appropriately in the programme. 5. The evidence section assumes some of the evidence for the local plan has already been completed and therefore focuses on those key evidence base documents where further work is typically required e.g. refining evidence to reflect the preferred growth strategy and policies. This includes: up-to-date development needs assessment (housing, GTAA, employment, retail (if required)); baseline and where needed spatial option appraisal including modelling for the Infrastructure Delivery Plan, Transport Assessment, Viability Assessment, Habitats Regulations Assessment, and up-to-date site selection selection assessment for sites submitted to the LPA prior to Regulation 18 consultation commencing. It is recognised that the status of the evidence base will vary significantly by LPA and their circumstances; and that each LPA will have evidence needs bespoke to their plan that may need to be included. In the worked example Green Belt has been included however it is recognised that this will not apply in every case. 6. The timescales in the project plan are set out to give the best chance of meeting the submission deadline. However, it is recognised that each LPA will have its own circumstances and some LPAs may need to have a more compressed process to achieve the December 2026 deadline. 7. The project plan runs up until the end of December 2026. However, it is recognised that some authorities will have to submit by 12 December if they are caught by the transitional arrangements in the NPPF (e.g. paragraph 237).
1 As set out in the PINS Local Plan procedure guidance if the LPA wishes to make changes to the plan following the Regulation 19 publication and before submission, and wish the changes to be considered as part of the submitted plan, this should be presented as an addendum to the plan containing the proposed changes. If the changes are significant, the addendum, together with a Sustainability Appraisal and Habitats Regulation Assessment of the proposed changes would need to be consulted on before the plan is submitted for examination. Where an LPA provides a list of proposed changes to the published plan that have not been the subject of consultation, the Inspector will not treat those proposed changes as part of the plan to be examined. However, the Inspector may consider it appropriate for some or all of the LPA’s proposed changes to be discussed at the hearing sessions, and in appropriate circumstances they may form the basis for Main Modifications. If such steps are potentially envisaged, a significant amount of additional time would be required within the programme.

## 1. PLEASE READ - Using the tool
Using the Summary Tracker, and formatting data
The Summary Tracker tab can be tailored to provide information on key/dates milestones and track progress on those. You can link to the key dates in the project plan tab by pressing “=” and then navigating to the right date in the project plan. This will mean the target date will automatically update when you update the programme tab.
The Project Plan has conditional formatting to help with populating the programme once start dates and end dates are added. Once you’ve populated it you may find it helpful to add your own visual aids to help identify key milestones, ‘pinch points’ and interdependencies.
Inputs can be made in Columns A-H. The date bars in the remainder of the chart are locked for editing, but will update based on the dates input in Columns E and F.
To ensure that the formatting of the tool remains protected, rows cannot be deleted. Text and dates can however be freely amended (in Columns A-H) to allow the renaming of tasks, or rows can be left blank if not required.
New rows can freely be added for additional tasks.
The 'Status' in Column D must be selected from a drop-down of valid options: Not started, Planned, In progress, Ongoing, Delayed, Completed.
The valid date range in Columns E and F is set to 2026, based on the December 2026 submission date for plans under the current plan-making regulations.
The Project Plan can be unprotcted if desired via the Review tab, then 'Unprotect Sheet'. However, given the risk of breaking formulae and formatting, this is not recommended.

## 2. Summary tracker
LDS Milestones | LDS key dates | Progress
Cabinet/Council approval date for Regulation 19 | 2026-09-01 | On track
Regulation 19 publication period | September-October 2026 | Not started
Submission date | 2026-12-01 | Not started
Regulation 18 key tasks | Key target dates | Status
Regulation 18 consultation period | 2026-12-07 | Delayed
Processing of consultation responses | 2026-01-05 | Not started
Draft consultation statement | 2026-02-13 | Not started
Regulation 19 key tasks | Key target dates | Status
PINS Local Plan Advisory Visit | 2026-05-25 | Not started
Finalise evidence to inform Reg 19 draft | 2026-07-13 | On track
Local Plan drafting | 2026-07-27 | Not started
Governance (approval of Regulation 19 Plan - report deadline) | 2026-07-27 | Not started
Regulation 19 publication period | 21/09/2026 - 26/10/2026 | Not started
Review and processing of representations | 2026-09-21 | Not started
Submission key tasks | Key target dates | Status
Complete PINS pre-submission checklist | 2026-11-23 | Not started
Finalise supporting documents for submission alongside Local Plan | 2026-11-16 | Not started
Approval of materials for submission | 2026-12-07 | Not started
Submission | 2026-12-14 | Not started
Timescales shown are linked to the Worked Project Plan in Tab 4. They are purely indicative and for illustrative purposes only.

## 3. Blank Project Plan
XX Local Plan - Project Plan Last updated: 22/12/25 | [7 empty] | 2026-01-01 |  |  |  | 2026-02-01 |  |  |  | 2026-03-01 |  |  |  |  | 2026-04-01 |  |  |  | 2026-05-01 |  |  |  | 2026-06-01 |  |  |  |  | 2026-07-01 |  |  |  | 2026-08-01 |  |  |  |  | 2026-09-01 |  |  |  | 2026-10-01 |  |  |  | 2026-11-01 |  |  |  |  | 2026-12-01
 | time axis 2026-01-05 to 2026-12-28
Stage | Activity | Tasks | Status | Start Date | End Date | Responsibility/ Officer(s) | Interdependencies/comments | time axis 2026-01-05 to 2026-12-28
Key dates/ milestones |  | Regulation 18 consultation | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cabinet/Committee/Full Council report deadline | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Regulation 19 publication period | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Submission for Independent Examination | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reg 18 |  | Regulation 18 consultation | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Regulation 19 stage | Reps analysis | Processing of consultation responses | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Draft consultation summary document | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Determine scope of updates to draft Plan and evidence base | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Outstanding technical evidence to be produced | Updates to Local Housing Need/Economic Development Needs | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Updated HELAA/site selection assessment | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transport Assessment | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Viability Assessment | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Infrastructure Delivery Plan | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Green Belt Exceptional Circumstances Topic Paper (if required) | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Urban design and site capacity evidence | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Climate change/sustainability evidence | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Strategic Flood Risk Assessment and/or Sequential test/exceptions paper | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Housing Trajectory | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plan preparation | Completion of PAS Local Plan Route Mapper toolkit | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Drafting of Regulation 19 Plan | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Site allocations & spatial strategy updates/refinement | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preparation of Topic Papers | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Proof reading of the plan before publishing | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications plan/strategy | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preparation for Regulation 19 publicity (including materials, feedback form & Statement of Representations procedure etc) | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Webpages updates and liaising with digital/comms in advance of publication launch | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PINS Local Plan advisory visit | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Appoint programme officer | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Supporting documents | Policies Map | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Finalise consultation statement | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Engagement & Governance | Developer engagement (& SoCGs where applicable) | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Engagement with statutory consultees (& SoCGs where applicable) | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Neighbouring and strategic authority engagement (& SoCGs where applicable) | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Officer working groups/engagement meetings | Not started |  |  |  |  | 2026-11-30: 0; 2026-12-07: 0; 2026-12-14: 0; 2026-12-21: 0; 2026-12-28: 0
|  | Member working groups/briefings | Not started |  |  |  |  | 2026-11-30: 0; 2026-12-07: 0; 2026-12-14: 0; 2026-12-21: 0; 2026-12-28: 0
|  | Cabinet/Committee/Full Council report deadline | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cabinet/Committee/Council meeting | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Regulation 19 publication period | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Legal requirements | Habitats Regulations Assessment | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equalities Impact Assessment | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sustainability Appraisal/SEA | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Submission |  | Processing of representations & consultation statement | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Finalise submission document (making and formatting/presentational changes required) | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Supporting submission documents (e.g. Topic Papers, Legal and Soundness Self Assessments) | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Complete & receive PINS pre-examination checklist (10 day turnaround time) | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Internal approval of materials for submission | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Submission | Not started |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 4. Worked Project Plan
XX Local Plan - Project Plan Last updated: 22/12/25 | [7 empty] | 2026-01-01 |  |  |  | 2026-02-01 |  |  |  | 2026-03-01 |  |  |  |  | 2026-04-01 |  |  |  | 2026-05-01 |  |  |  | 2026-06-01 |  |  |  |  | 2026-07-01 |  |  |  | 2026-08-01 |  |  |  |  | 2026-09-01 |  |  |  | 2026-10-01 |  |  |  | 2026-11-01 |  |  |  |  | 2026-12-01
 | time axis 2026-01-05 to 2026-12-28
Stage | Activity | Tasks | Status | Start Date | End Date | Responsibility/ Officer(s) | Interdependencies/comments | time axis 2026-01-05 to 2026-12-28
Key dates/ milestones |  | Regulation 18 consultation | Completed |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cabinet/Committee/Full Council report deadline | Planned | 2026-08-03 | 2026-08-03 |  | Governance and internal sign-off arrangements. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Regulation 19 publication period | Planned | 2026-08-10 | 2026-09-14 |  | Governance, stakeholder engagement strategy and LDS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Submission for Independent Examination | Not started | 2026-12-07 | 2026-12-16 |  | Dependent on key milestones being met. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
Reg 18 |  | Regulation 18 consultation | Completed |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Regulation 19 stage | Reps analysis | Processing of consultation responses | Planned | 2026-01-05 | 2026-02-13 |  | This will include identification of new sites that will need to be assessed. Also required for consultation statement on Regulation 19 publication. | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Draft consultation summary document | Planned | 2026-02-13 | 2026-03-27 |  | Required for Regulation 19 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Determine scope of updates to draft Plan and evidence base | Planned | 2026-01-05 | 2026-02-13 |  | Inform updates to evidence base and Reg 19 Plan | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Outstanding technical evidence to be produced | Updates to Local Housing Need/Economic Development Needs | In progress | 2025-06-10 | 2026-01-12 |  | Updated information - typically April release | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Updated HELAA/site selection assessment | Not started | 2026-01-05 | 2026-03-30 |  | Needs to be completed before housing trajectory can be done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Transport Assessment | In progress | 2025-10-13 | 2026-04-27 |  | Need draft suite of site allocations to test infrastructure impacts; may be some iterations depending on results. Outputs need to inform IDP | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Viability Assessment | Not started | 2026-05-04 | 2026-07-13 |  | Draft policies need to be in place to assess; plus confirmation of scale of costs (IDP and Transport Assessment) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Infrastructure Delivery Plan | In progress | 2026-01-05 | 2026-06-29 |  | Need draft suite of site allocations to test infrastructure impacts; may be some iterations depending on results | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Green Belt Exceptional Circumstances Topic Paper (if required) | Not started | 2026-03-30 | 2026-07-13 |  | Informed by HELAA/site assessment work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Urban design and site capacity evidence | In progress | 1899-12-31 | 2026-03-30 |  | Needs to be completed to inform site allocations, capacities assumptions and design policies. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Climate change/sustainability evidence | In progress | 2026-01-01 | 2026-02-02 |  | Needs to be completed to inform strategic policies. | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Strategic Flood Risk Assessment and/or Sequential test/exceptions paper | Not started | 2026-01-05 | 2026-03-23 |  | Needs to be informed by site allocations. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Housing Trajectory | Not started | 2026-03-30 | 2026-05-25 |  | Need draft suite of site allocations to understand implications for trajectory including need to allocate more sites/propose stepped trajectory. Likely interdependency with developer engagement & IDP. Housing delivery paper may also be required. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plan preparation | Completion of PAS Local Plan Route Mapper toolkit | Planned | 2025-10-06 | 2026-07-27 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Drafting of Regulation 19 Plan | Planned | 2026-01-05 | 2026-07-27 |  | Draft suite of site allocations and spatial strategy needed for different pieces of evidence to be progressed, to inform strategic policies and support ongoing engagement. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Site allocations & spatial strategy updates/refinement | Planned | 2026-02-02 | 2026-05-25 |  | Required for other evidence to be progressed e.g. transport assessment, infrastructure delivery plan, housing trajectory. | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preparation of Topic Papers | Ongoing | 2026-01-05 | 2026-12-07 |  | Dependent on the evidence base documents informing the content of the topic paper | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
|  | Proof reading of the plan before publishing | Not planned | 2026-06-22 | 2026-07-20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Communications plan/strategy | Not planned | 2026-05-11 | 2026-06-22 |  | Reflecting SCI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preparation for Regulation 19 publicity (including materials, feedback form & Statement of Representations procedure etc) | Planned | 2026-06-29 | 2026-08-10 |  | Regulation 19 publication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Webpages updates and liaising with digital/comms in advance of publication launch | Not planned | 2026-06-29 | 2026-07-06 |  | Regulation 19 publication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PINS Local Plan advisory visit | Planned | 2026-05-25 | 2026-05-25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Appoint programme officer | Not started | 2026-06-01 | 2026-06-29 |  | Required in advance of submission and takes time to appoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Supporting documents | Policies Map | Planned | 2026-02-02 | 2026-07-27 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Finalise consultation statement | Planned | 2026-06-22 | 2026-12-07 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Engagement & Governance | Developer engagement (& SoCGs where applicable) | Ongoing | 2026-02-16 | 2026-12-07 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
|  | Engagement with statutory consultees (& SoCGs where applicable) | Ongoing | 2026-02-16 | 2026-12-07 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
|  | Neighbouring and strategic authority engagement (& SoCGs where applicable) | Ongoing | 2026-02-16 | 2026-01-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Officer working groups/engagement meetings | Ongoing |  |  |  | Drafting of Regulation 19 Plan & plan approval | 2026-11-30: 0; 2026-12-07: 0; 2026-12-14: 0; 2026-12-21: 0; 2026-12-28: 0
|  | Member working groups/briefings | Ongoing |  |  |  | Drafting of Regulation 19 Plan & plan approval | 2026-11-30: 0; 2026-12-07: 0; 2026-12-14: 0; 2026-12-21: 0; 2026-12-28: 0
|  | Cabinet/Committee/Full Council report deadline | Planned | 2026-07-13 | 2026-07-13 |  | Plan approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cabinet/Committee/Council meeting | Planned | 2026-08-03 | 2026-08-03 |  | Plan approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Regulation 19 publication period | Planned | 2026-08-10 | 2026-09-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Legal requirements | Habitats Regulations Assessment | Planned | 2025-10-06 | 2026-07-13 |  | Need suite of sites plus potentially outputs from Transport Assessment (where air quality impacts are a potential issue) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equalities Impact Assessment | Planned | 2025-10-06 | 2026-07-13 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sustainability Appraisal/SEA | Ongoing | 2025-10-06 | 2026-11-16 |  | Need suite of sites to inform assessment and draft policies. SA needs to be iterative alongside the development of the Regulation 19 plan | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Submission |  | Processing of representations & consultation statement | Planned | 2026-09-21 | 2026-11-22 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Finalise submission document (making and formatting/presentational changes required) | Not started | 2026-09-21 | 2026-11-16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Supporting submission documents (e.g. Topic Papers, Legal and Soundness Self Assessments) | Not started | 2026-07-27 | 2026-11-16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Complete & receive PINS pre-examination checklist (10 day turnaround time) | Not started | 2026-11-23 | 2026-12-07 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0
|  | Internal approval of materials for submission | Not started | 2026-11-30 | 2026-12-07 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
|  | Submission | Not started | 2026-12-07 | 2026-12-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0

## 5. Key Meetings
Member meetings and/or briefings | Key target dates | Status
On track
Not started
Delayed
Not started
Meetings with neighbouring authorities and delivery partners | Key target dates | Status
On track
Not started
Not started
Not started
Developer/site promoter meetings (forums and/or one-to-one meetings) | Key target dates | Status
On track
Not started
Not started
Delayed

## 6. Risk Register
Risk number | Risk title | Risk description | Impact type |  |  | Unmitigated Probability (1-5) | Unmitigated Impact (1-5) | Unmitigated Risk Score | Mitigation | Mitigated Probability (1-5) | Mitigated Impact (1-5) | Mitigated Risk Score
|  |  | Delay? | Cost? | Quality? | [9 empty] | Risk Score |  |  |  |  | Key
1 | Short summary of the risk | Description of the risk and the specific impact that this will have on the successful progression of the Local Plan | Y/N | Y/N | Y/N |  |  | 0 | Description of action that will (or could) be taken to mitigate the risk, and how this will allow the probability and/or impact of the risk to be reduced |  |  | 0 | Impact | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | Low risk
2 | [7 empty] | 0 |  |  |  | 0 |  | 4 | 1 | 2 | 3 | 4 | 5 | 4 | 6 | Moderate risk
3 | [7 empty] | 0 |  |  |  | 0 |  | 3 | 2 | 4 | 6 | 8 | 10 | 8 | 12 | High risk
4 | [7 empty] | 0 |  |  |  | 0 |  | 2 | 3 | 6 | 9 | 12 | 15 | 15 | 25 | Extremely high risk
5 | [7 empty] | 0 |  |  |  | 0 |  | 1 | 4 | 8 | 12 | 16 | 20
6 | [7 empty] | 0 |  |  |  | 0 |  |  | 1 | 2 | 3 | 4 | 5
7 | [7 empty] | 0 |  |  |  | 0 |  |  | Probability
8 | [7 empty] | 0 |  |  |  | 0
9 | [7 empty] | 0 |  |  |  | 0
10 | [7 empty] | 0 |  |  |  | 0