## Slide 1: Delivering savings through ‘invest to save’ initiatives
Garry Cummings, Finance, Improvement and Sustainability Adviser to the East Midlands, Yorkshire & Humber and North East
www.local.gov.uk

## Slide 2: What is ‘Invest to Save’ & Why is it important
What is "Invest to Save"?
  Strategic approach where upfront investment leads to long-term savings or improved outcomes.
  Common in areas like digital transformation, social care, energy efficiency, and community services.
Why It Matters in 2025
  Rising demand for services vs. constrained budgets.
  Significant budget reductions
  Easier opportunities exhausted

## Slide 3: Key Principles
Efficiency: Reduce long-term costs.
Innovation: Result in new ways of working and delivering services
Sustainability: It must be the best solution over the long term
Stakeholder engagement key : engage early
Political Will: Are politicians willing to invest and potentially make difficult decisions
Data driven and evidence based

## Slide 4: What will we cover
Identification of potential schemes
Demonstrating a business case
Examples / Types of scheme
Key issues and considerations

## Slide 5: Types of Invest to Save
Changes in Service Provision
Digital Transformation
Capital investment / Infrastructure
Adult and Children Social Care – key area

## Slide 6: Challenges & Risks
Recognise the challenges up front
Upfront costs but savings and benefits take time.
Optimism bias – realistic about when savings will impact MTFP
How do we measure the benefit and change
  Baseline position is key
Cultural resistance to change
  Staff
  Wider Community & Residents

## Slide 7: Investments Required
Dependent on initiative
Revenue Costs
  Consultancy
  Staff Time and Resource
Major Capital Investment (borrowing)
  Buildings
  Infrastructure
New Technology
Recognise in Financial Plan
Corporate buy in key at early stage
  Chief Executive & Management Team
  Leader / Cabinet

## Slide 8: Baseline
What is the problem we are trying to solve
Clear scope
  define
  agree
Financial Position
Data and Performance
Benchmarks and Comparators – LG Inform
Basis for future monitoring

## Slide 9: Options Appraisal
Text book but important.
Define the Objective
  What is the project aiming to achieve
Identify Options
  Range of Options
  Do nothing, minimum, etc
Assess Costs and Benefits
Evaluate Risks and Dependencies
Determine preferred option = Invest to Save

## Slide 10: Business Case
A business case supports and justifies investment by showing:
  Strategic Fit, Value for Money,Affordability, Achievability, Viability
Demonstrate Investment Required
Source of funds
  Dependant upon scheme
  Revenue investment
  Capital / Borrowing
Comparison to baseline position

## Slide 11: Revenue Based Schemes
Change in Service Provision
Redirect revenue costs
Increase in some budgets resulting in savings elsewhere
No up front investment
Example
Increase in house foster carers
Increase in payments to in house
Reduction of payments to Agency

## Slide 12: Capital Investment
Change in Service Provision
Long Term investment
Consider costs of Capital
New Revenue Cost Base
Example
Build and operate Childrens Home
Fund Running Costs and Capital Costs
Reduction of External Placement Costs
Takes significant time

## Slide 13: Technology
Maximise use of Current Systems
  Has system been adapted to Council Processes
  Is there functionality not being used
  Are there opportunities to redevelop processes around systems
  Staff resistance
Use of new technology / AI
  Is technology proven / will it work
  Investment in developing solutions
  Every Council considering opportunities
  Example – Assistive technology supporting independent living

## Slide 14: Key Conclusions
Invest to Save – saves money but also can improve outcomes
Must be a clear rationale and business case
Savings not achieved overnight- takes time
Investment Required
  Revenue costs
  Capital / Investment
  Recognise early and build into plan
  Political buy in to principle early

## Slide 15: Key Considerations
Staff Resource and Capacity key
  Development and management of the project
  Implementation
  Dependant on scale of project
  Alongside day job or allocate resource
  Key to project
Change management required
  Cultural resistance to change
  Staff
  Wider Community & Residents
External Support

## Slide 16: Questions?

## Slide 17: Group Exercise - Discuss
Examples of Invest to Save Schemes
Key lessons learned – What are the do’s and don’t’s